## SEEEPHI updated budget 12-2021
Sharing European Educational Experience in Public Health for Israel (SEEEPHI)
618578-EPP-1-2020-1-BE-EPPKA2-CBHE-JP
Update: Wednesday 8 December 2021
Eligible budget of the project: |  |  |  | 886907.77
https://www.aspher.org/download/638/final_eligible_budget-618578-annex-iii.pdf
Payment schedule:
#1 | At the start of the project | 50% |  | 443453.885
#2 | After Y2 of the project | 40% |  | 354763.108
#3 | With the final reporting | Balance payment | up to | 88690.777
Initial payment to partners |  | 25% | Date | Amount
P1 | ASPHER |  | - | 27775.19
P2 | Ashkelon Academic College |  | 21-04-2021 | 25968.5
P3 | Hebrew University of Jerusalem |  | 29-04-2021 | 25302
P4 | University College Cork |  | 14-10-2021 | 17240
P5 | University of Haifa |  | 29-04-2021 | 26427
P6 | Jagiellonian University |  | 21-04-2021 | 16763
P7 | IAPHP |  | 21-04-2021 | 19012.5
P8 | Swedish Red Cross University College |  | 31-08-2021 | 15275
P9 | Ben-Gurion University of the Negev |  | 21-04-2021 | 29950
P10 | Maastricht University |  | 21-04-2021 | 18013.75
221726.94
| Project funds left (#1 payment) |  |  | 221726.945
DISTRIBUTION OF THE GRANT BY THE ORGANISATION (in EUR) based on the updated budget 12-2021
|  | Staff Costs | Travel Costs | Costs of Stay | Equipment Costs | Subcontracting | Total
P1 | ASPHER | 54175 | 7915 | 11280 | 0 | 36190.77 | 109560.77
P2 | Ashkelon Academic College | 27206 | 18280 | 23710 | 20500 | 7500 | 97196
P3 | Hebrew University of Jerusalem | 30638 | 18860 | 23710 | 20500 | 7500 | 101208
P4 | University College Cork | 38320 | 18020 | 14160 | 0 | 0 | 70500
P5 | University of Haifa | 30638 | 20140 | 24430 | 30500 | 0 | 105708
P6 | Jagiellonian University | 17782 | 10710 | 13560 | 0 | 25000 | 67052
P7 | IAPHP | 32840 | 13670 | 17040 | 0 | 12500 | 76050
P8 | Swedish Red Cross University College | 38320 | 10780 | 12000 | 0 | 0 | 61100
P9 | Ben-Gurion University of the Negev | 39708 | 18760 | 22510 | 45500 | 0 | 126478
P10 | Maastricht University | 43260 | 14275 | 14520 | 0 | 0 | 72055
Total |  | 352887 | 151410 | 176920 | 117000 | 88690.77 | 886907.77
% |  | 39.7885 | 17.0717 | 19.948 | 13.1919 | 10 | 100
Note on C14: ASPHER: See partnership agreement: https://www.seeephi.aspher.org/partner_zone/Partnership_Agreement/ Based on the eligible budget (original version prior to any adjustments): https://www.aspher.org/download/638/final_eligible_budget-618578-annex-iii.pdf
Note on G31: ASPHER: 1,309.23€ - Ineligible as above ceiling of 10% due to ineligible costs under Equipment costs.
Note on F37: ASPHER: 35,500.00 € - Partner is not a Higher Education Institution.
Note on C42: ASPHER: Cannot exceed 40% of the total eligible budget.
Note on F42: ASPHER: Cannot exceed 30% of the total eligible budget.
Note on G42: ASPHER: Cannot exceed 10% of the total eligible budget.

## SEEEPHI timeline w-budget ref
Project events and activities timeline
Activities | Y1M1 | Y1M2 | Y1M3 | Y1M4 | Y1M5 | Y1M6 | Y1M7 | Y1M8 | Y1M9 | Y1M10 | Y1M11 | Y1M12 | Y2M1 | Y2M2 | Y2M3 | Y2M4 | Y2M5 | Y2M6 | Y2M7 | Y2M8 | Y2M9 | Y2M10 | Y2M11 | Y2M12 | Y3M1 | Y3M2 | Y3M3 | Y3M4 | Y3M5 | Y3M6 | Y3M7 | Y3M8 | Y3M9 | Y3M10 | Y3M11 | Y3M12
WP1 Management
|  | BE 4D Kickoff | Kickoff report | Project Intranet |  | Partnership agreement |  |  |  |  | IE 4D Partners meeting | Meeting report | [7 empty] | PL 4D Partners mtg | Meeting report |  |  |  |  | SE 4D Partners mtg | Meeting report | [6 empty] | NL 4D Partners mtg | Meeting report
[12 empty] | Y1 report | [11 empty] | Y2 report | [11 empty] | Final report
WP2 Field Qualifications
|  |  | IL 3D W mtg, AAC & HUJI | Survey Instrument | [5 empty] | IL 3D W mtg, AAC & HUJI | Survey Report
Survey of IL Health System
WP3 Schools & Programmes
|  |  | IL 3D W mtg, AAC & HUJI | Survey Instrument | [5 empty] | IL 3D W mtg, AAC & HUJI |  | Survey Report
Survey of IL HEIs
WP4 Workforce Adaption
[6 empty] | Development of PHI Reference Framework | [18 empty] | Practical Placement scheme and development of Career fair
[15 empty] | Organization of practical placement schemes | [11 empty] | PHI Practical placement scheme |  |  | Career fair
[14 empty] | IL 4d W mtg, Haifa |  |  |  | PHIRF online tool |  |  |  | PHI Practical placement scheme |  |  |  |  | IL 4d W mtg, Haifa
WP5 Leadership Capacity Building
[15 empty] | Development of Leadership Academy | [11 empty] | IL 2D each Pilot of Leadership Academy 5+1 | [5 empty] | Report from pilots |  | IL 2D Final Pilot | Report from final pilot
[19 empty] | IL 4D W mtg, BGU |  |  |  |  | Training Manual | [6 empty] | IL 4D W mtg, BGU | Evaluation & adaption of Leadersip Academy
WP6 Stakeholder Engagement
[13 empty] | Dpt of IAMPH campaign |  |  | Campaign Plan |  | Campaign Happening, IAPHP Conf | Campaign Stories |  |  | Campaign Stories |  | Campaign Stories |  | Campaign Stories |  | Campaign Stories |  | Campaign Stories | Report from campaign |  | Campaign Stories |  | Campaign Stories
[15 empty] | Set up PHW Register | [14 empty] | Campaign Happening, IAPHP Conf
[17 empty] | IL 3D W mtg, IAPHP |  | PHW Register
WP7 Dissemination
|  | Project website | Maintain website
|  |  |  | EUPHW online |  | Newsletter |  | ASPHER D&D |  | EPH online |  | Newsletter |  |  |  |  | ASPHER D&D | Newsletter | [5 empty] | Newsletter |  |  |  |  | ASPHER D&D | Newsletter |  |  |  |  | EPH Pre conference | Newsletter
[18 empty] | IAPHP Conference | [11 empty] | IAPHP Conference | [5 empty] | PHR supplement
WP8 Quality Plan
|  | Election of EC |  |  | Interim EC - online | Minutes |  |  |  | Interim EC - online | Minutes |  |  | IL 2D EC meeting | Y1 EC Report |  | Interim EC online | Minutes |  | PL 1D Interim EC | Minutes |  | Interim EC online | Minutes |  | SE 2D EC meeting | Y2 EC Report |  | Interim EC online | Minutes |  | Interim EC online | Minutes | NL 2D EC meeting | Final EC Report
| Y1M1 | Y1M2 | Y1M3 | Y1M4 | Y1M5 | Y1M6 | Y1M7 | Y1M8 | Y1M9 | Y1M10 | Y1M11 | Y1M12 | Y2M1 | Y2M2 | Y2M3 | Y2M4 | Y2M5 | Y2M6 | Y2M7 | Y2M8 | Y2M9 | Y2M10 | Y2M11 | Y2M12 | Y3M1 | Y3M2 | Y3M3 | Y3M4 | Y3M5 | Y3M6 | Y3M7 | Y3M8 | Y3M9 | Y3M10 | Y3M11 | Y3M12
886907.77 |  |  | 443453.885 | [21 empty] | 354763.108 | [11 empty] | 88690.777
SEEEPHI account current balance: |  |  | 443453.885 |  | 254241.945 |  |  |  | 238966.945 |  | 221726.945
Key
Duration of WP activity
Activity held, but no physical meeting
Activity held/completed
Activity/Meeting yet to be completed involving travel
Activity/meeting yet to be completed not involving travel
Added event