SEEEPHI UCC Partners Meeting

04-05 September 2023

action points

WP4 Online Platform:

JU needs answer by end of November on where to transfer the platform

Platform is in wordpress and simple to use, but requires about 1-2 h per week for maintenance of data

Member schools may participate together to fund

The IAPHP was seen as best option as it won’t create bias toward one school

The site of the server hosting the platform does not need to be in the same location as the person maintaining it.

Action:

IAPHP agreed to explore once more with the PH services and then take a decision within 2 weeks time in consultation with Israel Partners to discuss any further concerns/requirements on how to support. Meeting to be set with Israel partners during week of 10 Sept.

WP4 placement scheme:

UH gathering information from all schools to report on this – also requested from Tel Aviv.

Action:

All partners reply to Haifa with requested information

Other:

Partners agreed it would be desirable to reinstitute an annual meeting of Heads of Schools leading into the IPH conference.

New head of school at Tel Aviv - ASPHER schedule a call

WP5: 5+1 Peer Train the Trainer sessions:

ToT sessions need to be scheduled for Haifa and HUJI; AAC also interested to schedule a session

Final +1 session in person in February with Maastricht in Israel – all partners invited

Must confirm the 6 total sessions for reporting

For HUJI, contact needs to be made with Ronit Calderon

Actions:

Nadav to contact and arrange to meet with faculty at HUJI and with Maya at Haifa- also including Kasia and Jascha online for training sessions.

Clarify the schedule of the 5 ToTs

Schedule February crowning training session

WP7 Dissemination events:

EPH Conference:

No longer the final dissemination workshop

Satellite event on simulations to schedule morning of 08 November

Israel country meeting – request to hold on Friday to include SEEEPHI participation

Action:

finalize EPH schedule and notify partners for travel planning

IAPHP Conference – In country final dissemination:

Schedule before end of extension period (May-early July) – note ASPHER D&D scheduled 13-15 June

Consider to hold in Jerusalem.

AAC open to host again

Action:

Hagai to contact HUJI head of school about Jerusalem hosting

Brussels meeting – EU final dissemination:

Consider a final event in Brussels coinciding with Maastricht PM (April)

WP6 IAMPH Campaign and reporting:

Actions:

Campaign plan and report from campaign need to be written up

Final campaign clips to be made available to all partners: raw materials to be made available to Israel Schools

IAPHP to schedule meeting with SRCU for update

WP1

Partners meeting in Maastricht:

Suggested to schedule for April

Action:

Canvas dates and confirm

Second budget distribution:

Second budget payment received from ERASMUS

EU partners will be prioritized to top up budget  to 70/75% as they have only received first budget payment of 25% (with exception of JU for subcontract)

Other partners may request budget and be considered case by case.

Action:

ASPHER to distribute funds to EU partners

Financial reports from October 2022 to be updated for further requests

WP8 Quality plan

Year 2 report needed

Schedule EC Zoom meeting and in person Dublin meeting with internal EC members, Walter and Paul onsite

Consider Maastricht meeting onsite in April

Action:

Clarify final year meeting schedule

Provide Y2 report