|  |  |  | Application Form Selection: 2020 KA2 – Cooperation for innovation and the exchange of good practices – Capacity Building in the field of Higher Education |
| --- | --- | --- | --- |

Call for Proposals 2020 - EAC/A02/2019

Sharing European Educational Experience in Public Health for Israel (SEEEPHI): harmonization, employability, leadership and outreach

DETAILED DESCRIPTION OF THE PROJECT

JOINT PROJECTS

(To be attached to the e-Form)

Please note that, in accordance with Article 193 of the “Financial Regulation Applicable to the General Budget of the Union”, grants cannot be awarded retroactively. This means that activities covered by the grant can only be implemented as from the date on which the last party has signed the grant agreement.

As it might not in all cases be possible to sign the grant agreement for a selected proposal before the start date indicated in the application, the project planning should ideally cater for this possibility.

If your work plan does not allow for the necessary flexibility to adapt to such an event and/or if you have scheduled activities that must start on a particular date in the very early phase of the proposed action, you should provide a justification. The justification should explain the reasons why the activities in question cannot be postponed if the contract is not signed by 15 November 2020 or 15 January 2021) and need to take place on the foreseen date.

If this is the case for your project, you should specify below the following (max 3000 characters):

- the date on which the consortium would need to start its project activities covered by the grant. Only from this date on costs covered by the EU grant can be incurred;

- a detailed justification. The justification should explain why the activities foreseen (and their corresponding costs) cannot be delayed and why such a delay would jeopardise the project’s implementation.

NA

# PART D – Relevance of the Project

# D.1 Why does the consortium undertake this project?

- Which problem(s) will the project address in the participating Partner Countries? Why are these problems pressing?

- Please explain the result of the need analysis carried out for each Partner Country and for each Partner institution and provide qualitative and quantitative evidence for your results. Please refer also to studies carried out and feasibility analyses undertaken. In particular explain for each institution, why the support from the CBHE action is required. (limit 10.000 characters)

The overall objective for the proposal has been defined as enhancement of the Public Health Workforce (PHW) in Israel through sharing European educational experience, including: harmonization, employability, leadership and outreach. As in Europe and elsewhere, public health (PH) challenges in Israel have become more complex. PH professionals must address an expanding set of needs to serve the health of changing epidemiology and population demographics. Infectious disease concerns remain, complicated by newly emerging infectious diseases, growing vaccination refusal and antibiotic resistance. While non-communicable diseases have moved to the forefront of a changing and ageing population in the form of cardiovascular disease, obesity and cancer. Meanwhile, new technologies and scientific advances bring opportunities but also complications for PH. In order to face challenges and meet the needs of potential employers, the PHW must be appropriately trained with problem-solving and leadership skills that can only be attained through real-world examples and experiences. Education and training must be appropriate at each level of the professional degree development (Bachelor, Master, PhD, Postdoc, Continuing Professional Development (CPD)) so that PH professionals may meet employers’ needs and expectations on entry to the workforce and subsequent career paths. PH training must also be available to and appropriate for different kinds of health and other relevant professions, such as academization in nursing, dental hygiene, research coordination, environmental health, medical technology, etc. In May 2017, the Israeli Council for Higher Education (CHE) evaluated several higher education institutions (HEIs) to assess their programmes in PH. Ben-Gurion University of the Negev (BGU), University of Haifa (UH) and Hebrew University of Jerusalem (HUJI) were evaluated. Ashkelon Academic College (AAC), a partner in this proposal, was not included as its new Bachelor (BA) in PH was still in its initial approved phase. CHE met with stakeholders at the institutions, including management, faculty, staff, students and alumni. Based on the evaluations, in October 2017, CHE reported recommendations both at the individual institutional level and overall for all Israeli Programmes in PH. This is the most recent evaluation of schools of Public Helath (SPH) in Israel and the report reccomendations remain valid today. While developing this proposal, ASPHER further consulted the CHE findings with the Israeli Partner Schools (BGU, UH, HUJI, AAC) for better need and feasibility analysis. ISRAEL-WIDE RECOMMENDATIONS INCLUDED: 1. Establish the Master of PH (MPH) degree as a professional degree, and revise the expectation for research (i.e., theses) in professional degree programmes. CHE identified problems balancing traditional academic PH education versus professional, practice-oriented training. CHE believed that MPH graduates should have a professional identity comparable to other professional degrees and recommended options to broaden the definition of what constitutes a MPH thesis to include a practice-oriented or problem-solving thesis. They encouraged faculty and students to work on MPH theses that relate to current PH issues to better serve the needs of the PH profession. Although this recommendation was made by CHE only for the MPH degree, Partner Schools have recognized the need to better prepare all Israeli PH students to meet the needs of employers for confronting challenges in PH. The current traditional, lecture-based learning system in place in most classrooms in Israel is inadequate and there is a need to adopt experiential, problem-based learning (PBL) and to teach leadership skills at all education and training levels - as adopted in many Schools and Programmes of PH in Europe. 2. Learning Outcomes (LOs) should be developed for each course and curriculum to prevent gaps as well as overlaps in curriculum content. LOs should be assessed for each student prior to their graduation. The Bologna Working Group on Qualifications developed LOs as a means of specifying expectations for what a student should learn from a particular course and the curriculum as a whole for programmes in Europe. In Israel, CHE observed that most programmes in PH have not fully embraced the concept of LOs. CHE recommended that all programmes in PH adopt processes for developing LOs and regular assessment of the content of individual courses and entire curricula to ensure that courses and degree programmes provide students with the skills and knowledge necessary to be effective PH professionals. The Israeli Partner Schools have also recognized that clarification and harmonization of LOs across degree programmes will allow students to move more efficiently through their educational trajectory, reducing overlap in course requirements if they choose to progress from Bachelor to Master, or Master to PhD. Competencies assessments in use in Europe would aid in ensuring students met the desired LOs at each step of their education. CHE also observed that some programmes relied on multiple-choice exams, which CHE strongly believed could not correctly assess LOs. In implementing experiential PBL, European Schools have developed alternative methods of educational assessment. 3. Waive the requirement for postdoctoral experience overseas as a criterion for academic appointments. Candidates for full-time tenure-track academic appointments in Israel are required to have international postdoctoral experience. CHE found that the policy could result in the loss of high-quality faculty candidates, and contribute to gender and ethnic bias against groups with less access to pursue postdocs abroad. CHE recommended that the requirement for international postdoctoral experience be waived. The ties created between European and Israeli schools will increase partnering opportunities for postdoctoral studies abroad, while also bolstering postdoctoral programmes within Israel itself - thereby improving the accessibility and quality of training at the highest level of the PHW. CHE FINDINGS SPECIFIC TO EACH PARTICIPATING ISRAELI HEI: UH: CHE found that students wanted more course content with practical problem solving. CHE therefore advised UH to increase the practical content of courses across their MPH and PhD programmes. CHE recommended that the school continue to develop and strengthen its alumni association. BGU: CHE found that students had concerns about a lack of integration of experiential learning, noted duplication of content between courses and lengthy time to graduation. CHE found that many of the introductory courses seemed basic for students with professional backgrounds. CHE advised that field experiences in healthcare settings would be enriching to students. As a result, CHE recommended that BGU increase the practical content in courses, review courses for repetition, make efforts for more timely graduation, improve career guidance, and increase field experience and connection to the regional medical centre. CHE advised that BGU forecast for the relevant needs of the Israeli health sector to ensure that their graduates have required skills. CHE recommended an alumni survey to monitor the progress of graduates. HUJI: CHE advised the school to improve the timeliness of graduation and strengthen its Israel alumni relations programme. CHE noted that a promising faculty candidate was lost due to the postdoc abroad requirement, highlighting the need to provide more flexible opportunities for postdocs abroad, while raising the calibre of local Israeli postdocs. AAC: The first BA degree programme in PH was confirmed in late 2017 and was not included in CHE’s evaluation. Enrolment in the BA in PH has grown from 14 students in the first class to 37 students in the third class. As this is a new degree in Israel, the school is still determining how it fits to serve the PHW and student’s education goals. Some students will take the BA as a terminal degree and must be empowered to seek entry in the PHW. Feedback is needed from employers to improve student preparation. For students who wish to continue their studies, redundancy in coursework must be avoided. European HEIs have tested solutions that may be offered to respond to the needs identified by CHE. ASPHER, in partnership with other European-level organisations such as the World Health Organization (WHO) Regional Office for Europe, has developed tools for assessing the qualifications required by employers for the PHW, and for accrediting and credentialing PH schools and professionals. The tools are designed to be adaptable for use across European Region’s diverse national contexts and can thus also be tailored to Israel’s unique needs. European Partner Schools have methods to train new faculty and instructors on how to implement PBL and leadership training and can transfer this to Israel. They also have long-standing PH training for Bachelor students and CPD offers, and can share relevant experience on academic progression, employment and career opportunities in PHW. CHE reports are available in English at: https://che.org.il/דוחות-הערכת-איכות-בתחום-בריאות-הציבור/

(Please add Partner Countries/partners as appropriate)

Please identify the target groups and their needs in each Partner Country and in each Partner Country institution. (limit 8.000 characters)

The Partner Country, Israel through its Council of Higher Education (CHE) has identified the need to strengthen public health (PH) education and provide graduates of PH programmes in Israel with practice-oriented, problem-solving training in order to better serve the needs of the PH profession in work and projects that address PH problems in Israel. The key target groups identified and their needs applying to all five participating Israel Partners are: SCHOOLS AND PROGRAMMES OF PUBLIC HEALTH: to clarify competencies required by graduates to meet the needs of employers at each academic degree level and throughout continuing professional development; to develop guidelines for clear academic and career progression in PH; FACULTY: to provide training in methods of practical, problem-based learning (PBL); to define and appropriately evaluate student’s learning objectives (LOs); and to promote leadership skills. STUDENTS AND ALUMNI: to ensure that students of PH programmes in Israel obtain experience in addressing PH issues in practical problem-solving research or programme interventions, along with leadership skills required for employment upon graduation. EMPLOYER ORGANISATIONS: to identify the competencies they require from the PH professionals so that education and training is appropriately responsive to meet their needs. PUBLIC HEALTH WORKFORCE (PHW): to empower professionals in the PHW with an academic degree and an adequate training offer, as well as clear PH identity for professional advancement; to provide guidance and continuing professional development that matches employers’ needs. MINORITY GROUPS: to provide career opportunities through access to higher education and training in PH for students from peripheral areas and marginal populations; to improve health awareness and services in PH in their local communities, and promote population health standards and the PHW, especially in underserved regions of the country. PUBLIC HEALTH SYSTEM GOVERNANCE STRUCTURES: to influence relevant policies for PH workforce development and professionalization strategies. Specific context for each school/institution include: ASHKELON ACADEMIC COLLEGE (ACC): The programme at ACC is the first Bachelor level degree available in PH in Israel and seeks integration with other HEIs in Israel and Europe and guidance for career placement and progression to continuing studies in PH or related professions such as nursing, dental hygiene, research management, environmental health, and medical technology. Regional minority groups include Arab, Bedouin and Orthodox (Haredi) communities in southern Israel. The school aims to increase the supply of professional workforce and academization of the health workforce in a deprived region through outreach and networking with local municipalities, hospitals, sick funds, in health promotion such as in smoke free communities and hypertension awareness and control. UNIVERSITY OF HAIFA (UH): The school trains Master, PhD, and Postdoctoral students in the field of Health Promotion and runs an international Master of PH (MPH) programme in Global Health Leadership and Administration. The student body reflects the regional makeup with significant numbers of Arab (49%) and Ethiopian refugee minority students. There is a need for more learning opportunities for these students and to develop internship and placement opportunities as part of the study programmes. The school services the very diverse population in the northern region of Israel focusing on research and community cooperation that include the Arab population and other minorities and at risk population such as the Ethiopian community and lower socioeconomic status communities. UH is working to affiliate with the Haifa District of the Ministry of Health. It works with Mother and Child Healthcare Centres and other organisations with senior staff in health promotion. The school wishes to develop and broaden collaborations with the healthcare sector such as Health Maintenance Organizations where students will be able to participate in planning, implementing and evaluating interventions, not only for the health of the community but also for patients groups. BEN-GURION UNIVERSITY (BGU): The school’s Master, PhD, and Postdoctoral students pursue studies in PH, Health Policy and Management, and Health Disaster Management. A strong focus is given to dealing with health inequities in the periphery, community health, and minority's health, reaching out to local Arab and Bedouin Communities in the southern Negev region. HEBREW UNIVERSITY OF JERUSALEM (HUJI): The school trains Master, PhD, and Postdoctoral students in PH, Health Administration, Clinical Epidemiology and Veterinary PH and grants an international MPH degree primarily to professionals from lower-income countries. 25% of students are Arab minorities and Palestinian students study in the international MPH programme. The school collaborates with scientists from around the world including the Palestinian Authority. It is deeply involved with the local communities in Jerusalem, Israel and beyond particularly with mentoring and lifelong learning activities in sub-Saharan Africa. The school aims to reach out to serve the community and strengthen social systems that cross political, religious and socio-economic boundaries both globally and locally; to expose students to medicine, healthcare systems and health outcomes in cultures and settings different than the ones they are familiar with, in order to make them more aware, culturally sensitive and resourceful and adaptable in their own settings, and to be aware of disparities on regional or geographical levels. ISRAELI MEDICAL ASSOCIATION – ISRAELI ASSOCIATION OF PUBLIC HEALTH PHYSICIANS (IMA/IAPHP): In order to expand the professionalization of the PH workforce IAPHP wishes to expend its scope of membership, to collaborate closely with all Israeli schools of PH, and to all PH professionals (including non-physicians) trained and engaged in PHW/PH professional work. Through annual conferences and workshops IMA/IAPHP reaches students and practitioners of multi-disciplinary groups from the wider fields of PH practice and research, in a variety of PH fields such as epidemiology, health policy, health promotion, environmental health and others. Through its Public Health Forum, IMA/IAPHP promotes work on urgent PH issues addressing PH reforms, health inequalities, climate change and health, tobacco control, healthy nutrition, vaccinations and more across Israel. Through PH law reform, IMA/IAPHP strives to strengthen PH infrastructures, personnel and public planning.

(Please add partner countries/partners as appropriate)

How will the project address the relevant thematic national/regional priorities (see https://eacea.ec.europa.eu/erasmus-plus/funding/capacity-building-higher-education-2019_en) set by the Programme for its target country (ies)/region(s)? (limit 8.000 characters)

The project addresses NATIONAL PRIORITY 3 for Israel: Developing the Higher Education Sector within Society at large. The proposal specifically targets: UNIVERSITY-ENTERPRISE COOPERATION – SUCH AS SUPPORT TO STUDENTS’ PRACTICAL PLACEMENT, ENTREPRENEURSHIP, EMPLOYABILITY OF GRADUATES, etc. Despite progress in improved longevity and reduced mortality from infectious and non-infectious diseases, and improving economic status, Israel faces important health effects, challenges of poverty (20% of the total population and 30% of children), inequities between ethnic and religious groups including the Ethiopian refugee, Arab, Bedouin and Orthodox (Haredi) Jewish population as compared to the middle and upper economic Jewish population especially in the central urban centres. The PH community has proven crucial to address this kind of challenge. The key purpose of the project proposed is to engage with European HEI partners to transfer lessons learned in education and training of the PH Workforce (PHW) to address the needs of employers and the wider social environment across several distinct country/regional contexts. Within Israel, this will require outreach to employers and communities, minority groups, inter-sectoral partnerships and advocacy of PH legislation and policies. The basic philosophy of PH education in Israel must shift from its over-emphasis on academic epidemiology and lecture-based learning to practical, pro-active PBL and advocacy for population health enhancement. The student population and their instructors need to be oriented to health problem identification, working with many partners and leading to seek solutions to the current and future challenges of PH. The skills required of the PHW population are changing and the HEIs in Israel need to make the changes in programmes that have already been undertaken by their European counterparts. The project will address these priorities by reaching out to understand the needs of employers and the communities the PHW serves and subsequent development of measures to ensure that shools and programmes of PH are able to train students in the field qualifications needed to meet the expectations of the job market. Preparation will be carried out through methods of mapping of field qualifications and competencies needed by employers at entry, competent, and expert levels to ensure coverage of standards and professional roles in the PH system and to enable comparison of qualifications by education/training providers, employer organisations and other relevant stakeholders. Israeli HEIs will also be assessed to determine the competencies currently taught at each educational level - Bachelors, Masters, Doctorate, Post-Doc and CPD. Crowning the preparatory phase, HEI, Employer and community feedback will be explored to make recommendations to HARMONIZE the qualifications required to meet employer needs and address skills mismatches at each level of Israel’s PH educational programmes. Programmes and schools will receive advice on how they may best meet the educational and training requirements of PH students and professionals as they move through the progression of their education and careers. This will permit students to work with faculty and instructors to better direct their education to serve their current and future careers while minimizing course overlap for students and maximizing workforce skills diversity for employers through practical coursework, theses and placements. A web-based Information Technology (IT) tool will be implemented to address EMPLOYABILITY and serve as an interface between HEIs, students, alumni, PH professionals, employers, and the community to sustain contacts. It will provide a network for practical placements for both internship and employment, and provide career guidance. It will be an important checkpoint for HEIs to maintain the relevance of their training and curricula as the needs of PH and employers evolve in the future. A PH LEADERSHIP academy will be established in Israel to provide sustained peer education and training to PH faculty and trainers to support the introduction of problem-based and leadership teaching and evaluation methods into their coursework and curricula. PH needs do not remain static as new threats to population health change and opportunities to address them emerge that require leadership with knowledge, vision and a sense of mission to promote population health. Stakeholder engagement will be secured via cross-disciplinary, -professional and -sectoral OUTREACH promoting the importance of PH for employers and the community and underlining how engaging the wider PHW improves the health of the population.

(Please add Partner Countries/regions as appropriate)

# D.2 Aims and objectives

- What does the proposal aim at in general? What are the project’s specific objectives?

- Explain how the specific objectives of the project address the problems mentioned in Part D1 and the needs of each target group in each Partner Country. Demonstrate also that the set objectives are realistic and feasible in the national and institutional context(s).

(limit 8.000 characters)

The overall aim for the proposal has been defined as ENHANCEMENT OF THE PUBLIC HEALTH WORKFORCE (PHW) IN ISRAEL THROUGH SHARING EUROPEAN EDUCATIONAL EXPERIENCE, INCLUDING: HARMONIZATION, EMPLOYABILITY, LEADERSHIP and OUTREACH. Under the above-mentioned aim and based on the evaluation reports of the Israeli Council for Higher Education (CHE) (https://che.org.il/דוחות-הערכת-איכות-בתחום-בריאות-הציבור/) and in consultation with the needs expressed by the Israeli Partner Schools (see section D1), the proposal has developed the following specific objectives. The ASPHER/WHO Europe Road Map to Professionalizing the Public Health Workforce (RMPHW) (https://www.aspher.org/download/245/professionalizationroadmap-finaldraft_23-05-19.pdf) will be used as an overall guiding document and tool to realize the proposal's aims. 1. DETAILED ANALYSIS OF FIELD QUALIFICATIONS CONTENT TO UNDERSTAND DIFFERENT PROFESSIONAL ROLES IN THE ISRAELI PUBLIC HEALTH SYSTEM. In preparation to meet the aim of enhancing the PHW in Israel, the different professional roles needed in the Israeli PH system must first be understood. In order to ensure adequate coverage of standards and roles, mutually understandable descriptors of competencies are needed to identify potential skills gaps and to inform development of training and educational programmes to match job market needs. Mapping field qualification expectations through survey and key person/organisation interviews will enable comparison of competencies by education/training providers, employer organisations and other relevant stakeholders. Developing a full picture of employer and community PHW needs will allow HEIs in Israel to more appropriately tailor their programmes to meet the real-world conditions that await students upon graduation, while strengthening the ties between HEIs, communities and employers. The WHO-ASPHER Competency Framework for the Public Health Workforce in the European Region (CFPHW) (https://www.aspher.org/download/365/05-11-19_phcomp-draft10.pdf) provides a means to evaluate the competencies needed at three levels of the workforce (entry, competent, expert) and can be applied to analyse the field qualifications needed by Israeli employers and communities. The multi-level aspect of the Framework corresponds well with the goals of the Israeli HEIs to understand the qualifications required by PH students at each education level. 2. MAPPING OF THE COMPETENCY PROFILES OF THE ISRAELI SCHOOLS AND PROGRAMMES OF PUBLIC HEALTH TO GUIDE HARMONIZATION BETWEEN PUBLIC HEALTH EDUCATION AND PRACTICE. Harmonization will be guided by the results generated in the preparatory phases to determine field qualifications required by employers and the mapping of competency profiles of Israeli HEIs of PH. Recommended guidelines of competencies and learning outcomes (LOs) needed by Israeli PH students at each degree and specialist training level will be generated. ASPHER’s European Core Competences List for the Public Health Professional (ECCLPHP) (https://journals.sagepub.com/doi/full/10.1177/1403494818797072) can be applied for curricula development, defining entrance and exit competencies to be achieved in courses and comprehensive programmes, testing of students’ competencies and setting competencies to be achieved or sustained during continuing professional development. Moreover, a critical number of HEIs in PH in Israel are committed partners to this project and will be receptive to the recommendations generated. 3. INTRODUCTION OF A DYNAMIC ONLINE INTERFACE TO ENABLE PUBLIC HEALTH EDUCATION/TRAINING – PRACTICE/WORKFORCE COLLABORATION, SUPPORTING EMPLOYABILITY AND CONTINUING PROFESSIONAL DEVELOPMENT IN THE ISRAELI PUBLIC HEALTH SYSTEM. This will be a platform for on-going interactions between the PH system, HEIs, employers, communities, students, alumni, faculty and PH professionals. It will serve to provide internship, employment and practical opportunities, individual career development guidance, and workforce capacity system planning. ASPHER’s European Public Health Reference Framework (EPHRF) (https://www.aspher.org/download/27/ephrf_concept_and_policy_brief.pdf), consisting of a systematic and flexible tool to contribute to the planning of the PHW as well as guiding of individual careers, education and training choices will serve as a model for developing the Public Health Isratil (PHI) PHRF platform accompanied by supporting supporting Practical Placement Schemes each semester annual Career Fair events. Insight provided by the first two preparatory phases of the project (objectives 1 and 2) will be taken into account for the tool develoment. IT support will be subcontracted to build the online infrastucture for the platform, which will subsequently be maintained and hosted by the Israeli HEIs. 4. BUILDING LEADERSHIP CAPACITY VIA CUTTING EDGE TRAINING IN THE ISRAELI PUBLIC HEALTH SCHOOLS AND PROGRAMMES, INCLUDING PEER-TO-PEER AND TRAIN THE TRAINERS OFFERINGS. Improvement in the education of students of PH will be met through the training of faculty and staff at Israeli HEIs in practical problem-based learning (PBL) and leadership training techniques. This must include techniques to appropriately evaluate students’ achieved LOs. In Israel, planning is underway to build a Leadership Training Academy in PH and this project will support this effort accordingly. The Leaders for European Public Health (LEPHIE) (https://www.aspher.org/download/85/lephie-for-aspher-newsletter.pdf) training was designed in recognition that courses offered by schools of PH often failed to meet the needs and expectations of the PHW. LEPHIE addresses the need for courses in leadership and critical thinking. The experiences and lessons from LEPHIE and the teaching methodologies used in European HEIs can be transferred to the Public Health Israel (PHI) Leadership Academy that is under development, which will then serve to sustain training activities locally. 5. STAKEHOLDER ENGAGEMENT TO SECURE KEY OUTREACH (COMMUNITY, INTER-PROFESSIONAL, CROSS-SECTORAL) NEEDED TO SUSTAIN THE PROPOSED SOLUTIONS. Stakeholder engagement with employers and the community must be assured. HEIs in PH must also build partnerships with key professional groups needed to promote integration of PH graduates across the broader PHW in Israel; to promote awareness to prioritization in resource allocation for PH and advance recognition and professionalism of the Israeli PHW. A campaign will be developed to raise awareness of PH and its roles, expanding on the ongoing "This is Public Health" campaign (https://www.aspher.org/this-is-public-health-tiph.html) to feature a new "I am Public Health" component to showcase roles and functions filled by members of the PHW. Visibility for the campaign will be given online and at various events and conferences in Israel. Campaign efforts to promote recognition and strengthen professional identity of the PHW will be supported by the establishment of a PHI Registry.

(Please add Partner Countries/regions as appropriate)

Please explain how the planned activities and the expected results meet the needs of the identified target groups in the Partner Countries (limit 6.000 characters)

The needs of identified target groups (see section D1) were taken into account when planning project activities. Project results are expected to meet many of their needs while enhancing the PHW in Israel. SCHOOLS AND PROGRAMMES OF PUBLIC HEALTH: An analysis of field qualifications will be carried out to identify the competencies in PH needed by employers and communities at entry, competent and expert levels. The results of the analysis will be used to map the corresponding competencies profiles at Israeli HEIs, generating recommendations to harmonize programmes at all academic levels and with employer needs. This will allow HEIs to offer more relevant training to their students and streamline their educational trajectories, resulting in reduced repetition in coursework and shortening times to graduation. By better preparing students in the competencies needed by employers, graduates of programmes and schools of PH will be better able to find employment and roles in the PH system immediately after graduation. Moreover, by improving education and training, HEIs will better train the PH experts who will eventually join their own faculties. FACULTY: The establishment of a PH Leadership Academy offering training in methods of practical, problem-based learning (PBL) and leadership education will allow Faculty to stay relevant and enrich their courses and curricula as Israeli HEIs and move away from traditional lecture-based academic teaching styles. Trainings will help faculty identify and appropriately evaluate students’ learning outcomes (LOs). This will result in a cadre of faculty with the capacity to better meet student’s education and training needs for their employability. STUDENTS AND ALUMNI: Activities to match competencies to what is needed by employers and to increase the use of PBL and leadership training in coursework and curricula will increase PH students potential to meet PH challenges upon graduation and make them more attractive to potential employers. Activities to promote increased collaboration with employers and communities will provide internship and practical placement opportunities to students allowing them to gain new skills in a real world environment and demonstrate to future employers that they have the experience necessary to face PH challenges. Virtual and real-world career development platforms that allow employers to share opportunities with PH students and alumni will improve PH student and alumni access to internships and employment and promote career advancement. EMPLOYER ORGANISATIONS: Identification of the field qualifications needed by PH employers and communities and harmonization of competencies offered at Israeli HEIs along with increased content in leadership and practical training will ensure that graduates of Israeli schools and programmes of PH are ready to meet employer organisation needs. Activities to develop and promote PH training to other health professionals and sectors will equip health related employers with employees with an expanded set of skills that will make them better able to address PH challenges in the course of their regular jobs. PUBLIC HEALTH WORKFORCE (PHW): Promotion of Continuing Professional Development (CPD) and new academic degree programmes in PH that emphasize leadership and PBL training will empower professionals in the core PHW and wider health workforce to improve their skills and reinforce their identity within the greater PH professional community. This will not only help with career advancement as they better meet PH employer needs, but will also allow them to better serve population and PH needs within the course of their current work. MINORITY GROUPS: Activities to provide higher educational opportunities and specialized preparatory courses for marginal and peripheral populations will allow them to enter rewarding careers in PH and other health professional tragectories. Such students often remain in or return to their home communities and will be equipped with the competencies to serve and improve the health of their own community. Activities to define and meet the qualification and competencies needs of minority groups and to place students in practical placements in these communities will help improve the health and health standards of underserved populations, which currently lag behind other parts of Israeli society in important health indicators. Moreover, PH students will gain cross-cultural understanding, which will allow them to better serve minority groups upon graduation. PUBLIC HEALTH SYSTEM GOVERNANCE STRUCTURES: Outreach and dissemination activities will engage with PH system governance structures informing them of the PHW needs and giving them access to an online health system development platform. This will allow them to better plan for the PH system, and resource allocation needs in order to optimize the impact of the PHW on the health of the population. Selected key deliverables will be translated into local languages (Hebrew and Arabic).

(Please add Partner Countries as appropriate)

How will the project and its results contribute effectively to the objectives of the action Capacity-Building in the Field of Higher Education in each targeted Partner Country? (limit 6.000 characters)

As stated in ERASMUS+ Key Action 2, Capacity-building projects in the field of higher education support the modernisation, accessibility and internationalisation of higher education in Partner Countries. The projects aim to encourage cooperation between the EU and Partner Countries and support eligible Partner Countries in addressing challenges in the management and governance of their HEIs. This includes improving the quality of higher education, developing new and innovative education programmes, modernising higher education systems through reform policies as well as fostering cooperation across different regions of the world through joint initiatives. More specifically, this Joint Project seeks to support Israel in National Priority 3: strengthening of relations between HEIs and the wider economic and social environment, targeting university-enterprise cooperation, entrepreneurship and employability of graduates through voluntary convergence with EU developments in higher education and PHW professionalization. By doing so, the project will improve the quality of higher education in Israel and enhance its relevance for the labour market and society. In order for Israeli HEIs to meet the capacity needs of PH employers and local communities, they must be able to prepare PH students with appropriately targeted and experience-based education and training that will give them the versatility and skills to meet the dynamic and changing challenges inherent in addressing the health of the entirety of the population – including harder to reach minority groups with special needs. To do so the proposal sets out to ENHANCE THE PUBLIC HEALTH WORKFORCE (PHW) IN ISRAEL THROUGH SHARING EUROPEAN EDUCATIONAL EXPERIENCE, INCLUDING: HARMONIZATION, EMPLOYABILITY, LEADERSHIP and OUTREACH to be accomplished via addressing the AIMS and OBJECTIVES elaborated in section D.2.1: 1. Detailed analysis of field qualifications content to understand different professional roles in the Israeli PH system; 2. Mapping of the corresponding profiles of the Israeli schools and programmes of PH to guide harmonization between PH education and practice; 3. Introduction of a dynamic online interface to enable PH education/training – practice/workforce collaboration, supporting employability and continuing professional development in the Israeli PH system; 4. Building leadership capacity via cutting edge training in the Israeli PH schools and programmes, including peer-to-peer and train the trainers offerings; and 5. Stakeholder engagement to secure key outreach (community, inter-professional, cross-sectoral…) needed to sustain the proposed solutions. The Israeli HEIs and the broader Israeli PH workforce will be able to benefit from voluntary incorporation of European tools, best practices and methodologies that touch on several of the specific types of activities listed for Capacity Building Joint Projects in Higher Education, including, but not limited to: • learning and teaching methodologies and pedagogical approaches; • new forms of practical training schemes and study of real-life cases in business and industry (i.e, PH employers and local communities); • university-enterprise cooperation; • new forms of learning and providing education and training; • guidance, counselling and coaching methods and tools; and • tools and methods for professionalization and professional development. Realizing the collaboration with HEIs in Europe will allow PH professionals and the broader PHW in Israel to gain the competencies, skills, and know-how (i.e. capacity) needed to meet the difficult and dynamic PH challenges that they, their employers, and the community will face across the span of their careers.

(Please add Partner Countries as appropriate)

How do the project's objectives fit in with the modernisation and internationalisation agenda of the targeted higher education institutions in the Partner Countries and with the development strategy for higher education in each Partner Country involved in the project? (limit 6.000 characters)

Since the 1970s, Israeli Sick Funds have come to recognize the economic and societal value of prevention and health promotion to reduce the burden of cardiovascular, cancer and trauma related conditions. By emphasizing PH within the health system and relying less on hospitalization and more on community care with active screening programmes and health promotion, Israel has drastically reduced mortality rates from these groups of diseases. The PH community has played a crucial role in this progress, with a growing emphasis on health promotion, multi-disciplinarily in professions, multi-sectoral partnerships and developing a skilled workforce. Despite progress in improved longevity and reduced mortality from infectious and non-infectious diseases, and improving economic status, Israel faces important health effects challenges of poverty (20% of the total population and 30% of children), inequities between ethnic and religious groups including the Ethiopian refugee, Arab, Bedouin and Orthodox (Haredi) Jewish populations as compared to the middle and upper economic Jewish population that is concentrated in the central urban centers. In order to meet the complexity of the remaining and ever changing PH challenges, the basic philosophy of PH education in Israel must be modernised–to shift from its over-emphasis on academic epidemiology to pro-active advocacy of population health enhancement. The student population and their teachers, need to be oriented to health problem identification, and working with many partners to seek solutions to the current and future challenges of PH in a growing population of elderly people to enhance “healthy aging” and self reliance. The skills required of the PHW population are changing and the HEIs in Israel need to make the changes to modernise their programmes. The project objective is to enhance the PHW in Israel through sharing European educational experience, including: harmonization, employability, leadership and outreach. This proposal comes at a critical time of evaluation and national self-reflection on programmes of PH education as illuminated in the reports of the Israel Council for Higher Education (CHE) Committee for the Evaluation of Public Health and Health System Management Study Programmes (See section D.1). The reports provided overall country-wide recommendations for programmes of PH as well as specific feedback for individual HEIs. Moreover, Israeli HEIs are currently seeking to make PH education and training available to a broader range of students with development of a programme for a Bachelor in PH, preparatory courses for minorities, and moves to formally train other health professionals in PH through continued professional development. Meanwhile, the past decade has seen Europe HEIs make substantial strides to modernise PH education and training and broaden its reach. The broader PH community and SPHs in Europe have also developed critical tools to professionalise and modernise the diverse European PHW, ensuring it meets the needs and standards expected of employers and the population. Putting together a consortium of European HEIs and ASPHER with the Israeli HEIs in PH and the IAPHP at this juncture, offers a unique opportunity to meet the recognized Israeli PH system, education and training needs at both the national and programme levels in Israel. The proposal offers a strategic plan for enhancing and developing the PHW to meet the needs of employers and Israeli communities based on international standards and taking advantage of the best practices in place in Europe.

(Please add Partner Countries/partners as appropriate)

Please explain how the proposal will pay attention to the issues of inclusion, diversity and socio-economically disadvantaged participants and/or organisations in the Partner Countries. (limit 2.000 characters)

It can be argued that, the core value of PH is service to ensure the health of the population. Implicit in this is concern for the health of all populations, including minorities as is evidenced by PH’s efforts to reduce health inequities. This project in particular, in seeking to engage with the greater Israeli community, recognizes the need for participation from minority and socioeconomically disadvantaged communities within the country, including Arabs, Bedouins, Othodox (Haredi) Jewish, and Ethiopian immigrants. Indeed, the Israeli Partner Schools already service and recruit students from these communities. However, in recognizing the special needs of these often underserved communities, this proposal seeks to strengthen and broaden these connections. The proposal will take the local minority communities into account at each step of the project by: including minority organisations in its outreach and determination of field qualifications; building the findings of these assessments into the recommendations for harmonization and development of the PH degree and continuing education programmes; seeking to place students in practicum, internships and employment in minority communities and thereby build up the PHW servicing the communities; encouraging exchange of knowledge and student recruitment to educate future PH leaders from within minority groups; and sustain contacts within the minority community organisations to continually build and react to their changing needs. Selected key deliverables will be translated into local languages (Hebrew and Arabic).

# D.3 Innovative character

Demonstrate why the proposal is innovative.

If it is complementary to previous/existing funded projects nationally or internationally please explain how the new proposal build on it/them and demonstrate its added value and why it is not a simple continuation thereof. (limit 2.000 characters)

The proposal brings together a consortium of schools of PH in Europe representing historically diverse PH systems from Eastern, Nordic, Continental, and non-Continental (the British Isles) Regional contexts. Moreover, the European HEIs taking part in the proposal represent partners that have been at the forefront of the development of programmes to reach students at all levels of PH education – starting from bachelor up to continuing professional development and across different health professions. This rich diversity of collective experience of the European HEIs offers Israeli schools the opportunity to benefit from a variety of solutions in order to find the best fit to transform their education and training approaches and harmonize their educational system in order to maximize the employability of their graduates. Moreover, the proposal takes advantage of state-of-the-art tools that have been developed over the past decade in Europe to offer creative solutions to strengthen and professionalise the PHW – putting them together for use at a critical moment of national self-reflection on the direction of PH education in Israel. The ASPHER/WHO Europe Road Map to Professionalizing the PHW (RMPHW) will act as an overarching guide to achieve the project aims, while specific European initiatives will guide each Prepratory and Development Work Package – WP2: Field Qualifications Analysis - WHO-ASPHER Competency Framework for the PHW in the European Region (CFPHW); WP3: Education and Workforce Harmonization - ASPHER’s European Core Competences List for the PH Professional (ECCLPHP); WP4: Workforce Adaptation and Employability - ASPHER’s European Public Health Reference Framework (EPHRF) ; WP5: Building Leadership Capacity - Leaders for European Public Health (LEPHIE); WP6: Stakeholder Engagement - "This is Public Health" campaign. (See section D.2.1 for links to the tool documentation) By synergizing the tools, best practices and experience in one concerted action across a comprehensive network of HEIs of PH in Israel, the proposal will be able to work within the national context to move the Israeli PHW and PH professionals to higher levels of excellence.

If the proposal builds on any previous or existing EU-funded/non-EU funded national or international activities/projects in this field, please fill the following table for each of these projects.

☐

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2019-2022 |  | Programme or initiative | A Three-Year Government Plan to Enhance Access to Higher Education for Negev Bedouin |
| Funded by | The Israeli Council for Higher Education |  |  |  |
| Title of the project | Gateway to the Academy |  |  |  |
| Coordinating organisation | The Israeli Council for Higher Education |  |  |  |
| Partner Countries /institutions targeted by this project | AAC, BGU, Sapir College, Ahva College, Open University |  |  |  |
| Website | NA |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) In June 2018, Israel’s Council for Higher Education (CHE) announced tender recipients for implementation of an unprecedented NIS 130 million three-year plan to promote higher education among Negev Bedouins in Israel. Five academic institutions have been selected to run a special preparatory program for more than 400 Bedouin students per year over the next two years (targets for the third year have not yet been set): Sapir College (where the model was developed), Ben Gurion University, Ahva College, Open University and the Ashkelon Academic College. Negev Bedouins are a population of approximately 240,000 living in Israel’s southern desert region who have the lowest rates of participation in higher education and the economy compared to both Jewish and Arab citizens, and suffer from the lowest socio-economic status in Israel, with poverty rates exceeding 70%. Bedouins comprise today only slightly more than 1% of first-degree students in Israel despite accounting for 4% of the 18-22 age group, a quarter of their proportional representation. The CHE Plan is a scaled up version the "Gateway to the Academy" model developed and piloted at Sapir College in the Negev to overcome the distinct barriers to higher education that Negev Bedouin face. The model was developed after evaluation of the CHE’s 2011 national 6-year plan to enhance access to higher education for Arab society in Israel overall showed that Bedouins require additional, specialized programs to address significant and persistent gaps beyond those affecting Arab society in general. The expanded Plan aims for a 75% increase in first-year Bedouin students—from 850 to 1,500 students over its three year span. This means that by 2020, a total of 4,500 Bedouins will be enrolled in first degree programs versus 2,600 in 2016. Through holistic solutions to the barriers affecting the Bedouin community, "Gateway to the Academy" aims not only to increase the number of Bedouin students in higher education, but also to the quality of their educational attainment and the number of students pursuing more market-relevant degrees. (b) There are no conflicts of ownership/copyright. |  |  |  |  |

| Reference number |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2019-current |  | Programme or initiative |  |
| Funded by | Mandel Foundation |  |  |  |
| Title of the project | Public Health Social Leadership |  |  |  |
| Coordinating organisation | BGU |  |  |  |
| Partner Countries /institutions targeted by this project | Faculty of Health Sciences and Faculty of Management, BGU and Mandel Foundation |  |  |  |
| Website | http://in.bgu.ac.il/en/fom/SociaLeadership/Pages/default.aspx |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) A joint project between BGU and Mandel foundation focused on research and models related to public health leadership. (b) There are no conflicts of ownership/copyright. |  |  |  |  |

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2018-2020 |  | Programme or initiative | MU-AAC national public health staff exchange |
| Funded by | The Israeli Council for Higher Education |  |  |  |
| Title of the project | The Program of Developing Internationalization in Higher Education Institutions in Israel |  |  |  |
| Coordinating organisation | The Israeli Council for Higher Education |  |  |  |
| Partner Countries /institutions targeted by this project | AAC/UM |  |  |  |
| Website | NA |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) The AAC-Maastricht University SPH faculty exchange program for 2018-19 is funded by MALAG (CHE). Its purpose is to foster international exchange of experience and ideas related to improving undergraduate training in public health and enhancing its academic and career development potential, The first visit was of Maastricht faculty with ASPHER staff in November 2018. Meeting with students and faculty discussed Maastricht's experience with Problem-Based Learning. AAC PH faculty are interested in adopting this approach especially in developing "specialization streams" in the third year of studies for the next academic year. AAC faculty members visited Maastricht in September 2019 with second visits planned from both sides in 2020. (b) There are no conflicts of ownership/copyright. |  |  |  |  |

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2019-2020 |  | Programme or initiative | TIPH-Europe Campaign |
| Funded by | ASPHER |  |  |  |
| Title of the project | Making Public Health the Students’ Choice: Israel’s “This is Public Health” Campaign |  |  |  |
| Coordinating organisation | Hebrew University of Jerusalem (HUJI) |  |  |  |
| Partner Countries /institutions targeted by this project | Israel |  |  |  |
| Website | http://www.aspher.org/this-is-public-health-tiph.html |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) This project aims to increase the numbers of students applying to study in a public health program - mainly MPH, from all bachelor level professions, and increase interest in Public Health residency for medical doctors. A secondary aim is to strengthen current collaborations between all schools of public health in Israel and the Palestinian Authority, and enhance the public health workforce in the country/region. A media campaign will be designed and advertised on web-based platforms, including mainly social media (Facebook and Instagram). This is the most suitable strategy as Israel has one of the world’s highest levels of smartphone ownership (nearly 100% among young adults) and social media use (overall 76%; 86% among 18-34 year old). The three leading social platforms are Instagram, Facebook and Twitter. Short video clips will be produced focusing on: PH in Society, PH Professionals, PH Victories. (b) There are no conflicts of ownership/copyright. |  |  |  |  |

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2018-2019 |  | Programme or initiative | WHO Europe Public Health Services Programme |
| Funded by | WHO Europe |  |  |  |
| Title of the project | ASPHER/WHO Europe Road Map to Professionalizing the Public Health Workforce (RMPHW) |  |  |  |
| Coordinating organisation | ASPHER |  |  |  |
| Partner Countries /institutions targeted by this project | WHO Europe Region member states |  |  |  |
| Website | https://www.aspher.org/download/245/professionalizationroadmap-finaldraft_23-05-19.pdf |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) The RMPHW supports the governments of each country in the WHO European Region, in developing policies related to PWH enumeration, developing, planning and forecasting. It also assists in strengthening professional identity of the current PHW, and aligning PH services and operations with PHW development and professionalization. The project addressed the need to define the PHW, and to shape the PH profession. (b) ASPHER is a co-author and co-owner of the tool. |  |  |  |  |

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2018-2019 |  | Programme or initiative | WHO Europe Public Health Services Programme |
| Funded by | WHO Europe |  |  |  |
| Title of the project | The WHO-ASPHER Competency Framework for the Public Health Workforce in the European Region |  |  |  |
| Coordinating organisation | ASPHER |  |  |  |
| Partner Countries /institutions targeted by this project | WHO Europe member states |  |  |  |
| Website | https://www.aspher.org/download/365/05-11-19_phcomp-draft10.pdf |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) The project designed and developed an integrated core competencies framework/model for the public health workforce. The developed tool enables an ongoing standardized and consistent assessment and development of public health knowledge and skills at individual, service, organizational and national/regional and country level, thus supporting public health professionalization and credentialing. (b) ASPHER is a co-author and co-owner of the tool. |  |  |  |  |

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2012-2013 |  | Programme or initiative | EU Lifelong Learning Programme |
| Funded by | EU Lifelong Learning Programme – Accompanying Measures |  |  |  |
| Title of the project | Toward Equity in the Quality of European Public Health Education: Reults, discussion and recommendations from the Public health Education Reform For Equity in Quality of Training” (PERFEQT) Project |  |  |  |
| Coordinating organisation | ASPHER |  |  |  |
| Partner Countries /institutions targeted by this project | ASPHER, APHEA, University of Torino, Berlin School of Public Health – Charite, Lithuanian University of Health Sciences |  |  |  |
| Website | NA |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) In February 2012 a small group of partners from the ASPHER network and the Agency for Public Health Education Accreditation (APHEA) submitted an application for funds to the European Commission’s Lifelong Learning Programme which would use the newly established accreditation agency criteria as a benchmark to assess the level of development toward the criteria across the region. This would also provide opportunity to showcase and test some of the new accreditation criteria. The application was successful and the project formally started in September 2012. (b) ASPHER was leader of the project and there are no conflicts of ownership/copyright. |  |  |  |  |

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2010-2013 |  | Programme or initiative | EU Lifelong Learning Programme |
| Funded by | EU Lifelong Learning Programme – Curriculum Development |  |  |  |
| Title of the project | Leaders for European Public Health (LEPHIE) |  |  |  |
| Coordinating organisation | Maastricht University |  |  |  |
| Partner Countries /institutions targeted by this project | Maastricht University, Sheffield Hallam University, Lithuanian University of Health Sciences, Medical University of Graz, ASPHER |  |  |  |
| Website | NA |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) The goal of the Leaders for European Public Health (LEPHIE) project was to develop understanding of the vital need to develop effective leadership at every level of European health systems. With this in mind the project partners have spent over three years developing and delivering a Leadership course for Public Health professionals using problem-based, blended-learning methods that utilise cutting edge online technologies. The course has been piloted in the UK, Lithuania, the Netherlands and Austria. The development of the programme has also been accompanied by a rigorous evaluation study on the effectiveness of the learning methods and the leadership content taught within a range of diverse educational and public health contexts. (b) ASPHER and UM are co-creators and co-owners of the LEPHIE Curriculum. |  |  |  |  |

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2006 - continuing |  | Programme or initiative | ASPHER’s Public Health Core Competences Programme |
| Funded by | ASPHER |  |  |  |
| Title of the project | European Public Health Reference Framework (EPHRF), incl. ASPHER’s Public Health Core Comptences List for the Public Health Professional (ECCLPHP) |  |  |  |
| Coordinating organisation | ASPHER |  |  |  |
| Partner Countries /institutions targeted by this project | ASPHER member schools and programmes |  |  |  |
| Website | http://aspher.org/european-public-health-reference-framework.html |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) Started in 2006, ASPHER’s European Programme on Public Health Core Competencies has involved more than one hundred European PH teachers, scientists and practitioners in the development of lists of competencies for public health professionals. In the first round, all ASPHER member schools were invited to contribute to six workgroups, which lead to the first list of competencies. Thereafter, European ministries of health were invited to participate, among other things in a conference at Aarhus University in April 2008, where, in the end, 27 European countries were represented, by decision makers and by teachers and scientists. At the same time the first two in a series of national practitioner-teacher workshops were performed, in Slovenia and Scotland, respectively. The 5th Edition of the ECCLPHP was published in 2018. (b) ASPHER is the author and the owner of the Public Health Core Competences Programme. |  |  |  |  |

| Reference number | NA |  |  |  |
| --- | --- | --- | --- | --- |
| Project dates (year started and completed) | 2000-2005 |  | Programme or initiative | OSI Public Health Program |
| Funded by | Open Society Institute Public Health Program |  |  |  |
| Title of the project | Lessons Learned from “Quality Development of Public Health Teaching Programmes in Cenral and Eastern Europe” |  |  |  |
| Coordinating organisation | ASPHER |  |  |  |
| Partner Countries /institutions targeted by this project | Schools and programmes of PH in CEE. |  |  |  |
| Website | https://www.aspher.org/download/49/aspher_book_final_04-04-08.pdf |  |  |  |
| Password / login if necessary for website |  |  |  |  |
| (a)Summarise the project outcomes (b) Explain how ownership/copyright issues are to be dealt with (limit 2000 characters). |  |  |  |  |
| (a) The project report documents experience and lessons learned from the thirteen-country project put forward by ASPHER and implemented by its members through twinning projects, on-site consultations, peer reviews, and faculty training and development. It includes information from parallel projects in other CEE and Central Asia countries funded by OSI in consultation with faculty from ASPHER member schools. It describes both new and sustainable institutions that continue to function, and it explains why other projects were less successful. Curricula and programme descriptions of individual projects are included. (b) ASPHER is co-author and co-owner of the the document. |  |  |  |  |

# D.4 European added value

Why is there a need for cooperation with the Programme Countries in this area of activity and a funding via the Erasmus+ Programme? Why can the intended results not be achieved through national, regional or local funding in the Partner Countries? (limit 2.000 characters)

The field of PH, its training and education has historically been disjointed across the European Region with different approaches from the East and the West as well as the North and the South. As a result, the PH labour market has been complicated with an absence of international standards and mutual recognition between countries. At the same time, the diversity itself reulted in a unique richness of different solutions within Europe to tackle the problems of PH training and professionalization of the PHW. The European Partners represent a set of HEIs originating from several different European Regional contexts: East, West, Scandinavia, and British Isles. Each European HEI offers its own set of solutions and innovations to meet PHW education and training challenges from which Israeli HEIs wish to benefit and each leads on different aspects of the project based on their particular strengths. Additionally, the tools and training methods that have been developed in Europe offer an adaptable way forward to improve the employability and professionalisation of the PHW, which may be applied to the local context in Israel. This proposal offers an opportunity for Israel to make use of these tools while at the same time engaging in an exchange of experience and best practices from four European HEIs from four national contexts with distinct PH systems. This interchange of capabilities would not be possible with involvement of only one European HEI, nor from within the Israeli national or local context. In order to modernise, Israel and its PH HEIs must incorporate and learn from the experience of best practices already applied across Europe.

# D.5 Cross-regional cooperation

If your proposal is cross-regional, demonstrate the need for this cooperation between institutions from different regions. Please also explain the added value of this cross-regional cooperation for the targeted Partner Country institutions. (limit 2.000 characters)

The proposal is not cross-regional as it is a national project with only one partner country. However, selected associated partners representing international school networks will be involved, including the Association of Schools and Programs of Public Health (ASPPH) in North America and the Association of Schools of Public Health in Africa (ASPHA) to ensure the global relevance of solutions.

# PART E – Quality of the Project Design and Implementation

# E.1 Project activities and methodology

Please provide a detailed description of the activities and the working methodology to be used for achieving the objectives (including major milestones, measurable indicators, etc.). (limit 6.000 characters)

The overall aim for the proposal is ENHANCEMENT OF THE PUBLIC HEALTH WORKFORCE IN ISRAEL THROUGH SHARING EUROPEAN EDUCATIONAL EXPERIENCE, INCLUDING: HARMONIZATION, EMPLOYABILITY, LEADERSHIP and OUTREACH with 5 specific objectives (SOs): 1. DETAILED ANALYSIS OF FIELD QUALIFICATIONS CONTENT TO UNDERSTAND DIFFERENT PROFESSIONAL ROLES IN THE ISRAELI PUBLIC HEALTH SYSTEM. 2. MAPPING OF THE COMPETENCY PROFILES OF THE ISRAELI SCHOOLS AND PROGRAMMES OF PUBLIC HEALTH TO GUIDE HARMONIZATION BETWEEN PUBLIC HEALTH EDUCATION AND PRACTICE. 3. INTRODUCTION OF A DYNAMIC ONLINE INTERFACE TO ENABLE PUBLIC HEALTH EDUCATION/TRAINING – PRACTICE/WORKFORCE COLLABORATION, SUPPORTING EMPLOYABILITY AND CONTINUING PROFESSIONAL DEVELOPMENT IN THE ISRAELI PUBLIC HEALTH SYSTEM. 4. BUILDING LEADERSHIP CAPACITY VIA CUTTING EDGE TRAINING IN THE ISRAELI PUBLIC HEALTH SCHOOLS AND PROGRAMMES, INCLUDING PEER-TO-PEER AND TRAIN THE TRAINERS OFFERINGS. 5. STAKEHOLDER ENGAGEMENT TO SECURE KEY OUTREACH (COMMUNITY, INTER-PROFESSIONAL, CROSS-SECTORAL…) NEEDED TO SUSTAIN THE PROPOSED SOLUTIONS. The project consortium is made up of ASPHER and 4 EU PH HEIs representing distinct regions of Europe and with a variety of expertise on education and PHW development. The Israeli Partners include the IAPHP and 4 PH HEIs servicing different regions and student populations in Israel (see D3.1 and F.3). Each of the 5 core WPs is co-led by one Israeli and one EU Partner ensuring a balance of responsibilities and ownership and playing to the roles, strengths and experiences of each Partner (see F.2). The core content of the project is divided into 5 core WPs – 2 preparatory (WP2 & WP3) and 3 development (WP4-6); respectively addressing the 5 SOs listed above. Management (WP1), Dissemination (WP7) and Quality Plan and Evaluation (WP8) support the project. Each core WP corresponds to a single SO. The European WP co-leader supports the context of the WP agenda, sharing experience, European solutions, tools, best practices, etc. The Israeli WP co-leader operationalises input from the European Partner into the Israeli PH system context and bears primary responsibility for the development and implementation work. The ASPHER/WHO Europe Road Map to Professionalizing the PHW (RMPHW) supports countries and PH professionals in taking action to professionalize the PHW, describing a variety of measures that countries can take, and identifying considerations related to the implementation. It is used as an overarching guide for all proposal activities. Each of the 5 core WPs is supported by a specific European tool or model that offers actionable solutions on PHW development and PH systems to be adapted to the Israeli context. WP2 (SO1): WHO-ASPHER Competency Framework for the PHW in the European Region (CFPHW): The Framework enables standardization and consistent definition of the skills required of PH professionals. As the first preparatory WP it will deliver a report from the survey of field qualifications. The measurable indicator is the extent to which the field qualification analysis comprehensively reflects the entirety of the Israeli PH system and individual function areas as defined by Essential Public Health Operations (EPHOs) (see also section E.4). WP3 (SO2): ASPHER’s European Core Competences List for the PH Professional (ECCLPHP): The List complements the definitions from the point of view of competencies and core-curricula; based on the list, the nature and activities of PH can be derived, aggregated and combined to the level of definition of the discipline. This second preparatory WP will produce a report and recommendations for harmonization of the offers at all academic levels from the mapping of the competency profiles of the Israeli HEIs of PH and in response to the employer and community needs (WP2). The measurable indicator is the extent to which the competency analysis comprehensively reflects the entirety of the PH offerings of HEI in Israel and the number of Israeli HEIs receptive to implementing recommendations (see also section E.4). WP4 (SO3): ASPHER’s European PH Reference Framework (EPHRF): The EPHRF constitutes a central and comprehensive source of information to enable interactions for PHW planning; mapping PH education and training programmes; mapping job opportunities; and individual career guidance. Building on the findings from WP1&2, the PHI PHRF tool will be developed. It will be supported by the PHI Practical Placement Scheme to place students in practical research and PH campaigns each semester in order to gain real world PH experience and skills. An annual PHI Career Fair will be organized to assist students, alumni, and PH professionals and others with job placement and career advancement opportunities. The measurable indicator will be the development of the PHI PHRF online tool interface enabling relevant interactions between target groups and successful implementation of the practical placement scheme and career fair activities. This will be elaborated by the number of PHI PHRF users from the project target groups and outcomes impacting on employability (see also section E.4). WP5 (SO4): Leaders for European Public Health (LEPHIE): the programme, resulting from a previous European collaborative effort, developed a leadership course for PH professionals using PBL and blended-learning methods utilizing. LEPHIE methodology will be used for the training of trainers for the PHI Leadership Academy. The measureable indicators will be the number of successful peer-to-peer training sessions and the faculty trained as well as uptake of new leadership and PBL components in PH curricula. WP6 (SO5): This is Public Health (TIPH) Europe Campaign: The campaign increases awareness of PH roles. An Israeli TIPH campaign is currently underway and will be augmented by the I am Public Health (IAMPH) campaign in the current proposal to raise awareness of the roles played by individual members of the PHW. IAMPH will encourage professionals with a role in PH officially register as PH Professionals strengthening their PH identity. The measurable indicators are the number of parties engaged in the campaign and the number of individuals registered in the PHI Register. A further indicator will be the number of students enrolling in PH courses from other health and related professional backgrounds, other sectors and minorities.

Please demonstrate that the activities and the methodology mentioned are the most appropriate to achieve the envisaged results and that they are feasible. (limit 3.000 characters)

The methodology presented in the above section is based on validated European tools, models and solutions for PHW development and professionalization resulted from ASPHER collaborative efforts with WHO Europe, and European SPHs. Leading experts and stakeholders were consulted in the development of the materials, which underwent extensive peer review. Due to the diversity of PH systems across European countries – based on the varying histories and cultures of each country – the European solutions have by necessity been designed to be adaptable to multiple country contexts. This makes them suitable for adaptation to the Israeli context. The strong consortium of European Partners have been involved with development and implementation of many of the listed tools and models and therefore can offer experience and expertise on their methodologies to the Israeli Partners. The Israeli Partners have expressed their receptivity to use of the tools and methods to be adapted to their local and country contexts making the use of these methods feasible for the project to enhance the PHW in Israel through sharing European educational experience, including: HARMONIZATION, EMPLOYABILITY, LEADERSHIP and OUTREACH. For detailed activities per each Partner Organization, please see section F.3.

What concrete, tangible results are expected to be achieved at the end of the project's activities in each of the targeted Partner Countries? (limit 6.000 characters)

By the end of the project activities, the following tangible results should be achieved: WP2: A preparatory analysis of employer and community expectations of PH field qualifications should be complete. This will include a survey instrument used to solicit employer and community organisation feedback and a full report from the survey. It will result in a final PHI Qualification Map of entry, competent and expert levels of PH competencies to be used in subsequent WPs (see also section E.6 WP2). WP3: A preparatory analysis of HEI offerings in PH in Israel will be completed. This will include a survey instrument to map the competency profiles of the Israeli schools and programmes of PH and a full report from the survey. It will result in a final PHI SPHs Competency Map. Recommendations will be made to harmonise programmes of PH, informed by the PHI Qualification Map from WP2 (see also section E.6 WP3). WP4: The PHI PHRF tool will be built providing an online interface for students, employers and PH system governance structures to use for practical placement and employment opportunities, career guidance, and PHW planning and development. Further a PHI Practical Placement Scheme and annual PHI Career Fair will be developed and implemented to contribute to employability of project target groups (see also section E.6 WP4). WP5: The PHI Leadership Academy will be developed and piloted. It will be supported by a train-the-trainer manual with leadership teaching and learning modalities. The piloting of peer train the trainer sessions will generate a cadre of trainers ready to introduce and sustain leadership practices and problem based learning to a larger audience of PH faculty and educators across the wider Israeli PH community (see also section E.6 WP5). WP6: The on-going “This is PH” campaign will be reinforced with an IAMPH campaign and promoted widely in Hebrew and Arabic languages with special happenings at IAPHP conferences. It will result in better understanding and recognition of what makes up PH and who is part of the PHW. It will be targeted to related health professionals, other stakeholders, and the wider public to engage them further in PH. A PHI Register will be developed resulting in a scheme for the PHW to gain official recognition as PH professionals (see also section E.6 WP6). WP7: Results will be disseminated widely at ASPHER Deans’ & Directors’ Retreat 2021-2023; IAPHP annual conference 2021-2023; the European Public Health Conference 2023; through ASPHER’s website and social media channels; and in a special edition of ASPHER’s Journal, Public Health Reviews which is freely available online to a wide readership (see also section E.6 WP7)

(Please add Partner Countries as appropriate)

For all types of activities (curriculum development, modernisation of governance, management and functioning of HEIs; strengthening of relations between HEIs and the wider economic and social environment), for each Partner Country institution please provide information in Part F.2 Organisation and Activities.

# E.2 Quality control and monitoring

Please explain what mechanisms will be put in place for ensuring the quality of the project and how the evaluation will be carried out. If an external evaluation is foreseen, provide information on the purpose and expected outcomes of this evaluation. Please define the specific quality measures established, as well as the benchmarks and indicators foreseen to verify the outcome of the action. Make sure that the information in this section is consistent with the project Logical Framework Matrix. (limit 3.000 characters)

Quality control and monitoring (WP8) led by AAC (P1) will focus on timely action on activities and deliverables for each of the SOs (see E.1). Evaluations will be based on the activity reports and deliverables of each WP. The Evaluation Committee (EC) will be established at the 1st consortium meeting in M2 of Year 1. It will be made up of 4 elected representatives from among the project partners: 2 European, 2 Israeli; plus the External Evaluator (EE). There will be two co-Chairs of the 5 member EC: the EE will be ex officio co-Chair and a 2nd co-Chair will be selected from among the 4 internal EC Members. External evaluation will be subcontracted to an Israeli-based entity familiar with the country context and PH landscape in order to ensure an impartial review. Serving a critical role for a project of this breadth, the EE will be a driver in the project evaluation process, present at all EC meetings, both annual and interim. The EE will be present at the kick-off consortium meeting to give advice at the start of the project. There will be 4 in person EC meetings. Three annual in person meetings will result in external evaluation reports from the EE, to act as progress benchmarks. One interim mid-year in person meeting will take place in year 2, at the project midpoint and a critical period of project activity. There will be 6 interim meetings by phone. Minutes of the 7 interim meetings will serve as internal evaluation reports and will be made available to all Partners and the EE. EC meeting schedule: YEAR 1 M2: (in person) EC election and selection of internal co-Chair 1st semester: Interim phone meeting 2nd semester: Interim phone meeting YEAR 2 M2: (in person) 1st annual meeting to result in Year 1 External Evaluation Report. 1st semester: Interim phone meeting M8: Interim in person meeting 2nd semester: Interim phone meeting YEAR 3 M3: 2nd annual meeting to result in Year 2 External Evaluation Report. 1st semester: Interim phone meeting 2nd semester: Interim phone meeting M10: 3rd annual meeting to result in Final External Evaluation Report. The project work will be critically reviewed in terms of actionability and sustainability with consultation of multiple stakeholders impacted by the project activities. The EC will summarise successes and pitfalls towards a sustainable structure. The criteria will focus on the envisaged main outcomes of the proposal and will be based on the process, output and outcome indicators of the SOs. The identified successes and pitfalls towards a sustainable structure will be the basis for the development of strategic recommendations. The EE will provide strategic recommendations for the project e.g. on how to increase its impact with special attention paid to reaching stakeholders such as PH employers. It will guide the project in achieving its major expected outcomes to enhance the PHW in Israel through harmonization, employability, leadership and outreach.

# E.3 Budget and cost effectiveness

Please describe the strategy adopted to ensure that the proposed results and objectives will be achieved in the most economical way, and on time. Explain the principles of budget allocation amongst partners. Indicate the arrangements adopted for financial management. What sources of co-funding will be used? (limit 3.000 characters)

ASPHER oversees finances ensuring timely and economical results and deliverables with 5 regular, in-person management meetings with Partners covering progress and use of finances; and 2 annual Progress Reports with all Partner financial reporting and a final Project Financial Report. Thus WP progress/finances are monitored annually. An Evaluation Committee (EC) meets regularly to review progress and give advice (see E.2). Strategies for economical results: 1. Management meetings at each EU Partner location (BE/IE/NL/PL/SE) with representatives from all Partners. The EU Partners represent a spectrum of countries/regions with a variety of PH experiences, practices and solutions; time is allotted during meetings for site visits and local activities so that Israeli HEIs benefit from 1st-hand encounters with EU HEIs and PHW. 2. WP activity meetings are held in Israel with EU Partners traveling to Israel allowing for high attendance at activities by the Israeli HEIs and maximizing impact. Trainings in WP5 bring all Partners together at the 5 Israeli Partner sites ensuring understanding of local specificities for the project duration. 3. Of the 4 in-person EC meetings, 2 will coincide with consortium management meetings reducing travel costs. 6 Interim EC meetings will take place over the phone. 4. Poland has an able IT workforce with services at competitive rates. Polish Partner, JU will oversee subcontracting to build the IT infrastructure of the PHRF Platform. 5. The Leadership Academy builds on the BGU School of Management Social Leadership Programme, extending it to PH and benefiting from support of the Mandel Foundation. 6. ASPHER’s Journal, Public Health Reviews (PHRS) will publish results. PHRS is open access and was first published in Israel retaining a readership in country. Delegates will be sent to the European Public Health Conf., and ASPHER’s Deans & Directors Retreat to disseminate results internationally and to the IAPHP Conf. to disseminate in Israel. The budget allocates the bulk of monies (~ 60%) to Israeli Partners (primary project beneficiaries). EU partners receive smaller budgets for supporting roles and travel. Partners are assigned co-leads in at least one WP to ensure project ownership. Co-leads of activities in WP2 & 3 scheduled for year 1 only, remain engaged with lead/support roles in later WPs. ASPHER as the managing organization, and co-lead of several WPs receives a larger allocation. Partners contribute 10% co-funding for added costs (e.g., translation to Hebrew and Arabic, conference registrations, other relevant staff cost). The budget is balanced for type of WP: ~ 2/3 to development and management, ~ 1/3 to preparation, quality plan, and dissemination/exploitation. Cost Breakdown: staff 38%, equipment 16%, subcontracting <10%, activities, travel & stay ~35%

If your project involves any "exceptional costs" related to travel, please justify them here. (limit 2.000 characters)

NA

Please justify the equipment costs for each Partner Country Institution:

- why the Partner Country institutions need them for the implementation of the project;

- their relations with the content to be developed and the specific activities to be implemented) and

- the estimated timeframe for their purchase as well as the estimated place where they will be located (limit 3.000 characters)

Three laptops will be purchased at the start of the project for each of the Israeli Partners and will be located at each Partner’s campus. The laptops will be set up with the project’s IT environment required for all partners to support their roles and communicate and share documents and results. These will be available for use as needed for the Partners to complete activities, and to write up and submit reports. Being portable, the laptops may be used when traveling for fieldwork, to management and activity meetings, and to conferences. Four information station/portals will be purchased for each Israeli Partner to host the PHI EPHRF online platform (WP4). These will be purchased in year 2 of the project when the PHI platform will be developed and will be installed in fixed locations at each Partner’s campus where access will be available to students, faculty, staff and alumni. This will allow access to the opportunities and career planning available for students and alumni on the platform regardless of whether they have the resources available to purchase a personal computer with access to the Internet. Audio-visual, computing and other support equipment will be purchased to support the PHI Career Fair (WP4). This equipment will be located at UH (P5), the Partner responsible for organising the event. Investment in the equipment will support the continued sustainability of the annual event in the years immediately following the project. This equipment will be purchased in years 3 of the project during the Career Fair planning. Audio-visual, computing and other support equipment will be purchased to support the PHI Leadership Academy peer-to-peer sessions (WP5). This equipment will be purchased during years 2 and 3 of the project and will be located at BGU and the other Israeli Partners. The equipment will be needed to support the train-the-trainer, peer-to-peer activities during the project period and will remain at BGU to help sustain the Leadership Training Academy activities in the years immediately following the project period. Exhibition stand and audio-visual equipment will be purchased to support stakeholder engagement and dissemination activities (WP6/7). This equipment will be purchased in years 1-3 of the project and will support stakeholder engagement at local events and dissemination of project results at conferences. The equipment will be located with IAPHP in Tel Aviv. It will help sustain dissemination and stakeholder activities in Israeli PH workforce development in the years immediately following the project period.

(Please add Partner Countries as appropriate)

Please complete the following Logical Framework Matrix:

☐

# E.4 Logical Framework Matrix – LFM

| Wider Objective: ☒ What is the general objective, to which the project will contribute? - Enhancement of the PHW in Israel through sharing European educational experience, including: harmonization, employability, leadership and outreach. | Indicators of progress: What are the key indicators related to the wider objective? - Harmonization – learning objectives (LOs) and training appropriate at each education level across Israeli programmes of PH. - Employability – Education and training received by PH students matches employer expectations. - Leadership – Leadership and problem-based competencies transferred to the PHW with courses and programmes of PH reflecting real-world examples and experiences in their training. - Outreach – PH training available and attractive to other health professions, communities and sectors. | How indicators will be measured: What are the sources of information on these indicators? - Harmonization: HEIs in PH adopt new policies and strategies to adjust their programmes’ LOs in order to address the competencies required at each education level to meet employer expectations. - Employability: Proportion of students finding practical placements during the course of their education and employed in the PH sector upon graduation/completion of training. - Leadership: New leadership and problem-based learning (PBL) components incorporate into PH programme curricula, courses and theses. Number of faculty trained to provide leadership and PBL. - Outreach: New promotion strategies taken and number of relevant course offerings in PH training provided by HEIs (e.g., academization of allied professions, and CPD). Number of enrolled students with other health and related professional backgrounds, other sectors, and minorities. |  |  |
| --- | --- | --- | --- | --- |
| Specific Project Objective/s: What are the specific objectives, which the project shall achieve? - SO1: Detailed analysis of field qualifications content to understand different professional roles in the Israeli PH system. - SO2: Mapping of the competency profiles of the Israeli HEIs of PH to guide HARMONIZATION at different academic levels and between PH education and practice. - SO3: Introduction of a dynamic online interface to enable PH education/ training - practice/ workforce collaboration, supporting EMPLOYABILITY and continuing professional development in the Israeli PH system. - SO4: Building LEADERSHIP capacity through cutting edge training in the Israeli HEIs in PH, including peer-to-peer and train-the-trainers offerings. - SO5: Stakeholder engagement to secure key OUTREACH (community, inter-professional, cross-sectoral) needed to sustain the proposed solutions. | Indicators of progress: What are the quantitative and qualitative indicators showing whether and to what extent the project’s specific objectives are achieved? - SO1: The indicator for achievement of SO1 will be delivery of the report of field qualifications in the Israeli PH system that is comprehensive and representative of the field qualifications required of PH employers and communities throughout Israel reflected over the 10 Essential Public Health Operations (EPHOs). To be fully realized this should indicate field qualifications at entry, competent and expert levels. - SO2: The indicators for achievement of S02 will be delivery of the report of the mapping of competency profiles of PH education and training in Israeli HEIs with recommendations to guide harmonization between education and training at all academic levels of at least the 4 participating HEIs and the PHW needs indicated in WP2. - SO3: The indicators for achievement of SO3 will be the development of the PHI PHRF online tool to serve as a dynamic interface enabling relevant interactions based on the analysis and mapping in SO1 and SO2; and the organisation of an annual PHI career fair for the particpating 4 HEIs and pracitcal placement schemes for the PH system. - SO4: The indicator for accheivement of SO4 will be enhanced Leadership Capacity achieved and number of trainers and faculty trained within the framework of the PHI Leadership Academy to train-the-trainers and offer peer-to-peer services on PBL and leadership teaching methodologies. - SO5: The indicators for achievement of SO5 will be development of the IAMPH campaign to raise awareness of the roles played by PH and PH Professionals; development of a PH register for PH professionals in relation to the EPHOS. Progress will be indicated by increased numbers of target group members enrolling in PH HEIs and registering in the PHI Register. | How indicators will be measured: What are the sources of information that exist and can be collected? What are the methods required to get this information? - SO1: The WHO-ASPHER Competency Framework for the Public Health Workforce in the European Region (CFPHW) provides a means to evaluate the competencies needed at three levels of the workforce (entry, competent, expert). It will be adjusted to survey the PH system in Israel and analyse the field qualifications needed by Israeli employers, stakeholders and communities. - SO2: ASPHER's European Core Competences list for the PH Professional (ECCLPHP) can be applied to define entrance and exit competencies to be achieved in courses and comprehensive programmes of PH, and Continuing Professional Development (CPD). Based on the ECCLPHP, a survey instrument will be developed to map the competency profiles of Israeli HEIs in PH and adminstered to at least the 4 participating HEIs. - SO3: ASPHER’s European Public Health Reference Framework (EPHRF), constituting of a systematic and flexible tool to contribute to PHW planning, career guidance, education and training choices, and practical placement will serve as a model for developing the PHI PHRF platform informed by reports from WP2&3. IT technological support will be subcontracted to build the platform, which will be maintained and hosted by the Israeli HEIs. Partners leading on this work will build on past successes organising alumni events to organise the PHI Career Fair. - SO4: Leaders for European Public Health (LEPHIE) will serve as a model for building and implementing the PHI Leadership Academy. LEPHIE has developed a Leadership course and manuals for PH professionals using PBL, and blended-learning methods. - SO5: The PHI IAMPH campaign will be built on the established This is PH Europe and Israel campaigns. The IAMPH and design of the PHI Register will be informed by the reports from WP2&3 to pinpoint stakeholders and ensure comprehensive coverage of target groups. | Assumptions & risks - What are the factors and conditions not under the direct control of the project, which are necessary to achieve these objectives? What risks have to be considered? - SO1: Assumptions: Employers and community organizations must be willing and able to provide useful and comprehensive feedback on the qualifications required by the PHW to meet PH challenges. Risks: Employers and the community may not be aware of what competencies are available nor what competencies they require to meet population health needs. - SO2: Assumptions: HEIs must be willing to share information about their students and programmes and be receptive to recommendations for changes to their PH curicula and to recognise competencies students may have already attained in previous degree programmes and in the course of their work experience. Risks: HEIs and their structures may be resistant to making fundamental changes in their programmes and curricula. - SO3: Assumptions: Students, alumni, employers, and communities will use the online platform and career fair to interface, offer and find practical placement and offer career development and PHW planning. Risks: Target audiences may not engage in and make use of the online platform nor attend the career fair. - SO4: Assumptions: Faculty will be keen to modernise and diversify their teaching methodologies and implement these into their course work. HEIs will be willing to support the staffing needs to implement these more intensive teaching methods Risks: Faculty may be resistant to changing their teaching methods. Experiential teaching methods are more time intensive and may require more staff hours; students may be resistant to participatory learning. - SO5: Assumptions: The core and wider PHW will want to participate and officially recognise/register their role as PH professionals. Risks: There is a large portion of the workforce delivering EPHOs that are not formally trained in PH, they may feel threatened by professionalisation and registration of the PHW when they lack specific PH training. Other health professionals may not see the need for PH training or recognition. | How the risks will be mitigated: - SO1: Use of the CFPHW will mitigate this risk, as it outlines a framework of competencies/qualifications using specific terminology linking to the EPHOs, thus offering an accessible guide to employers and communities. - SO2: Risk will be mitigated by presenting harmonization in the form of recommendations that will better serve students and their LOs at each education level making them more employable and increasing the relevance of all PH programmes. 4 Israeli HEIs of PH are partners, representing a majority of HEIs in PH in Israeli and are receptive to the project objectives. The CHE has called for reforms of PH education in Israel. - SO3: In order to mitigate risks, platform stations will be set up at HEI campuses for easy student access. The online platform and career fair will be promoted widely at Israeli HEIs and amongst the Parner Schools’ and IAPHP’s networks of employers and community organisations. Faculty will be encouraged to engage to provide career development guidance and match students to placement opportunities. Employers and communities will be encouraged to post placements and employment opportunities.SO4: Risks will be mitigated by presentation of how the leadership and PBL methods work to prepare students to face real world problems and challenges and meet employer needs. Instructors and trainers in these methodologies do not need to be faculty level - PhD students may be trained to work with MPH students, MPH students to work with Bachelors, etc. - reducing the need to hire additional faculty. Students have already expressed their desire for more practical, experience-based education in CHE evaluation reports. - SO5: Risks will be mitigated by promoting PH CPD training schemes. Programmes such as the BA can be offered to paraprofessionals to improve how they do their jobs and advance careers. The IAMPH campaign will show the diversity of the PHW delivering EPHOs allowing more of the wider PHW to recognize their own PH identity. |
| Outputs (tangible) and Outcomes (intangible): Please provide the list of concrete DELIVERABLES - outputs/outcomes (grouped in Work packages), leading to the specific objective/s.: - WP2 Field Qualifications Analysis in the Israeli PH System (SO1) - As a preparatory WP, it will result in clarity over PH careers and field qualifications needed by PH employers and communities - [2.1] Survey instrument for the mapping of field qualifications - [2.2] Report from Survey mapping field qualifications in the Israeli PH system - WP3 Education and PHW harmonization in the Israeli PH system (SO2) - As a preparatory WP, it will give clarity over current academic competencies offered at HEIs in Israel and provide recommendations to harmonize academic progression at all education levels and with the PHW - [3.1] Survey Instrument to map the competency profiles of the Israeli HEIs of PH - [3.2] Report from the mapping of competency profiles of the Israeli HEIs of PH - WP4 WF adaptation and employability in the Israeli PH system (SO3) - This development WP will provide a platform and opportunities for HEI students, alumni and faculty to interface and collaborate with PH system employers, communities and stakeholders for practicums, career opportunities and PHW development - [4.1] PHI PHRF online tool for PH education/training and workforce/employer collaboration - [4.2] PHI Practical Placement Scheme - [4.3] PHI Career Fair - WP5 Building leadership capacity in the Israeli PH system (SO4) - This WP will develop a cadre of faculty and trainers with knowledge in PBL and leadership training that they may use for future trainings and integration into PH curricula - [5.1] PHI Leadership Academy train-the-trainer manual - [5.2] Reports from the 5 + 1 pilot train-the-trainer sessions - WP6 Stakeholder engagement (SO5) - The WP will result in a strengthened PH professional identity growing the interest of target groups to take up education and training in PH and recognize themselves as professionals within the PHW - [6.1] PHI IAMPH Campaign Plan - [6.2] PHI IAMPH Stories - [6.3] PHI IAMPH Happenings at IAPHP conferences - [6.4] PHI PHW Register - [6.5] Report from PHI IAMPH Campaign | Indicators of progress: What are the indicators to measure whether and to what extent the project achieves the envisaged results and effects? - WP2 - [2.1] Development of a Survey instrument for Israel suitable to evaluating PH field qualifications at entry, competent and expert levels - [2.2] Full report from the survey comprehensively mapping professional roles identified for the Israeli PH system and their corresponding field qualifications at entry, competent and expert levels. Number and comprehensiveness of employers surveyed. - WP3 - [3.1] Development of a Survey instrument for Israel suitable to evaluating PH competencies offered at HEI at Bachelors, Masters, PhD and CPD levels - [3.2] Full report from the survey comprehensively mapping competencies offered at Israeli HEIs. Recommedations made that are feasible to harmonize PH education and training at all eduation levels and with the PHW. Number of PH HEIs surveyed. - WP4 - [4.1] Number of individual and institutional users of the PHI EPHRF tool (web-based) - [4.2] Number of individuals enrolled in the PHI Practical Placement Scheme. Number of host/employer organizations offering practical placements. Impact on employment and career paths - [4.3] Numbers attending PHI Career Fair. Number of host/employer /stakeholders participating in career fair. Numbers of participants successfully finding employment/advancement - WP5 - [5.1] A manual will be produced that can be used after the project period to continue train-the-trainer activities in Israel - [5.2] Number of trainers and faculty trained in PBL and leadership methodologies. Percentage of PBL/leadership methods included in courses and curricula of Israeli HEIs. Impact on student's leadership capabilities and job readiness upon graduation - WP6 - [6.1] PHI IAMPH campaign is well constructed and able to engage stakeholders - [6.2] Number of IAMPH videos and stories and their reach - [6.3] Number of participants in IAMPH campaign happenings - [6.4] Number of PH professionals registered - [6.1-4] Number of allied and wider PHW professionals identifying with PH roles. Number of target groups enrolling in PH HEIs | How indicators will be measured: What are the sources of information on these indicators? - WP2 - [2.1] The CFPHW upon which the Survey will be based offers standardized and consistent definition of skills required of PH professionals to deliver EPHOs. - [2.2] Internal and external experts and stakeholders, external evaluator, IAPHP - WP3 - [3.1] The ECCLPHP upon which the Survey will be based consists of a comprehensice list of competencies for PH Professionals designed to be used to assess PH educational programmes - [3.2] Israeli Partners and external evaluator - WP4 - [4.1] Number of site visits and users engaged and in what activities (e.g., practical placements, career guidance, job postings). - [4.2] Numbers of students engaged in research practicums and PH campaigns and number and variety of opportunities offered through the scheme. Alumni surveys to determine impact of practicums on employment and career paths - [4.3] Numbers of students and alumni finding employment opportunities through the career fair. Tracking of alumni employment outcomes and career paths - WP5 - [5.1] The manual will be based on the LEPHIE programme and will be tested in 5 pilot train-the-trainer sessions during the project period. Evaluation surveys will be given to pilot participants - [5.2] Follow up survey with faculty and HEIs after the pilot period to determine PBL and Leadership training content integrated into curricula. Survey of student satisfaction from courses designed with PBL and Leadership training content - WP6 - [6.1] Previous IAMPH and TIPH campaigns in Europe and North America. - [6.2] Number of events showcasing IAMPH stories. Number of viewers and readers of online content. - [6.3] Tracking of numbers attending IAMPH Campaign happenings - [6.4] Tracking of numbers of professionals registered, their PH and other professional roles - [6.1-4] Follow up surveys with PHW professionals. Enrolment statistics at HEIs | Assumptions & risks What external factors and conditions must be realised to obtain the expected outcomes and results on schedule? - WP2 - [2.1] Assumption: Survey Instrument is suited to assess Israeli PH field qualification needs. Risk: Survey will not be appropriate to the Israeli context nor capture the extent of PH roles - [2.2] Assumption: A comprehensive map of Israeli PH roles/field qualifications is achieved. Risk: Key PH employers are missed or are unwilling or unable to complete the survey in a timely manner - WP3 - [3.1] Assumption: Survey instrument will assess Israeli PH HEI competencies. Risk: the Survey does not capture the extent of competencies offered - 3.2] Assumption: A map of competencies taught at Israeli PH HEIs is achieved. HEIs are open to recommendations. Risk: HEIs are unwilling to participate in survey and unreceptive to recommendations. - [4.1-3] Assumption: HEI target groups will engage in PHI PHRF/Practical Placement Scheme/Career Fair. PH employers will engage with HEIs through the 3 deliverables offering practicums and employment. Risks: Target groups from HEIs do not engage with the 3 deliverables. Stakeholders and employers are unaware of the platforms or do not offer placement opportunities - WP5 - [5.1] Assumption: the manual will be suitable to carry out pilots and used after the project. Risk: the Manual will not be suitable - [5.2] Assumption: Pilot participants will train others after the project. Faculty and HEIs will integrate PBL/Leadership methods into course curricula. Risk: Trainings end after project. HEIs and faculty not receptive to methodologies. - WP6 - [6.1] Assumption: IAMPH Campaign will be well-designed. Risks: campaign is poorly considered - [6.2-3] Assumption: IAMPH Campaign/happenings will reach a large audience informing target groups of PH roles. Risks: The campaign fails to engage a wide audience. - [6.4] Assumption: Professionals will recognize the roles they play in PH and wish to strengthen their PH identity through the PHI register. Risks: Professionals will not recognize their roles in PH and not wish to register. | How the risks will be mitigated: - WP2 - [2.1] CFPHW upon which the Survey will be built represents a comprehensive framework of competencies to deliver EPHOs at all levels of the PHW. It is designed to be adaptable to different countries. - [2.2] Internal and external experts will be consulted to ensure that a comprehensive representation of PH employers is surveyed. An external evaluator familiar with the Israeli PH system will be engaged. Follow up will be taken with survey recipients as needed - WP3 - [3.1] ECCLPHP upon which the Survey will be built is a comprehensive list of PH competencies needed by PH professionals designed for HEIs to evaluate their programmes. - [3.2] 4 of the 5 major HEIs with programmes of PH in Israel are Partners. CHE has called for reforms in PH training in Israel - [4.1-3] The PHI PHRF online platform/Practical Placement Scheme/Career Fair will be widely advertised to target groups (both HEIs and employers) through social media and HEI's and IAPHP's networks. Employers surveyed in WP2 will be invited to participate. Associate Partners have been identified to offer practicums. Specific to 4.1, computer stations will be set up at HEIs for students to access the online platform. - WP5 - [5.1] The manual will be based on the LEPHIE materials produced and tested in Europe and will be translated into Hebrew. Feedback from pilot sessions can be use to make improvements as needed. - Experts in the methods from European Partners will be involved in pilot trainings. BGU committed to establishing a Leadership Academy responsible for future trainings as an extention of the BGU Management School's Social Leadership Programme. 4 HEI Partners have expressed commitment to update teaching methods. - WP6 - [6.1-3] Experts from previous IAMPH/TIPH campaigns will be consulted. Social media and Partner networks will be exploited to engage a wide audience. - [6.4] IAMPH will feature a range of PH roles to feature the diversity of PH professionals and encourage others to identify and register |
| Activities: What are the key activities to be carried out (grouped in Work packages) and in what sequence in order to produce the expected results? - YEAR 1 - Preparation - WP2 - Survey [2.1] of employers across the Israeli PH system to map field qualifications. Delivery of WP2 report [2.2] for M11 so that findings may be used to inform report of WP3 [3.2]. - WP3 - Survey [3.1] of competency profiles of Israeli HEIs of PH. Delivery of the WP3 report [3.2] in M12 taking into account [2.2] for recommendations to HEIs. - Dissemination - WP7 - Presentation at ASPHER Retreat M7 [7.1]. Project website M2; newsletters in M2 and M8; ongoing social media [7.5] - YEAR 2 - Development - WP4 - PHRF tool [4.1] for M6. Practical Placement Scheme [4.2] M10 to enrol students in practicums for fall semester. Deliverables [2.2 & 3.2] inform content of PHRF and Scheme. - WP5 - Trainer manual [5.1] for Leadership Academy for M12. Deliverables [2.2 & 3.2] inform the training needs required. - WP6 - IAMPH Campaign Plan [6.1] completed by M6. 1st edition of IAMPH stories [6.2] launched M7 (updates M10 & M12), and IAMPH happenings at IAPHP Conf. M8 to encourage PHW to identify as PH professionals and register. PHI Register [6.4] launched M7 to coincide with launch of IAMPH. Deliverables [2.2 & 3.2] inform development of IAMPH and Register. - Dissemination - WP7 - Presentations/workshops at ASPHER Retreat M7 and IAPHP Conf. M8 [7.1,7.2]. Ongoing dissemination: website, social media, newsletter [7.5] - YEAR 3 - Development - WP4 - Practical Placement Scheme [4.2] M3 to enrol students in practicums for spring semester. Career Fair [4.3] in M8 to coincide with end of academic year. - WP5 - 5 Peer pilots M3,4,5,6,7 at Israel Partners using trainer manual [5.1]. Interim pilot report M8. Leadership Academy Pilot M11 using trainer manual [5.1] and informed by interim pilot report. - WP6 - Updates to IAMPH stories [6.2]. IAMPH happenings at IAPHP Conf. M8. - Dissemination - WP7 - Presentations/workshops at ASPHER Retreat M7 and IAPHP Conf. M8. Presentation at EPH pre-conf. M12 [7.3]. Supplement to PHRS M12 [7.4]. Ongoing: website, social media, newsletter [7.5] | ### Inputs: What inputs are required to implement these activities, e.g. staff time, equipment, mobilities, publications etc.? - YEAR 1 - WP2 - Tool: CFPHW. Staff: 104 days (researcher/trainer). Mission: Travel & Stay. Subcontract: IT support - WP3 - Tool: ECCLPHP. Staff: 104 days (researcher/trainer). Mission: Travel & stay. Subcontract: IT support. Publication: For [3.2] WP2 Report [2.2] - WP7 - Staff: 13 days (technical), 6 days (admin). Mission: Travel, & Stay. Subcontract: IT support - YEAR 2 - WP4 - Tool: EPHRF. Staff: 117 days (researcher/trainer), 39 days (technical). Mission: Travel & Stay. Subcontract: IT support. Equipment: 4 PHRF stations at Israel HEIs [4.1]. Publication: WP2&3 Reports [2.2,3.2] - WP5 - Tool: LEPHIE. Staff: 51 days (researcher/trainer) 17 days (technical), 8 days (admin). Mission: Travel & Stay. Publication: WP2&3 Reports [2.2,3.2] - WP6 - Tool: TIPH Campaign. Staff: 78 days (researcher/trainer), 13 days (technical). Mission: Travel & Stay. Equipment: exhibition stands and 4 audiovisual recording devices. Subcontract: IT & audio-video techincal support. Publication: WP2&3 Reports [2.2,3.2] - WP7 - Staff: 13 days (technical) 6 days (admin). Mission: Travel & Stay. Subcontract: IT support - YEAR 3 - WP4 - Staff: 117 days (researcher/trainer) 39 days (technical). Mission: Travel & Stay. Equipment: Audio-visual and stands for Career Fair [4.1]. Publication: WP2&3 Reports [2.2,3.2] - WP5 - Tool: LEPHIE. Staff: 105 days (researcher/trainer), 35 days (technical), 18 days (admin). Mission: Travel & Stay. Equipment: Audio-visual for peer sessions. Publication: Training Manual [5.1] - WP6 - Tool: TIPH Campaign. Staff time: 78 days (researcher/trainer), 13 days (technical). Mission: Travel & Stay. Equipment: Exhibition Stands and 4 Audio-video recorders (purchased in Y2) Subcontract: IT & audio-visual support, translation - WP7 - Staff: 13 days (technica), 6 days (admin). Mission: Travel & Stay. Subcontract: IT support, publication [7.4] |  | Assumptions ¦& risks What pre-conditions are required before the project starts? What conditions outside the project’s direct control have to be present for the implementation of the planned activities? - Preconditions: - The project relies on PHW and HEI development tools created and tested in Europe. There is a risk that they will not be suitable for adaptation to the Israeli Context. - HEIs of PH in Israel must be receptive to making changes to their programmes and curricula and to new training methodologies. - Project deliverables such as the preparatory work must be comprehensive and delivered on time to support development WPs. - Conditions outside direct control: - Israel is subject to instability due to periodic conflicts. These may interfere with planned in-country meetings and activities. | How the risks will be mitigated: - PH systems and HEIs in Europe vary widely due to differing country and regional contexts. The tools to be used have been designed to be adaptable to the various country contexts found within Europe. ASPHER and WHO recognize Israel within the WHO-European Region and therfore tools created by these organizations are meant to also be adaptable to the Israeli context. Moreover, the consortium brings together HEIs representing several distinct regional contexts in Europe (Eastern, Western, Scandinavia, British Isles-Ireland) that can provide expertise and advice with a variety of options for Israel. - The Consortium brings together 4 of the 5 major HEIs with programmes in PH representing a critical number of HEIs that are interested in and ready to update their programmes. Moreover, the recent evaluations and reports from the Council of Higher Education (CHE) in Israel have called for reforms across all PH programmes and can be used to argue for implementation of recommendations at other HEIs. - The project management will ensure timely work on deliverables. Aside from the expertise offered by the Israeli Partners, an external evaluator familiar with the Israeli PH system will be subcontracted and given a driving role in project evaluation and advice to ensure comprehensive deliverables. - In country activities may be moved to more secure partner locations if needed. Consortium meetings scheduled in Israel could be moved to more secure partner locations in country or to European partner countries if needed. If required some meetings and trainings could be held by phone or through distance learning. |

Please complete the following work plan. ☒

# E.5 Work Plan

On the following pages, please provide your work plan for each year of the proposed project

- Please use the model provided below.

- Please complete a one-page work plan for each project year.

- For each year of your proposal, please complete a work plan indicating the deadlines for each outcome and the period and location in which your activities will take place.

- If needed, please insert additional rows into the work plan tables.

- The same reference and sub-reference numbers as used in the logical framework matrix must be assigned to each outcome and related activities.

Examples:

Activity carried out in the Programme Country:         = (E.g. activity in France for two weeks in the first month of the project 2= under M1)

Activity carried out in the Partner Country (ies):        X (E.g., activity in Tunisia for three weeks in the second month of the project: 3X under M2)

# WORKPLAN for project year 1 ☒

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | [WP1] Two project consortium meetings in the location of the EU-based partners (BE, IE) | 8 days |  | 4d= |  |  |  |  |  |  |  |  | 4d= |  |
|  | [WP1] Deliverable 1.1 Terms of reference for the project governance | - |  | o |  |  |  |  |  |  |  |  |  |  |
|  | [WP1] Deliverable 1.2 Project Intranet | - |  |  |  | o |  |  |  |  |  |  |  |  |
|  | [WP1] Deliverable 1.3 Summaries of the project consortium meetings | - |  |  | o |  |  |  |  |  |  |  |  | o |
|  | [WP1] Deliverable 1.4 Progress report - Y1 | - |  |  |  |  |  |  |  |  |  |  |  | o |
|  | [WP2] Two working meetings (IS – Ashkelon/Jerusalem – 1 day jointly WP2/WP3) | 6 days |  |  | 3dX |  |  |  |  |  |  | 3dX |  |  |
|  | [WP2] Survey/self-assessment across PH system in Israel; follow up interviews with key stakeholders | 24 weeks |  |  |  | 4wX | 4wX | 4wX | 4wX | 4wX | 4wX |  |  |  |
|  | [WP2] Development of the Report re FIELD QUALIFICATIONS | 8 weeks |  |  |  |  |  |  |  | 2w X/= | 2w X/= | 2w X/= | 2w X/= |  |
|  | [WP2] Deliverable 2.1 Survey instrument | - |  |  |  | o |  |  |  |  |  |  |  |  |
|  | [WP2] Deliverable 2.2 Report from the survey | - |  |  |  |  |  |  |  |  |  |  | o |  |
|  | [WP3] Two working meetings (IS – Jerusalem/Ashkelon – 1 day jointly WP3/WP2) | 6 days |  |  | 3dX |  |  |  |  |  |  | 3dX |  |  |
|  | [WP3] Mapping of the competency profiles of the Israeli schools and programmes of public health | 24 weeks |  |  |  | 4wX | 4wX | 4wX | 4wX | 4wX | 4wX |  |  |  |
|  | [WP3] Development of the Report re COMPETENCY PROFILES OF PH HEIs in Israel | 8 weeks |  |  |  |  |  |  |  |  | 2w X/= | 2w X/= | 2w X/= | 2w X/= |
|  | [WP3] Deliverable 3.1 Survey instrument | - |  |  |  | o |  |  |  |  |  |  |  |  |
|  | [WP3] Deliverable 3.2 Report from the survey | - |  |  |  |  |  |  |  |  |  |  |  | o |
|  | [WP7] Set up and regularly update the project website, newsletter (2) and social media channels | R (regularly) |  | R | R | R | R | R | R | R | R | R | R | R |
|  | [WP7] Prepare project presentation sessions at the ASPHER Retreat 2021 | 1 week |  |  |  |  |  | 1w X/= |  |  |  |  |  |  |
|  | [WP7] Deliverable 7.1 Project presentation session at the ASPHER Retreat 2020 | - |  |  |  |  |  |  | o |  |  |  |  |  |
|  | [WP7] Deliverable 7.5 Project website, newsletter and social media | - |  | o | o | o | o | o | o | o | o | o | O | o |
|  | [WP8] Evaluation Committee election & selection of internal co-chair (at the 1st consortium mtg) | 1 hour |  | 1hX |  |  |  |  |  |  |  |  |  |  |
|  | [WP8] Two EC interim meetings via teleconference (1st semester & 2nd semester) | 3 hours |  |  |  |  | 1,5h X/= |  |  |  |  | 1,5h X/= |  |  |
|  | [WP8] Deliverable 8.1 Summaries of the EC interim/internal meetings | - |  |  |  |  |  | o |  |  |  |  | o |  |

# WORKPLAN for project year 2 ☐

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | [WP1] One project consortium meeting in the location of the EU-based partner (PL) | 4 days |  |  |  |  |  |  |  | 4d= |  |  |  |  |
|  | [WP1] Deliverable 1.3 Summary of the project consortium meeting | - |  |  |  |  |  |  |  |  | o |  |  |  |
|  | [WP1} Deliverable 1.4 Progress report - Y2 | - |  |  |  |  |  |  |  |  |  |  |  | o |
|  | [WP4] One working meeting (IS – Haifa) | 4 days |  | 4dX |  |  |  |  |  |  |  |  |  |  |
|  | [WP4] Development of the PHI Reference Framework | 24 | 4w X/= | 4w X/= | 4w X/= | 4w X/= | 4w X/= | 4w X/= |  |  |  |  |  |  |
|  | [WP4] Organisation of the Practical Placements Scheme | 8 |  |  | 1w X/= | 1w X/= | 1w X/= | 1w X/= | 1w X/= | 1w X/= | 1w X/= | 1w X/= |  |  |
|  | [WP4] Deliverable 4.1 PHI EPHRF online tool | - |  |  |  |  |  | o |  |  |  |  |  |  |
|  | [WP4] Deliverable 4.2 PHI Practical Placement Scheme | - |  |  |  |  |  |  |  |  |  | o |  |  |
|  | [WP5] One working meeting (IS – Beer Sheva) | 4 days |  |  |  |  |  |  |  |  | 4dX |  |  |  |
|  | [WP5] Development of the overall framework for the PHI Leadership Academy / Development of leadership training modalities and the train the trainer manual to serve as key for peer series | 14 |  |  |  |  |  | 2w X/= | 2w X/= | 2w X/= | 2w X/= | 2w X/= | 2w X/= | 2w X/= |
|  | [WP5] Deliverable 5.1 PHI Leadership Academy train the trainer manual incl. leadership training modalities | - |  |  |  |  |  |  |  |  |  |  |  | o |
|  | [WP6] One working meeting (IS – Tel Aviv) | 3 days |  |  |  |  | 3X |  |  |  |  |  |  |  |
|  | [WP6] Devising the IAMPH campaign | 10 weeks | 2w X/= | 2w X/= | 2w X/= | 2w X/= | 2w X/= |  |  |  |  |  |  |  |
|  | [WP6] Piloting the campaign in the context of the IAPHP conferences and PHW video stories series | 14 weeks |  |  |  |  |  | 4X | 4X | 4X |  | 1X |  | 1X |
|  | [WP6] Setting up the PHW register | 10 weeks |  |  | 2w X/= | 2w X/= | 2w X/= | 2w X/= | 2w X/= |  |  |  |  |  |
|  | [WP6] Deliverable 6.1 PHI IAMPH Campaign Plan | - |  |  |  |  |  | o |  |  |  |  |  |  |
|  | [WP6] Deliverable 6.2 PHI IAMPH Stories (1st ed) | - |  |  |  |  |  |  | o |  |  | o |  | o |
|  | [WP6] Deliverable 6.3 PHI IAMPH Happenings at IAPHP 2021 | - |  |  |  |  |  |  |  | o |  |  |  |  |
|  | [WP6] Deliverable 6.4 PHI PHW Register | - |  |  |  |  |  |  | o |  |  |  |  |  |
|  | [WP7] Regularly update the project website, newsletter (2) and social media channels | R (regularly) | R | R | R | R | R | R | R | R | R | R | R | R |
|  | [WP7] Prepare project presentation sessions at the ASPHER Retreat 2022 | 1 Week |  |  |  |  |  | 1w X/= |  |  |  |  |  |  |
|  | [WP7] Prepare project dissemination workshops at the IAPHP Conference 2022 | 1 Week |  |  |  |  |  |  | 1w X/= |  |  |  |  |  |
|  | [WP7] Deliverable 7.1 Project presentation session at the ASPHER Retreat 2022 | - |  |  |  |  |  |  | o |  |  |  |  |  |
|  | [WP7] Deliverable 7.2 Project dissemination workshops at the IAPHP Conferences 2022 | - |  |  |  |  |  |  |  | o |  |  |  |  |
|  | [WP7] Deliverable 7.5 Project website, newsletter and social media | - | o | o | o | o | o | o | o | o | o | o | o | o |
|  | [WP8] 1st Annual EC meeting (in person) | 2 days |  | 2dX |  |  |  |  |  |  |  |  |  |  |
|  | [WP8] Interim in person EC meeting (in the context of the 3rd consortium mtg /WP1) | 1 day |  |  |  |  |  |  |  | 1d= |  |  |  |  |
|  | [WP8] Two interim EC meetings via teleconference (1st semester & 2nd semester) | 3 hours |  |  |  |  | 1,5h X/= |  |  |  |  |  | 1,5h X/= |  |
|  | [WP8] Deliverable 8.1 Summaries of the EC interim meetings (in person & phone) | - |  |  |  |  |  | o |  |  | o |  |  | o |
|  | [WP8] Deliverable 8.2 Year 1 External Evaluation Report | - |  | o |  |  |  |  |  |  |  |  |  |  |

# WORKPLAN for project year 3 ☐

| Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | [WP1] Two project consortium meetings in the location of the EU-based partners (SE, NL) | 8 days |  | 4d= |  |  |  |  |  |  |  | 4d= |  |  |
|  | [WP1] Deliverable 1.3 Summaries of the project consortium meetings | - |  |  | o |  |  |  |  |  |  |  | o |  |
|  | [WP1] Deliverable 1.4 Project final report | - |  |  |  |  |  |  |  |  |  |  |  | o |
|  | [WP4] One working meeting (IS – Haifa) | 4 days |  |  | 4dX |  |  |  |  |  |  |  |  |  |
|  | [WP4] Organisation of the annual PH Career Fair and Practical Placements Scheme | 8 | 1w X/= | 1w X/= | 1w X/= | 1w X/= | 1w X/= | 1w X/= | 1w X/= | 1w X/= |  |  |  |  |
|  | [WP4] Deliverable 4.2 PHI Practical Placement Scheme | - |  |  | o |  |  |  |  |  |  |  |  |  |
|  | [WP4] Deliverable 4.3 PHI Career Fair | - |  |  |  |  |  |  |  | o |  |  |  |  |
|  | [WP5] One working meeting (IS – Beer Sheva) | 4 days |  |  |  |  |  |  |  | 4dX |  |  |  |  |
|  | [WP5] Pilot of the PHI Leadership Academy (Peer 5 +1) | 12 days |  |  | 2dX | 2dX | 2dX | 2dX | 2dX |  |  |  | 2dX |  |
|  | [WP5] Evaluation & adaptation of the PHI Leadership Academy framework after 5 peer sessions | 4 weeks |  |  |  |  |  |  |  | 1w X/= | 1w X/= | 1w X/= | 1w X/= |  |
|  | [WP5] Deliverable 5.2 Reports from the PHI Leadership Academy pilot (Peer 5 +1) | - |  |  |  |  |  |  |  | o |  |  |  | O |
|  | [WP6] One working meeting (IS – Tel Aviv) | 3 days |  |  |  |  | 3dX |  |  |  |  |  |  |  |
|  | [WP6] Piloting the campaign in the context of the IAPHP conferences and PHW video stories series | 14 weeks |  | 1X |  | 1X |  | 2X | 4X | 4X |  | 1X |  | 1X |
|  | [WP6] Deliverable 6.2 PHI IAMPH Stories (1st cont. and 2nd eds) | - |  | o |  | o |  | o |  | o |  | o |  | o |
|  | [WP6] Deliverable 6.3 PHI IAMPH Happenings at IAPHP 2023 | - |  |  |  |  |  |  |  | o |  |  |  |  |
|  | [WP6] Deliverables 6.5 Report from the PHI IAMPH Campaign pilot | - |  |  |  |  |  |  |  |  |  | o |  |  |
|  | [WP7] Regularly update the project website, newsletter (2) and social media channels | R (regularly) | R | R | R | R | R | R | R | R | R | R | R | R |
|  | [WP7] Prepare project presentation sessions at the ASPHER Retreat 2023 | 1 week |  |  |  |  |  | 1w X/= |  |  |  |  |  |  |
|  | [WP7] Prepare project dissemination workshops at the IAPHP Conference 2023 | 1 week |  |  |  |  |  |  | 1w X/= |  |  |  |  |  |
|  | [WP7] Prepare project pre-conference at the EPH Conference 2023 – SEEPHI FINAL CONFERENCE | 2 weeks |  |  |  |  |  |  |  |  |  | 1w X/= | 1w X/= |  |
|  | [WP7] Publish the project supplement in Public Health Reviews (phone meetings) | 6 hours |  | 1,5h X/= |  |  | 1,5h X/= |  |  | 1,5h X/= |  |  | 1,5h X/= |  |
|  | [WP7] Deliverable 7.1 Project presentation session at the ASPHER Retreat 2023 | - |  |  |  |  |  |  | o |  |  |  |  |  |
|  | [WP7] Deliverable 7.2 Project dissemination workshops at the IAPHP Conferences 2023 | - |  |  |  |  |  |  |  | o |  |  |  |  |
|  | [WP7] Deliverable 7.3 Project pre-conference at the EPH Conference 2023 | - |  |  |  |  |  |  |  |  |  |  |  | o |
|  | [WP7] Deliverable 7.4 Project supplement in Public Health Reviews | - |  |  |  |  |  |  |  |  |  |  |  | o |
|  | [WP7] Deliverable 7.5 Project website, newsletter and social media | - | o | o | o | o | o | o | o | o | o | o | o | o |
|  | [WP8] 2nd & 3rd Annual EC meetings (in person) (the latter in the context of the 5th consortium mtg /WP1) | 4 days |  |  | 2dX |  |  |  |  |  |  | 2d= |  |  |
|  | [WP8] Two interim EC meetings via teleconference (1st semester & 2nd semester) | 3 hours |  |  |  |  | 1,5h X/= |  |  | 1,5h X/= |  |  |  |  |
|  | [WP8] Deliverable 8.1 Summaries of the EC interim meetings | - |  |  |  |  |  | o |  |  | o |  |  |  |
|  | [WP8] Deliverable 8.2 Year 2 & Year 3/Final External Evaluation Report | - |  |  |  | o |  |  |  |  |  |  | o |  |

Please complete the information on each work package for your project

# E.6 Work packages

Please enter the different project activities you intend to carry out in your project. Make sure that the information in this section is consistent with the project Logical Framework Matrix.

| Work package type and ref.nr ☒ | MANAGEMENT |  |  | 1 |
| --- | --- | --- | --- | --- |
| Title | PROJECT COORDINATION |  |  |  |
| Related assumptions and risks | ASSUMPTIONS: Project activities follow the agreed work plan and budget. RISKS: Delays and shortcomings in each work package. ASPHER has experience and capacity for coordinating projects in multi-partner consortia; it can act as a facilitator for communication between partners (all HEIs participating in the project being member schools of ASPHER) and oversee the appropriate implementation of the project. Regular meetings of the Project Board (PB) including leads of individual WPs for monitoring of progress and the project content and acivity agendas. The project Intranet to facilitate communication. Each work package co-led by one European/international and one Israeli partner. This WP is synergized with WP8 Quality Plan Activities with two Evaluation Committee meetings overlapping with Management Meetings. A local/Israel-based subcontractor with extensive international background and knowledge of the Israeli PH System hired to facilitate comprehensive external evaluation /quality plan monitoring (WP8). - General considerations for the project management: - The project relies on PHW and HEI development tools created and tested in Europe. There is a risk that they will not be suitable for adaptation to the Israeli Context. - HEIs of PH in Israel must be receptive to making changes to their programmes and curricula and to new training methodologies. - Project deliverables such as the preparatory work must be comprehensive and delivered on time to support development WPs. - Conditions outside direct control: - Israel is subject to instability due to periodic conflicts. These may interfere with planned in-country meetings and activities. - Mitigation : - PH systems and HEIs in Europe vary widely due to differing country and regional contexts. The tools to be used have been designed to be adaptable to the various country contexts found within Europe. ASPHER and WHO recognize Israel within the WHO-European Region and therfore tools created by these organizations are meant to also be adaptable to the Israeli context. Moreover, the consortium brings together HEIs representing several distinct regional contexts in Europe (Eastern, Western, Scandinavia, British Isles-Ireland) that can provide expertise and advice with a variety of options for Israel. - The Consortium brings together 4 of the 5 major HEIs with programmes in PH representing a critical number of HEIs that are interested in and ready to update their programmes. Moreover, the recent evaluations and reports from the Council of Higher Education (CHE) in Israel have called for reforms across all PH programmes and can be used to argue for implementation of recommendations at other HEIs. - The project management will ensure timely work on deliverables. Aside from the expertise offered by the Israeli Partners, an external evaluator familiar with the Israeli PH system will be subcontracted and given a driving role in project evaluation and advice to ensure comprehensive deliverables. - In country activities may be moved to more secure partner locations if needed. Consortium meetings scheduled in Israel could be moved to more secure partner locations in country or to European partner countries if needed. If required some meetings and trainings could be held by phone or through distance learning. |  |  |  |
| Description | The WP1 will enable the project’s appropriate coordination and leadership of the project consortium. Detailed objectives of this work package are as follows: - to ensure the achievement of the specific objectives of the project within the agreed time and budget, with support for technical and administrative project coordination; - to provide efficient administrative and financial management of the project via the adequate governance of the project. ACTIVITIES: Five project consortium meetings in the location of the EU-based partners (i.e. BE, IE, NL, PL, SE). The relevant schedule will be synergized with other project work packages and WPs 7 and 8 in particular (dissemination and quality plan/evaluation). Time isallotted during each of these EU-based meetings for school site visits and community activities so that Israeli representatives will be able to profit from direct contact with European HEIs and PH systems. DELIVERABLES: Terms of reference for the project governance [1.1] Project Intranet [1.2] Summaries of the project consortium meetings (5) [1.3] Progress reports (2) and the project final report [1.4] |  |  |  |
| Tasks | - To set up the project governance system. - To develop and ensure effective use of the Intranet on the project website. - To ensure proper organization of the project consortium meetings. - To organize timely integration and delivery of the project reports. - providing administrative and technical support for successful project development. - supporting Israeli Partners with equipment for project coordination. - subcontract of set up of project intranet. |  |  |  |
| Estimated Start Date (dd-mm-yyyy) | 15-11-2020 | Estimated End Date (dd-mm-yyyy) | 14-11-2023 |  |
| Lead Organisation | Association of Schools of Public Health in the European Region (ASPHER) (P1) |  |  |  |
| Participating Organisation | P2, P3, P4, P5, P6, P7, P8, P9, P10 |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. | - Staff costs (Higher allocation to ASPHER for coordination, remainder proportionately distributed to all partners). - Activities costs (project consortium meetings): 5 meetings in the location of the EU-based partners (i.e. BE, IE, NL, PL, SE); 3 representative/s per partner. - Equipment: 3 laptops per Israeli Partner with the project IT environment set up; required for all partners to support them in their respective partner roles and relevant project coordination (see section E.3 for more details). |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Terms of reference for the project governance |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | Detailed terms of reference for individual governance structures, including: 1. Project Board (composed of representatives of the core project consortium partners, P1-P10). 2. Advisory Council (including representatives of associate partners and other key stakeholders). 3. Evaluation Committee made up of 4 Consortium Representatives, 2 from EU Partneres and 2 from Israeli Partners & 1 Israeli External Evaluator familiar with the Israeli HEIs and PH system. 4. Ad hoc task forces as needed for coordination of project activities and monitoring. |  |  |  |
|  | Due date | Y1M2 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected ‘Other’, please identify these target groups. (Max. 250 words) Project consortium and relevant other parties participating in the project |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☐ International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Project Intranet |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | Integrated with the project website enabling effective internal communication/coordination between partners. |  |  |  |
|  | Due date | Y1M4 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Project consortium and relevant other parties participating in the project |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☐ International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Summaries of the project consortium meetings |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☒ Report ☐ Service/Product |  |
|  | Description | 5 summaries, incl. updates on the project consolidated and detailed work plan, and relevant reporting (annex): #1: introductory (meeting: Year 1, M2) #2: focus on preparatory WP2 & WP3 and 1st interim report including end of year financial and evaluation updates (meeting: Year 1, M11) #3: focus on W4 (meeting: Year 2, M8 integrated with evaluation committee meeting) #4: focus on W5 & WP6 and 2nd interim report including end of year financial and evaluation updates (meeting: Year 3, M2) #5: wrapping up / final report (meeting: Year 3, M10 M8 integrated with evaluation committee meeting) |  |  |  |
|  | Due date | One month after each meeting respectively: #1: Y1M3; #2: Y1M12; #3: Y2M9; #4: Y3M3; #5: Y3M11 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Project consortium and relevant other parties participating in the project |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☐ International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 1.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Progress reports and the project final report |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☒ Report ☐ Service/Product |  |
|  | Description | 2 progress/interim reports delivered at the end of each of the first 2 years of the project; and the project final report. Development of individual reporting elements will be coordinated via the project Intranet and discussed at the project consortium meetings (see 1.3). |  |  |  |
|  | Due date | Progress reports: #1: Y1M12; #2: Y2M12 Final report: Y3M12 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Project consortium and relevant other parties participating in the project |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☒ International |

| Work package type and ref.nr ☐ | PREPARATION |  |  | 2 |
| --- | --- | --- | --- | --- |
| Title | FIELD QUALIFICATION ANALYSIS IN THE ISRAELI PUBLIC HEALTH SYSTEM |  |  |  |
| Related assumptions and risks | General : Assumptions: Employers and community organizations must be willing and able to provide useful and comprehensive feedback on the qualifications required by the PHW to meet PH challenges. Risks: Employers and the community may not be aware of what competencies are available nor what competencies they require to meet population health needs. - Mitigation: Use of the WHO-ASPHER Competency Framework for the Public Health Workforce in the European Region (CFPHW) will mitigate this risk, as it outlines a framework of competencies/qualifications using specific terminology linking to the EPHOs, thus offering an accessible guide to employers and communities. - Deliverable 2.1 - Assumption: Survey Instrument is suited to assess Israeli PH field qualification needs. - Risk: Survey will not be appropriate to the Israeli context nor capture the extent of PH roles. - Mitigation: CFPHW upon which the Survey will be built represents a comprehensive framework of competencies to deliver EPHOs at all levels of the PHW. It is designed to be adaptable to different countries. - Deliverable 2.2 - Assumption: A comprehensive map of Israeli PH roles/field qualifications is achieved. - Risk: Key PH employers are missed or are unwilling or unable to complete the survey in a timely manner. - Mitigation: Internal and external experts will be consulted to ensure that a comprehensive representation of PH employers is surveyed. An external evaluator familiar with the Israeli PH system will be engaged. Follow up will be taken with survey recipients as needed. |  |  |  |
| Description | DETAILED ANALYSIS OF FIELD QUALIFICATIONS CONTENT TO UNDERSTAND DIFFERENT PROFESSIONAL ROLES IN THE ISRAELI PUBLIC HEALTH SYSTEM. In preparation to meet the aim of enhancing the PHW in Israel, the different professional roles needed in the Israeli PH system must first be understood. In order to ensure adequate coverage of standards and roles, mutually understandable descriptors of competencies are needed to identify potential skills gaps and to inform development of training and educational programmes to match job market needs. Mapping field qualification expectations through survey and key person/organisation interviews will enable comparison of competencies by education/training providers, employer organisations and other relevant stakeholders. Developing a full picture of employer and community PHW needs will allow HEIs in Israel to more appropriately tailor their programmes to meet the real-world conditions that await students upon graduation, while strengthening the ties between HEIs, communities and employers. The WHO-ASPHER Competency Framework for the Public Health Workforce in the European Region (CFPHW) (https://www.aspher.org/download/365/05-11-19_phcomp-draft10.pdf) provides a means to evaluate the competencies needed at three levels of the workforce (entry, competent, expert) and can be applied to analyse the field qualifications needed by Israeli employers and communities. The multi-level aspect of the Framework corresponds well with the goals of the Israeli HEIs to understand the qualifications required by PH students at each education level. |  |  |  |
| Tasks | A preparatory analysis of employer and community expectations of PH field qualifications should be complete. This will include a survey instrument used to solicit employer and community organisation feedback and a full report from the survey. It will result in a final PHI Qualification Map of entry, competent and expert levels of PH competencies to be used in subsequent WPs. |  |  |  |
| Estimated Start Date (dd-mm-yyyy) | 15-11-2020 | Estimated End Date (dd-mm-yyyy) | 14-11-2021 |  |
| Lead Organisation | P1/ASPHER & P2/Ashkelon Academic College |  |  |  |
| Participating Organisation | P3, P5, P7, P9 (supporting deliverables 2.1 & 2.2 with local knowledge) |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. | - Staff costs (P1 & P2) - Activities costs (2 meetings in ISRAEL – P1 and P2 /in Y1M3 and Y1M10) – integrated with 2 meetings planned for WP3 with P3 and P4 to synergize preparatory activities - IT subcontracting to support the WP activities with online technologies (deliverables 2.1). This task is subcontracted due to specific technical skills required. |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Survey instrument (based on CFPHW tool) |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | Web-based Survey designed to map field qualifications in the Israeli PH system adapted from the WHO-ASPHER Competency Framework for the PHW in the European Region (CFPHW). The Framework enables standardization and consistent definition of the skills required of PH professionals. |  |  |  |
|  | Due date | Y1M4 |  |  |  |
|  | Languages | English/Hebrew/Other as needed |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Relevant stakeholders in the Israeli PH system, PH employers, Local communities, PH Organizations |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☒ Local ☒ Regional |  | ☒ National ☐ International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 2.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Report from the survey – FIELD QUALIFICATIONS IN THE ISRAELI PUBLIC HEALTH SYSTEM |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☒ Report ☐ Service/Product |  |
|  | Description | As the first preparatory WP it will deliver a report from the survey of field qualifications complemented with findings from a series of follow up interviews with selected/key stakeholders. Including a section dedicated to outreach needed (community, professional, cross-sectoral). |  |  |  |
|  | Due date | Y1M11 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☒ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Training providers and employer organisations as well as other relevant stakeholders in the Israeli public health system. |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☒ National ☐ International |

| Work package type and ref.nr ☐ | PREPARATION |  |  | 3 |
| --- | --- | --- | --- | --- |
| Title | MAPPING OF THE COMPETENCY PROFILES OF THE ISRAELI SCHOOLS AND PROGRAMMES OF PUBLIC HEALTH |  |  |  |
| Related assumptions and risks | - General : - Assumptions: HEIs must be willing to share information about their students and programmes and be receptive to recommendations for changes to their PH curicula and to recognise competencies students may have already attained in previous degree programmes and in the course of their work experience. - Risks: HEIs and their structures may be resistant to making fundamental changes in their programmes and curricula. - Mitigation: Risk will be mitigated by presenting harmonization in the form of recommendations that will better serve students and their LOs at each education level making them more employable and increasing the relevance of all PH programmes. 4 Israeli HEIs of PH are partners, representing a majority of HEIs in PH in Israeli and are receptive to the project objectives. The CHE has called for reforms of PH education in Israel. - Deliverable 3.1 - Assumption: Survey instrument will assess Israeli PH HEI competencies. - Risk: The Survey does not capture the extent of competencies offered - Mitigation: The ECCLPHP upon which the Survey will be built is a comprehensive list of PH competencies needed by PH professionals designed for HEIs to evaluate their programmes. - Deliverable 3.2 - Assumption: A map of competencies taught at Israeli PH HEIs is achieved. HEIs are open to recommendations. - Risk: HEIs are unwilling to participate in survey and unreceptive to recommendations. - Mitigation: 4 of the 5 major HEIs with programmes of PH in Israel are Partners. CHE has called for reforms in PH training in Israel |  |  |  |
| Description | MAPPING OF THE COMPETENCY PROFILES OF THE ISRAELI SCHOOLS AND PROGRAMMES OF PUBLIC HEALTH TO GUIDE HARMONIZATION BETWEEN PUBLIC HEALTH EDUCATION AND PRACTICE. Harmonization will be guided by the results generated in the preparatory phases to determine field qualifications required by employers and the mapping of competency profiles of Israeli HEIs of PH. Recommended guidelines of competencies and learning outcomes (LOs) needed by Israeli PH students at each degree and specialist training level will be generated. ASPHER’s European Core Competences List for the Public Health Professional (ECCLPHP) (https://journals.sagepub.com/doi/full/10.1177/1403494818797072) can be applied for curricula development, defining entrance and exit competencies to be achieved in courses and comprehensive programmes, testing of students’ competencies and setting competencies to be achieved or sustained during continuing professional development. Moreover, a critical number of HEIs in PH in Israel are committed partners to this project and will be receptive to the recommendations generated. |  |  |  |
| Tasks | A preparatory analysis of HEI offerings in PH in Israel will be completed. This will include a survey instrument to map the competency profiles of the Israeli schools and programmes of PH and a full report from the survey. It will result in a final PHI SPHs Competency Map. Recommendations will be made to harmonise programmes of PH, informed by the PHI Qualification Map from WP2 |  |  |  |
| Estimated Start Date (dd-mm-yyyy) | 15-11-2020 | Estimated End Date (dd-mm-yyyy) | 14-11-2021 |  |
| Lead Organisation | P3/Hebrew University of Jerusalem & P4/University College Cork |  |  |  |
| Participating Organisation | P2, P5, P7, P9 (supporting deliverables 3.1, 3.2) |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. | - Staff costs (P3 & P4) - Activities costs (2 meetings in ISRAEL – P3 and P4 /in Y1M3 and Y1M10) – integrated with 2 meetings planned for WP2 with P1 and P2 to synergize preparatory activities - IT subcontracting to support the WP activities with online technologies (deliverable 3.1). This task is subcontracted due to specific technical skills required. |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Survey instrument (based on ECCLPHP tool) |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | Web-based Survey designed to map PH compency profiles of Israeli HEIs of PH adapted from ASPHER’s European Core Competences List for the PH Professional (ECCLPHP): The List complements the definitions from the point of view of competencies and core-curricula; based on the list, the nature and activities of PH can be derived, aggregated and combined to the level of definition of the discipline. |  |  |  |
|  | Due date | Y1M4 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☒ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Schools and prorammes of public health in Israel, Israeli Council of Higher Education (CHE) |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☒ National ☐ International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 3.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Report from the mapping of the competency profiles of the Israeli schools and programmes of public health |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☒ Report ☐ Service/Product |  |
|  | Description | This second preparatory WP will produce a report and recommendations for harmonization of the offers at all academic levels from the mapping of the competency profiles of the Israeli HEIs of PH and in response to the employer and community needs. |  |  |  |
|  | Due date | Y1M12 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☒ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Schools and prorammes of public health in Israel, Israeli Council of Higher Education (CHE) |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☒ National ☐ International |

| Work package type and ref.nr ☒ | DEVELOPMENT |  |  | 4 |
| --- | --- | --- | --- | --- |
| Title | WORKFORCE ADAPTATION AND EMPLOYABILITY IN THE ISRAELI PUBLIC HEALTH SYSTEM |  |  |  |
| Related assumptions and risks | General: - Assumptions: Students, alumni, employers, and communities will use the online platform and career fair to interface, offer and find practical placement and offer career development and PHW planning. - Risks: Target audiences may not engage in and make use of the online platform nor attend the career fair. - Mitigation: In order to mitigate risks, platform stations will be set up at HEI campuses for easy student access. The online platform and career fair will be promoted widely at Israeli HEIs and amongst the Parner Schools’ and IAPHP’s networks of employers and community organisations. Faculty will be encouraged to engage to provide career development guidance and match students to placement opportunities. Employers and communities will be encouraged to post placements and employment opportunities. - Deliverables 4.1-3 - Assumption: HEI target groups (students, alumni) will engage in PHI PHRF/Practical Placement Scheme/Career Fair. PH employers will engage with HEIs through the 3 deliverables offering practicums and employment. - Risks: Target groups from HEIs do not engage with the 3 deliverables. Stakeholders and employers are unaware of the platforms or do not offer placement opportunities. - Mitigation: The PHI PHRF online platform/Practical Placement Scheme/Career Fair will be widely advertised to target groups (both HEIs and employers) through social media and HEI's and IAPHP's networks. Employers surveyed in WP2 will be invited to participate. Associate Partners have been identified to offer practicums. Specific to 4.1, computer stations will be set up at HEIs for students to access the online platform. |  |  |  |
| Description | INTRODUCTION OF A DYNAMIC ONLINE INTERFACE TO ENABLE PUBLIC HEALTH EDUCATION/TRAINING – PRACTICE/WORKFORCE COLLABORATION, SUPPORTING EMPLOYABILITY AND CONTINUING PROFESSIONAL DEVELOPMENT IN THE ISRAELI PUBLIC HEALTH SYSTEM. Building on WP2/Preparation (mapping field qualifications) and WP3/Preparation (mapping of HEI Comptency profiles), WP4/Development aims to introduce a dynamic interface to enable PH HEI and PHW collaboration. This will be a platform for on-going interactions between the PH system, HEIs, employers, communities, students, alumni, faculty and PH professionals. It will serve to provide internship, employment and practical opportunities, individual career development guidance, and workforce capacity system planning. ASPHER’s European Public Health Reference Framework (EPHRF) (https://www.aspher.org/download/27/ephrf_concept_and_policy_brief.pdf), consisting of a systematic and flexible tool to contribute to the planning of the PHW as well as guiding of individual careers, education and training choices will serve as a model for developing the Public Health Isratil (PHI) PHRF platform accompanied by supporting Practical Placement Schemes each semester and annual Career Fair events. Insight provided by the first two preparatory phases of the project (objectives 1 and 2) will be taken into account for the tool develoment. IT support will be subcontracted to build the online infrastucture for the platform, which will subsequently be maintained and hosted by the Israeli HEIs. |  |  |  |
| Tasks | The PHI PHRF tool will be built providing an online interface for students, employers and PH system governance structures to use for practical placement and employment opportunities, career guidance, and PHW planning and development. Further a PHI Practical Placement Scheme and annual PHI Career Fair will be developed and implemented to contribute to employability of project target groups. |  |  |  |
| Estimated Start Date (dd-mm-yyyy) | 15-11-2021 | Estimated End Date (dd-mm-yyyy) | 14-11-2023 |  |
| Lead Organisation | P5/University of Haifa & P6/Jagiellonian University |  |  |  |
| Participating Organisation | P2, P3, P7, P9 (supporting deliverables 4.1, 4.2 & 4.3); P4 to support lead organizations |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. | - Staff costs (P4, P5 & P6) - Activities costs (2 meetings in Haifa – P5 and P6 /in Y2M2 and Y3M3) - Equipment: 2 information stations/portals per Israeli Partner hosting the PHI EPHRF online tool. - Equipment (P5): audio-visual material and other to support PHI Career Fair - IT subcontracting to support the WP activities with online technologies (deliverable 4.1) This task is subcontracted due to specific technical skills required. |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | PHI PHRF online tool (based on EPHRF) |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | Encompassing and operationalizing key outputs of WP2 and WP3, the PHI PHRF online tool will be developed based on ASPHER’s European PH Reference Framework (EPHRF). The EPHRF constitutes a central and comprehensive source of information to enable interactions for PHW planning; mapping PH education and training programmes; mapping job opportunities; and individual career guidance. Building on the findings from WP1&2, the PHI PHRF tool will be developed. |  |  |  |
|  | Due date | Y2M6 |  |  |  |
|  | Languages | English/Other languages as needed and where feasible |  |  |  |
| Target groups | ☒ Teaching staff ☒ Students ☒ Trainees ☒ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Alumni, Employer organisations, PH system governance and other relevant stakeholders in the Israeli public health system. |  |  |  |  |
| Dissemination level | ☒ Department / Faculty ☒ Institution |  | ☒ Local ☒ Regional |  | ☒ National ☐ International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | PHI Practical Placement Scheme |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | PHI Practical Placement Scheme to place students in practical research and PH campaigns each semester in order to gain real world PH experience and skills |  |  |  |
|  | Due date | Y2M10, Y3M3 |  |  |  |
|  | Languages | English/Other languages as needed |  |  |  |
| Target groups | ☐ Teaching staff ☒ Students ☒ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☐ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) |  |  |  |  |
| Dissemination level | ☒ Department / Faculty ☒ Institution |  | ☒ Local ☒ Regional |  | ☒ National ☐ International |

| Expected Deliverable/Results/ Outcomes | Work Package and Outcome ref.nr | 4.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | PHI Career Fair |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☒ Event ☐ Report ☐ Service/Product |  |
|  | Description | An annual PHI Career Fair will be organized to assist students, alumni, and PH professionals and others with job placement and career advancement opportunities |  |  |  |
|  | Due date | Y3M8 |  |  |  |
|  | Languages | English/Other languages as needed and when feasible |  |  |  |
| Target groups | ☐ Teaching staff ☒ Students ☒ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Alumni, General public, PHW, wider health workforce, other professions with PH roles in Israel. |  |  |  |  |
| Dissemination level | ☒ Department / Faculty ☒ Institution |  | ☒ Local ☒ Regional |  | ☒ National ☐ International |

| Work package type and ref.nr ☒ | DEVELOPMENT |  |  | 5 |
| --- | --- | --- | --- | --- |
| Title | BUILDING LEADERSHIP CAPACITY IN THE ISRAELI PUBLIC HEALTH SYSTEM |  |  |  |
| Related assumptions and risks | - General - Assumptions: Faculty will be keen to modernise and diversify their teaching methodologies and implement these into their course work. HEIs will be willing to support the staffing needs to implement these more intensive teaching methods - Risks: Faculty may be resistant to changing their teaching methods. Experiential teaching methods are more time intensive and may require more staff hours; students may be resistant to participatory learning. - Mitigation: Risks will be mitigated by presentation of how the leadership and PBL methods work to prepare students to face real world problems and challenges and meet employer needs. Instructors and trainers in these methodologies do not need to be faculty level - PhD students may be trained to work with MPH students, MPH students to work with Bachelors, etc. - reducing the need to hire additional faculty. Students have already expressed their desire for more practical, experience-based education in CHE evaluation reports. - Deliverable 5.1 - Assumption: the manual will be suitable to carry out pilots and used after the project. - Risk: the Manual will not be suitable - Mitigation: The manual will be based on the LEPHIE materials produced and tested in Europe and will be translated into Hebrew. Feedback from pilot sessions can be use to make improvements as needed. - Deliverable 5.2 - Assumption: Pilot participants will train others after the project. Faculty and HEIs will integrate PBL/Leadership methods into course curricula. - Risk: Trainings end after project. HEIs and faculty not receptive to methodologies. - Mitigation: Experts in the methods from European Partners will be involved in pilot trainings. BGU committed to establishing a Leadership Academy responsible for future trainings as an extention of the BGU Management School's Social Leadership Programme. 4 HEI Partners have expressed commitment to update teaching methods. |  |  |  |
| Description | BUILDING LEADERSHIP CAPACITY VIA CUTTING EDGE TRAINING IN THE ISRAELI PUBLIC HEALTH SCHOOLS AND PROGRAMMES, INCLUDING PEER-TO-PEER AND TRAIN THE TRAINERS OFFERINGS. Improvement in the education of students of PH will be met through the training of faculty and staff at Israeli HEIs in practical problem-based learning (PBL) and leadership training techniques. This must include techniques to appropriately evaluate students’ achieved LOs. In Israel, planning is underway to build a Leadership Academy in PH and this project will support this effort accordingly. The Leaders for European Public Health (LEPHIE) (https://www.aspher.org/download/85/lephie-for-aspher-newsletter.pdf) training was designed in recognition that courses offered by schools of PH often failed to meet the needs and expectations of the PHW. LEPHIE addresses the need for courses in leadership and critical thinking. The experiences and lessons from LEPHIE and the teaching methodologies used in European HEIs can be transferred to the PHI Leadership Academy that is under development, which will then serve to sustain training activities locally. |  |  |  |
| Tasks | The PHI Leadership Academy will be developed and piloted. It will be supported by a train-the-trainer manual with leadership teaching and learning modalities. The piloting of 5+1 peer train the trainer sessions will generate a cadre of trainers ready to introduce and sustain leadership practices and problem based learning to a larger audience of PH faculty and educators across the wider Israeli PH community. |  |  |  |
| Estimated Start Date (dd-mm-yyyy) | 15-04-2022 | Estimated End Date (dd-mm-yyyy) | 14-11-2023 |  |
| Lead Organisation | P9/Ben Gurion University & P10/Maastricht University |  |  |  |
| Participating Organisation | P2, P3, P4 P5, P6, P7, P8 (participating in the peer sessions) |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. | - Staff costs (P9 & P10) - Activities costs (2 meetings in Beer Sheva – P9 and P10 /in Y2M9 and Y3M8) (5 +1 peer sessions at each Israeli Partner + BGU PHI Leadership Academy) - Equipment (audio-visual material and other to support peer sessions) |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 5.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | PHI Leadership Academy train the trainer manual including leadership training modalities (based on LEPHIE) |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | The Leaders for European Public Health (LEPHIE) programme, resulting from a previous European collaborative effort, developed a leadership course for PH professionals using PBL and blended-learning methods. LEPHIE manuals and methodology will be used to develop the train the trainers manual. |  |  |  |
|  | Due date | Y2M12 |  |  |  |
|  | Languages | English/Other languages if needed and feasible |  |  |  |
| Target groups | ☒ Teaching staff ☐ Students ☐ Trainees ☒ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) PHI Leadership Academy /schools and programmes of public health in Israel |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☐ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 5.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Reports from the 5 peer sessions (evaluation & adaptation of the PHI Leadership Academy framework) / Report (5 +1) from the PHI Leadership Academy pilot |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☒ Report ☐ Service/Product |  |
|  | Description | 5 peer train-the-trainer sessions will be piloted at each of the Israeli Parners using the train the trainer manual [5.1]. Reports and evaluations will be generated and used to pilot the +1 peer session of the PHI Leadership Academy. A final Report will be delivered. |  |  |  |
|  | Due date | Y3M8 (PEER 1-5), Y3M12 (PEER 5) |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) PHI Leadership Academy /schools and programmes of public health in Israel |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☐ International |

| Work package type and ref.nr ☒ | DEVELOPMENT |  |  | 6 |
| --- | --- | --- | --- | --- |
| Title | STAKEHOLDER ENGAGEMENT |  |  |  |
| Related assumptions and risks | - General - Assumptions: The core and wider PHW will want to participate and officially recognise/register their role as PH professionals. - Risks: There is a large portion of the workforce delivering EPHOs that are not formally trained in PH, they may feel threatened by professionalisation and registration of the PHW when they lack specific PH training. Other health professionals may not see the need for PH training or recognition. - Mitigation: Risks will be mitigated by promoting PH CPD training schemes. Programmes such as the BA can be offered to paraprofessionals to improve how they do their jobs and advance careers. The IAMPH campaign will show the diversity of the PHW delivering EPHOs allowing more of the wider PHW to recognize their own PH identity. - Deliverable 6.1 - Assumption: PHI IAMPH Campaign will be well-designed. - Risks: campaign is poorly considered - Mitigation: Experts from previous IAMPH/TIPH campaigns will be consulted. - Deliverable 6.2 & 6.3 - Assumption: PHI IAMPH Campaign/happenings will reach a large audience informing target groups of PH roles. - Risks: The campaign fails to engage a wide audience. - Mitigation: Social media and Partner networks will be exploited to engage a wide audience - Deliverable 6.4 - Assumption: Professionals will recognize the roles they play in PH and wish to strengthen their PH identity through the PHI register. - Risks: Professionals will not recognize their roles in PH and not wish to register. - Mitigation: PHI IAMPH will feature a range of PH roles to feature the diversity of PH professionals and encourage others to identify and register |  |  |  |
| Description | STAKEHOLDER ENGAGEMENT TO SECURE KEY OUTREACH (COMMUNITY, INTER-PROFESSIONAL, CROSS-SECTORAL) NEEDED TO SUSTAIN THE PROPOSED SOLUTIONS. Stakeholder engagement with employers and the community must be assured. HEIs in PH must also build partnerships with key professional groups needed to promote integration of PH graduates across the broader PHW in Israel; to promote awareness to prioritization in resource allocation for PH and advance recognition and professionalism of the Israeli PHW. A campaign will be developed to raise awareness of PH and its roles, expanding on the ongoing "This is Public Health" campaign (https://www.aspher.org/this-is-public-health-tiph.html) to feature a new "I am Public Health" component to showcase roles and functions filled by members of the PHW. Visibility for the campaign will be given online and at various events and conferences in Israel. Campaign efforts to promote recognition and strengthen professional identity of the PHW will be supported by the establishment of a PHI Register. |  |  |  |
| Tasks | The on-going “This is PH” campaign will be reinforced with an IAMPH campaign and promoted widely in Hebrew and Arabic languages with special happenings at IAPHP conferences. It will result in better understanding and recognition of what makes up PH and who is part of the PHW. It will be targeted to related health professionals, other stakeholders, and the wider public to engage them further in PH. A PHI Register will be developed resulting in a scheme for the PHW to gain official recognition as PH professionals. |  |  |  |
| Estimated Start Date (dd-mm-yyyy) | 15-11-2021 | Estimated End Date (dd-mm-yyyy) | 14-11-2023 |  |
| Lead Organisation | P7/Israeli Assoc of PH Physicians & P8/Swedish Red Cross University College |  |  |  |
| Participating Organisation | P2, P3, P5, P9 (supporting deliverables 6.2 & 6.3), P3 to support lead organizations |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. | - Staff costs (P3, P7 & P8) - Activities costs (2 meetings in ISRAEL – P3, P7 and P8 /in Y2M5 and Y3M5) (IAPHP conferences 2021 & 2022 /in Y2M7 and Y3M7) - Equipment (supporting deliverables 6.2 & 6.3; including: exhibition stand equipment and 2 x audio-video recording devices) - Technical services subcontracting to support the WP activities with audio-video recording and processing work. - IT subcontracting to support the WP activities with online technologies (deliverables 6.2 & 6.4). This task is subcontracted due to specific technical skills required. |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 6.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | PHI IAMPH Campaign Plan (building on TIPH Campaign) |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | This is Public Health (TIPH) Europe and Israel Campaigns will be built upon to create the PHI I am Public Health (IAMPH) Campaign Plan to increases awareness of roles played by individual members of the PHW. |  |  |  |
|  | Due date | Y2M6 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Project consortium and relevant other parties participating in the project |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☐ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 6.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | PHI IAMPH Stories |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | A series of videos featuring stories by PH professionals and their PH roles. |  |  |  |
|  | Due date | 1st edition: Y2M6, Y2M9, Y2M12, Y3M6 Y3M2, Y3M4 2nd edition : Y3M6, Y3M8, Y3M10, Y3M12 |  |  |  |
|  | Languages | English/other languages as needed |  |  |  |
| Target groups | ☐ Teaching staff ☒ Students ☒ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) General public, PHW, wider health workforce, other professionals with a role in PH in Israel. |  |  |  |  |
| Dissemination level | ☒ Department / Faculty ☒ Institution |  | ☒ Local ☒ Regional |  | ☒ National ☒ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 6.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | PHI IAMPH Happenings at IAPHP conferences |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☒ Event ☐ Report ☐ Service/Product |  |
|  | Description | Exhibition stand to serve as a central location to show IAMPH Stories and stage special IAMPH happenings |  |  |  |
|  | Due date | Y2M8, Y3M8 |  |  |  |
|  | Languages | English/other languages as needed |  |  |  |
| Target groups | ☐ Teaching staff ☒ Students ☒ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) General public, PHW, wider health workforce, other professionals with a role in PH in Israel. |  |  |  |  |
| Dissemination level | ☒ Department / Faculty ☒ Institution |  | ☒ Local ☒ Regional |  | ☒ National ☒ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 6.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | PHI PHW Register |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | The PHI PHW Register will be created to officially recognize professionals with a role in PH. Supported by PHI EPHRF [4.1] and the IAMPH Stories and Happenings [6.2,6.4] professionals with a role in PH will be encouraged to officially register as PH Professionals in order to be recognized by employers and to strengthen their PH identity. |  |  |  |
|  | Due date | Y2M6 |  |  |  |
|  | Languages | English/Hebrew |  |  |  |
| Target groups | ☐ Teaching staff ☒ Students ☒ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) PHW, wider health workforce, other professionals with a PH role |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☒ National ☐ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 6.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Report from the PHI IAMPH Campaign pilot |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☒ Report ☐ Service/Product |  |
|  | Description | A final report of the PHI IAMPH Campaign detailing successes and limitations upon which future actions may be built after the project period. |  |  |  |
|  | Due date | Y3M10 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected ‘Other’, please identify these target groups. (Max. 250 words) Project consortium and relevant other parties participating in the project. PHW in Israel. |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☒ National ☒ International |

| Work package type and ref.nr ☒ | DISSEMINATION & EXPLOITATION |  |  | 7 |
| --- | --- | --- | --- | --- |
| Title | DISSEMINATION & EXPLOITATION |  |  |  |
| Related assumptions and risks | ASSUMPTIONS: Synergy with all other WPs. RISKS: Conferences and publishers may not see the relevance of the project to present/publish in their venues. This risk will be ameliorated by organising pre-conference workshops, and using ASPHER (Deans’ and Directors’ Retreat/Public Health Reviews) and IAPHP (annual conference) platforms and networks for dissemination. Online and social media presence will be used to create awareness of the project. |  |  |  |
| Description | ASPHER Deans’ and Directors’ Retreats 2021/Dublin, 2022/Porto, 2023/Kuopio SEEEPHI Project Presentation Sessions IAPHP Conferences 2022/Tel Aviv, 2023/Tel Aviv Dissemination Workshops EPH Conferences 2023/Berlin Project preconference Public Health Reviews supplement of SEEEPHI Project website, newsletter & social media |  |  |  |
| Tasks | - To set up and regularly update the project website including communications via social media. - To organize 3 projects presentation sessions at the ASPHER Retreats 2021-23. - To organize 2 dissemination workshops at the IAPHP Conferences 2022-23. - To organize project pre-conference at the EPH Conference 2023 AS THE FINAL CONFERENCE OF THE PROJECT. - To publish the project supplement in Public Health Reviews |  |  |  |
| Estimated Start Date (dd-mm-yyyy) | 15-11-2020 | Estimated End Date (dd-mm-yyyy) | 14-11-2023 |  |
| Lead Organisation | P1/ASPHER & P7/IAPHP |  |  |  |
| Participating Organisation | P2, P3, P4, P5, P6, P8, P9, P10 (supporting/participating in selected activities) |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. | - Staff costs (P1 & P7 ) - Activities costs: ASPHER Retreats – Y1M7, Y2M7, Y3M7 (financial support to 2 representatives per partner organisation); IAPHP Conferences – Y2M8, Y3M8 (financial support to 30 students/trainees from each Israeli school /120); EPH Conference – Y3M12 (financial support to 2 representative per partner organization; and financial support to 5 students/trainees from each Israeli HEI) - PHR supplement subcontracting – PHR is published on a recognized platform (BioMed Central) which requires specific publishing and production expertise - Subcontracting (P1): IT services for setting up the project website and other needed technical work. This task is subcontracted due to specific technical skills required. |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 7.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | ASPHER Deans’ and Directors’ Retreats 2021-2023 |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☒ Event ☐ Report ☐ Service/Product |  |
|  | Description | SEEEPHI Project Presentation Sessions will be held at the ASPHER Deans & Directors’ Retreat. Organised each year in a different location within the European region, the Deans' & Directors' Retreat is the most important ASPHER membership events of the calendar year. This high level meeting of the heads of ASPHER member institutions plays a significant role in evaluating the ongoing activities. |  |  |  |
|  | Due date | Y1M7, Y2M7, Y3M7 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) ASPHER community (members and partners) |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☐ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☒ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 7.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | IAPHP Conferences 2022 & 2023 |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☒ Event ☐ Report ☐ Service/Product |  |
|  | Description | Dissemination Workshops will be held at the Annual IAPHP Confernce. In cooperation with the Israeli Medical Association, IAPHP organizes an annual conference widely attended by PH and Health Professionals and other PH system stakeholders in Israel. Representatives of Israeli HEIs regularly present work at the event. |  |  |  |
|  | Due date | Y2M8, Y2M8 |  |  |  |
|  | Languages | Hebrew/English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) IAPHP community (members and partners) |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☐ Institution |  | ☐ Local ☐ Regional |  | ☒ National ☐ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 7.3. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | EPH Conference 2023 |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☒ Event ☐ Report ☐ Service/Product |  |
|  | Description | A Final Project dissemination preconference event will be organized at the European Public Health Conference. Organised each year in a different location in Europe, the EPH Conference serves as a forum offering to members a scientific forum for presenting their work, providing the opportunity for young public health professionals to integrate with a broad public health community, and to present the Andrija Stampar Award. ASPHER is a partner for the organisation of the European Public Health Conference from the very beginning (2008).The EPH Conference aims to contribute to the improvement of public health in Europe by offering a means for exchanging information and a platform for debate to researchers, policy makers, and practitioners in the field of public health and health services research as well as public health training and education in Europe. |  |  |  |
|  | Due date | Y3M12 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other IAPHP community (members and partners) |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Wide PH community |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☐ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☒ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 7.4. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | SEEEPHI Public Health Reviews supplement |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | A special supplement of Project materials wll be published in ASPHER’s Society Journal, Public Health Reviews (PHR). It is a multi-disciplinary journal dedicated to publishing topics of current importance to public health. The scope of the journal is global, but special emphasis is placed on Europe and issues that impact and speak to public health in the European Region. PHR publishes thematic series of high-quality review articles on key topics in public health that aim to inform public health practitioners, teachers, students and policymakers. We present historical and contemporary reviews to emphasize new possibilities for public health, to translate research into recommendations for best practices in the real world and to promote discussion in the public health community. Originally published in Israel, PHR retains a recognized readership in the country. |  |  |  |
|  | Due date | Y3M12 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☒ Teaching staff ☒ Students ☒ Trainees ☒ Administrative staff ☐ Technical staff ☒ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Wide PHR readership |  |  |  |  |
| Dissemination level | ☒ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☒ National ☒ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 7.5. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Project website, newsletter & social media |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☐ Report ☒ Service/Product |  |
|  | Description | A dedicated project website will be set up to host Project materials before and after the project period. The web address will be listed on all promotional materials. Periodic newsletters will be published to inform on Project developments, events and other news. An ongoing social media campaign will be maintained. |  |  |  |
|  | Due date | Y1M2 for Project website, ongoing for newsletter and social media |  |  |  |
|  | Languages | English/Other languages as needed and when feasible |  |  |  |
| Target groups | ☒ Teaching staff ☒ Students ☒ Trainees ☒ Administrative staff ☒ Technical staff ☒ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Wide Internet/social media community /PHW |  |  |  |  |
| Dissemination level | ☒ Department / Faculty ☒ Institution |  | ☒ Local ☒ Regional |  | ☒ National ☒ International |

| Work package type and ref.nr ☒ | QUALITY PLAN |  |  | 8 |
| --- | --- | --- | --- | --- |
| Title | QUALITY PLAN & EVALUATION |  |  |  |
| Related assumptions and risks | Assumptions: The Project consortium brings together a unique set of experts and staff with the knowledge and ability to carry out all tasks with excellence in a thourough, timely manner. Risks: Partners engaged in the project may not see gaps and shortcomings in their own work. Mediation: This risk will be ameliorated by subcontracting evaluation and quality control to an outside entity familiar with and with expertise in the Israeli PH HEIs and PH System. The External Evaluatior will be a driver behind the Evaluation Committee, which meets regularly (see section E.3) to monitor and review project work at planning, interim and outcome stages. Partners will engage with associated partners, such as the Association of Schools and Programs of Public Health (ASPPH) in North America to act as peer reviewers on project development. |  |  |  |
| Description | Quality control and monitoring (WP8) led by AAC (P1) will focus on timely action on activities and deliverables for each of the SOs (see E.1). Evaluations will be based on the activity reports and deliverables of each WP. The Evaluation Committee (EC) will be established at the 1st consortium meeting in M2 of Year 1. It will be made up of 4 elected representatives from among the project partners: 2 European, 2 Israeli; plus the External Evaluator (EE). There will be two co-Chairs of the 5 member EC: the EE will be ex officio co-Chair and a 2nd co-Chair will be selected from among the 4 internal EC Members. External evaluation will be subcontracted to an Israeli-based entity familiar with the country context and PH landscape in order to ensure an impartial review. Serving a critical role for a project of this breadth, the EE will be a driver in the project evaluation process, present at all EC meetings, both annual and interim. The EE will be present at the kick-off consortium meeting to give advice at the start of the project. There will be 4 in person EC meetings. Three annual in person meetings will result in external evaluation reports from the EE, to act as progress benchmarks. One interim mid-year in person meeting will take place in year 2, at the project midpoint and a critical period of project activity. There will be 6 interim meetings by phone. Minutes of the 7 interim meetings will serve as internal evaluation reports and will be made available to all Partners and the EE. |  |  |  |
| Tasks | - establishment of the EC - internal project evaluation and quality checks - arrangement of a contractual agreement (supported by P1) for an external evaluation entity. - overseeing EC meetings and delivery of interim reports - coordination with the External Evaluator for Annual Evaluation Reports (2) and Final Evaluation Report (1). |  |  |  |
| Estimated Start Date (dd-mm-yyyy) | 15-11-2020 | Estimated End Date (dd-mm-yyyy) | 14-11-2023 |  |
| Lead Organisation | P2/AAC |  |  |  |
| Participating Organisation | P1, P3, P4, P5, P6, P7, P8, P9, P10 |  |  |  |
| Costs Please explain the necessary costs for this WP: What travels are necessary? If equipment is requested, explain why it is required. If subcontracting is necessary, explain why the task cannot be performed by the partner. | - Staff costs (P2) - Activities costs (5 meetings /budgeted under WP1 and other WPs already) - Subcontracting: external evaluator for a systematic monitoring of the project quality plan to be contracted through ASPHER (P1) as overall project lead and for management. |  |  |  |

Deliverables/results/outcomes

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 8.1. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | Summaries from the Interim Evaluation Committee meetings (7) |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☒ Report ☐ Service/Product |  |
|  | Description | Minutes of 7 interim EC meetings, including input from the external evaluator will serve as internal evaluation reports and will be made available to all Partners and the external evaluator. |  |  |  |
|  | Due date | Y1M6, Y1M11, Y2M6, Y2M9, Y2M12, Y3M6, Y3M9 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Project consortium and relevant other parties participating in the project |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☐ International |

| Expected Deliverable/Results/ Outcomes ☒ | Work Package and Outcome ref.nr | 8.2. |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Title | SEEEPHI Evaluation Reports (3) |  |  |  |
|  | Type | ☐ Teaching material ☐ Learning material ☐ Training material |  | ☐ Event ☒ Report ☐ Service/Product |  |
|  | Description | Three annual in person meetings will result in external evaluation reports from the External Evaluator, to act as progress benchmarks. Two annual external Reports and one final external report will be made available to all Partners. |  |  |  |
|  | Due date | Y2M2, Y3M4, Y3M11 |  |  |  |
|  | Languages | English |  |  |  |
| Target groups | ☐ Teaching staff ☐ Students ☐ Trainees ☐ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other |  |  |  |  |
|  | If you selected 'Other', please identify these target groups. (Max. 250 words) Project consortium and relevant other parties participating in the project Part of the report widely available |  |  |  |  |
| Dissemination level | ☐ Department / Faculty ☒ Institution |  | ☐ Local ☐ Regional |  | ☐ National ☐ International |

# E.7 Consortium partners involved and human resources required to complete the work packages

Indicative input of consortium staff - The total number of days per staff category should correspond with the information provided in the budget tables. ☐

| Work Package Ref.nr | Partner nr | Partner acronym | Country | Number of staff days ☒ |  |  |  |  | Exact Role and tasks of each person in the work package |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Category 1 | Category 2 | Category 3 | Category 4 | Total |  |
| PREPARATION | P1 | ASPHER | Belgium | 0 | 26 | 0 | 0 |  | Role & tasks include: Co-Lead WP2: Field Qualifications Analysis in the Israeli PH System: - support/assist AAC (P2) to develop and run a survey/self-assessment across PH system in Israel using the ECFPHW tool, complemented with a series of interviews with key stakeholders; - support/assist AAC (P2) to develop the report on Field Qualifications in the Israeli PH System. --- 1 prs (cat.2) – 26 days in 1 year/duration of WP2 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP2) |
|  | P2 | AAC | Israel | 0 | 78 | 26 | 0 |  | Role & tasks include: Co-Lead WP2: Field Qualifications Analysis in the Israeli PH System: - develop and run a survey/self-assessment across PH system in Israel using the ECFPHW tool, complemented with a series of interviews with key stakeholders; - develop the the report on Field Qualifications in the Israeli PH System. --- 1 prs (cat.2) – 78 days in 1 year/duration of WP2 1 prs (cat.3) – 26 days in 1 year/duration of WP2 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP2) |
|  | P3 | HUJI | Israel | 0 | 78 | 26 | 0 |  | Role & tasks include: Co-lead WP3: Mapping of the Competency Profiles of the Israeli Schools and Programmes of Public Health. - map the competency profiles of the Israeli schools and programmes of public health using the ECCLPHP; - develop the report from the mapping of the competency profiles of the Israeli schools and programmes of public health including recommendations on harmonization between education/training and practice/workforce. --- 1 prs (cat.2) – 78 days in 1 year/duration of WP3 1 prs (cat.3) – 26 days in 1 year/duration of WP3 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP3) |
|  | P4 | UCC | Cork | 0 | 26 | 0 | 0 |  | Role & tasks include: Co-lead WP3: Mapping of the Competency Profiles of the Israeli Schools and Programmes of Public Health. - support/assist HUJI (P3) to map the competency profiles of the Israeli schools and programmes of public health using the ECCLPHP; - support/assist HUJI (P3) to develop the report from the mapping of the competency profiles of the Israeli schools and programmes of public health including recommendations on harmonization between education/training and practice/workforce --- 1 prs (cat.2) – 26 days in 1 year/duration of WP3 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP3) |
| SUBTOTAL |  |  |  | 0 | 208 | 52 | 0 |  |  |
| DEVELOPMENT | P5 | UH | Israel | 0 | 104 | 26 | 0 |  | Role & tasks include: Co-lead WP4: Workforce Adaptation and Employability in the Israeli PH System. - work with JU (P6) to develop and implement the PHI EPHRF online tool to serve as a dynamic interface for education/training – practice/workforce collaboration; informing/enabling; - organise an annual PH Career Fair and Practical Placements Scheme for the Israeli PH system. --- 1 prs (cat.2) – 78 days in 2 years/duration of WP4 1 prs (cat.3) – 26 days in 2 years/duration of WP4 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP4) |
|  | P6 | JU | Poland | 0 | 104 | 52 | 0 |  | Role & tasks include: Co-lead WP4: Workforce Adaptation and Employability in the Israeli PH System. - work with UH (P5) to develop and implement the PHI EPHRF online tool to serve as a dynamic interface for education/training – practice/workforce collaboration; informing/enabling; - support/assist UH (P5) to organise an annual PH Career Fair and Practical Placements Scheme for the Israeli PH system. --- 1 prs (cat.2) – 104 days in 2 years/duration of WP4 1 prs (cat.3) – 26 days in 2 years/duration of WP4 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP4) |
|  | P4 | UCC | Cork | 0 | 26 | 0 | 0 |  | Role & tasks include: Support/assistance in WP4: Workforce Adaptation and Employability in the Israeli PH System. - support/assist co-leads of WP4: UH (P5) and JU (P6) to develop and implement the PHI EPHRF online tool to serve as a dynamic interface for education/training – practice/workforce collaboration; informing/enabling; - support/assist UH (P5) to organise an annual PH Career Fair and Practical Placements Scheme for the Israeli PH system. --- 1 prs (cat.2) – 26 days in 2 years/duration of WP4 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP4) |
|  | P7 | IAPHP | Israel | 0 | 78 | 26 | 0 |  | Role & tasks include: Co-lead WP6: Stakeholder Engagement. - devise the campaign IAMPH for the Israeli PH system; - pilot the campaign in the context of the IAPHP conferences (2022 & 2023) and video stories series by the Israeli PHW; - set up the PHW register in Israel. --- 1 prs (cat.2) – 78 days in 2 years/duration of WP6 1 prs (cat.3) – 26 days in 2 years/duration of WP6 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP6) |
|  | P8 | RCUC | Sweden | 0 | 52 | 0 | 0 |  | Role & tasks include: Co-lead WP6: Stakeholder Engagement. - support/assist IAPHP (P7) to devise the campaign IAMPH for the Israeli PH system; - support/assist IAPHP (P7) to pilot the campaign in the context of the IAPHP conferences (2022 & 2023) and video stories series by the Israeli PHW; - support/assist IAPHP (P7) to set up the PHW register in Israel. --- 1 prs (cat.2) – 52 days in 2 years/duration of WP6 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP6) |
|  | P3 | HUJI | Israel | 0 | 26 | 0 | 0 |  | Role & tasks include: Support/assistance in WP6: Stakeholder Engagement. - support/assist IAPHP (P7) to devise the campaign IAMPH for the Israeli PH system; - support/assst IAPHP (P7) to pilot the campaign in the context of the IAPHP conferences (2022 & 2023) and video stories series by the Israeli PHW; - support/assist IAPHP (P7) to set up the PHW register in Israel. --- 1 prs (cat.2) – 26 days in 2 years/duration of WP6 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP6) |
|  | P9 | BGU | Israel | 0 | 104 | 26 | 26 |  | Role & tasks include: Co-lead WP5: Building Leadership Capacity in the Israeli PH System. - develop the overall framework for the PHI Leadership Academy including leadership training modalities and the train the trainer offering to serve as key for peer series; - carry out the pilot across Israel - 5 peer sessions in P9, P2, P3, P5, P7 - evaluate and adapt the framework based on the feedback received, followed by the 6th/final peer session in P9. --- 1 prs (cat.2) – 104 days in 1,5 year/duration of WP5 1 prs (cat.3) – 26 days in 1,5 year/duration of WP5 1 prs (cat.4) – 26 days in 1,5 year/duration of WP5 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP5) |
|  | P10 | UM | Netherlands | 0 | 52 | 26 | 0 |  | Role & tasks include: Co-lead WP5: Building Leadership Capacity in the Israeli PH System. - support/assist BGU (P9) to develop the overall framework for the PHI Leadership Academy including leadership training modalities and the train the trainer offering to serve as key for peer series; - support/assist BGU (P9) to carry out the pilot across Israel - 5 peer sessions in P9, P2, P3, P5, P7 - support/assist BGU (P9) to evaluate and adapt the framework based on the feedback received, followed by the 6th/final peer session in P9. --- 1 prs (cat.2) – 52 days in 1,5 year/duration of WP5 1 prs (cat.3) – 26 days in 1,5 year/duration of WP5 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP5) |
| SUBTOTAL |  |  |  | 0 | 548 | 156 | 26 |  |  |
| QUALITY PLAN | P2 | AAC | Israel | 0 | 0 | 39 | 39 |  | Role & tasks include: Lead WP8: Quality Plan and Evaluation: - organise and coordinate internal quality control and evaluation. --- 1 prs (cat.3) – 39 days in 3 years/duration of WP8 1 prs (cat.4) – 39 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P1 | ASPHER | Belgium | 0 | 0 | 6 | 3 |  | - support WP8 by arranging for an external evaluation (via subcontracting). - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P3 | HUJI | Israel | 0 | 0 | 6 | 3 |  | - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P4 | UCC | Cork | 0 | 0 | 6 | 3 |  | - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P5 | UH | Israel | 0 | 0 | 6 | 3 |  | - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P6 | JU | Poland | 0 | 0 | 6 | 3 |  | - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P7 | IAPHP | Israel | 0 | 0 | 6 | 3 |  | - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P8 | RCUC | Sweden | 0 | 0 | 6 | 3 |  | - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P9 | BGU | Israel | 0 | 0 | 6 | 3 |  | - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
|  | P10 | UM | Netherlands | 0 | 0 | 6 | 3 |  | - participate/contribute in the WP8 activities and/or reporting. --- 1 prs (cat.3) – 6 days in 3 years/duration of WP8 1 prs (cat.4) – 3 days in 3 year/duration of WP8 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP8) |
| SUBTOTAL |  |  |  | 0 | 0 | 93 | 66 |  |  |
| DISSEMINATION & EXPLOITATION | P1 | ASPHER | Belgium | 0 | 0 | 39 | 18 |  | Role & tasks include: Co-Lead WP7: Dissemination and Exploitation. - work with IAPHP (P7) to set up and regularly update the project website including communications via social media; - work with IAPHP (P7) to organize 3 projects presentation sessions at the ASPHER Retreats 2021-23; - work with IAPHP (P7) to organize 2 dissemination workshops at the IAPHP Conferences 2022-23; - work with IAPHP (P7) to organize project pre-conference at the EPH Conference 2023; - work with IAPHP (P7) to publish the project supplement in PH Reviews. --- 1 prs (cat.3) – 39 days in 3 years/duration of WP7 1 prs (cat.4) – 18 days in 3 years/duration of WP7 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP7) |
|  | P7 | IAPHP | Israel | 0 | 0 | 39 | 18 |  | Role & tasks include: Co-Lead WP7: Dissemination and Exploitation. - work with ASPHER (P1) to set up and regularly update the project website including communications via social media; - work with ASPHER (P1) to organize 3 projects presentation sessions at the ASPHER Retreats 2021-23; - work with ASPHER (P1) to organize 2 dissemination workshops at the IAPHP Conferences 2022-23; - work with ASPHER (P1) to organize project pre-conference at the EPH Conference 2023; - work with ASPHER (P1) to publish the project supplement in PH Reviews. --- 1 prs (cat.3) – 39 days in 3 years/duration of WP7 1 prs (cat.4) – 18 days in 3 years/duration of WP7 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP7) |
| SUBTOTAL |  |  |  | 0 | 0 | 78 | 36 |  |  |
| MANAGEMENT | P1 | ASPHER | Belgium | 11 | 0 | 156 | 78 |  | Role & tasks include: Lead WP1: Project Coordination. - set up the project governance system; - develop and ensure effective use of the Intranet on the project website; - ensure proper organization of the project consortium meetings; - organize timely integration and delivery of the project reports; --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 156 days in 3 years/duration of WP1 1 prs (cat.4) – 78 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P2 | AAC | Israel | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P2; - participation in WP5 /hosting a peer session. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P3 | HUJI | Israel | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P3; - participation in WP5 /hosting a peer session. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P4 | UCC | Cork | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P4. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P5 | UH | Israel | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P5; - participation in WP5 /hosting a peer session. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P6 | JU | Poland | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P6. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P7 | IAPHP | Israel | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P7; - participation in WP5 /hosting a peer session. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P8 | RCUC | Sweden | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P8. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P9 | BGU | Israel | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P9; - participation in WP5 /hosting 2 peer sessions. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
|  | P10 | UM | Netherlands | 11 | 0 | 78 | 39 |  | Role & tasks include: - overall project management/coordination in P10. --- 1 prs (cat.1) – 11 days in 3 years/duration of WP1 1 prs (cat.3) – 78 days in 3 years/duration of WP1 1 prs (cat.4) – 39 days in 3 years/duration of WP1 (see sections E5 for the project work plan/detailed schedule and E6 for details on WP1) |
| SUBTOTAL |  |  |  | 110 | 0 | 858 | 429 |  |  |
| TOTAL |  |  |  | 110 | 756 | 1237 | 557 |  |  |

# PART F – Quality of the Project Team and Cooperation Arrangements

# F.1 Background of partnership and the proposal preparation

Please provide shortly the history of cooperation between partners (if any). How the idea of the project was developed and which/ who among partners contributed to the proposal development. (limit 3.000 characters)

There is a rich history of cooperation between the partners. All the consortium partner HEIs are members of ASPHER. The immediate past-president of ASPHER is a faculty member of UM and ASPHER’s office space is located at the UM, Brussels Campus. The eight consortium schools and ASPHER submitted a previous Erasmus+ Capacity Building proposal in 2017 to develop PH undergraduate curriculum in Israel. The proposal was not funded, but the partners continued their resolve to work together. In 2018, AAC was awarded a grant from Israel’s CHE to promote exchange visits of faculty with UM. The IMA/IAPHP works with the SPHs in Israel on planning its annual conferences where faculty and students are active participants. The IMA/IAPHP has been active in the AAC Smoke Free campus since 2017 and are anxious to expand to wider partnerships and advocacy on PH policy issues. As indicated, the consortium submitted a previous Capacity Building Proposal designed to build PH undergraduate curriculum in Israel. The former proposal failed to be funded, however the schools remained committed to building PH capacity in Israel. After pausing plans in 2018 and 2019 to regroup and develop a stronger project. Taking into consideration the CHE Reports the consortium broadened the scope of the proposal to address issues in PH workforce employability in Israel at all education levels, which serves the needs of all Israeli HEIs and the country as a whole. All partners have contributed to the proposal development. Meetings were held in Israel with representatives of UM, ASPHER, the four Israeli HEIs, IMA/IAPHP and the Israel Erasmus office to discuss and plan a proposal for the 2020 call. Current efforts in Europe with ASPHER and WHO to professionalise the PH workforce were presented and UM described skills-based leadership and PBL learning it uses to train PH students. The Israeli HEIs voiced their particular concerns and needs and affirmed their belief that the work already accomplished in Europe would benefit PH workforce capacity and employability in Israel. The overall aim of the project to enhance the PH workforce in Israel was agreed upon and discussions were begun to clarify work packages. Further consortium meetings were held in Ljubljana, Slovenia at the occasion of the European PH Conference with representatives of ASPHER, UCC, RCUC, JU, BGU, HU and IMA/IAPHP and at the ASPHER Deans' & Directors' Retreat in Erice. Sicily. The European partner HEIs were briefed on the meetings in Israel and reaffirmed their commitment to the project. Work Packages were discussed and agreed upon with assignments made for partners to lead on each WP. ASPHER, as the coordinating partner, led on writing and further developing the proposal with continued input from partners via, email, telephone and in person communications.

If relevant, please explain how and to which extent the project benefits from the experience and participation of non–academic partners. (limit 3.000 characters)

The project benefits very highly from the full participation of the partner organisations, ASPHER and IMA/IAPHP. The main functions of ASPHER are to support the professionalisation of the PH workforce in Europe, and thus, to sustain capacity building in PH as supported by best standards of PH education and training, scientific research, and practice. ASPHER has built coalitions with other programmes and PH organisations whose mission is to improve PH and led and partnered on developing and implementing tools to professionalise Europe’s PH workforce. Amongst its objectives, ASPHER aims to develop models for PH education and training at all academic and professional levels, and the interaction of education and training with population health, health systems and services; and to promote structured processes of sharing evidence-based PH models of innovation and good practice. As a membership organisation of institutions, spread across the EU and the wider WHO European Region, ASPHER is poised to take advantage of this collective experience and expertise as well as to widely disseminate project results. The IAPHP, historically founded by PH physicians to promote and develop the scientific, administrative, clinical, social, educational and ethical aspects of PH in Israel, now extends membership to all PH professionals. As a part of the IMA, IAPHP is linked into a much larger, well-resourced organisation which allows it to advance the professional standing of PH professionals among government agencies, medical colleagues and the public; serve as an official source for comprehensive professional consultation on the development and organization of health; influence and affect the development and implementation of PH policy and to promote prioritization in resource allocation for PH; facilitate partnerships, processes and actions affecting PH; advance the professionalism of Israeli PH; oversee the training of physicians in PH; collaborate, nationally and internationally, with organizations that share similar goals; and to support the dissemination of research findings among PH colleagues, policymakers and the general public. Specific project roles will be taken on by each of these organisations. ASPHER’s experience and capacity allows it to coordinate and manage the overall proposal. The Association will assist AAC with its outreach to employers and communities to determine field qualifications needed by PH professionals using European tools that ASPHER was instrumental in developing and implementing. IMA/IAPHP will take on Israeli stakeholder and inter-professional involvement and sustainability through its extended networks. Both associations will lead on dissemination of results of the project in Israel and abroad through their memberships and organised forums (association related conferences and publications).

Please explain the role and the participation of the Programme Country partners and their support in the development of the different activities (e.g. in the development of the curricula) and (limit 3.000 characters)

ASPHER (P1), which counts all consortium HEIs as members, will manage and coordinate the project (WP1), supporting the project as a whole and acting to facilitate communication with partners, including overseeing the implementation of the project Intranet. ASPHER will also co-lead on WP2, Field Quality Analysis in the Israeli PH system. The Association will use its experience conducting reviews of PH practices in Europe to assist AAC (P2) with its survey of the PH system of empoyers needs at entry/competent/expert level and development of the PHI Qualification Framework. ASPHER also co-leads WP7, Dissemination and Exploitation where it will support dissemination activities in Europe at its annual Deans’ & Directors’ Retreat, at the European Public Health (EPH) Conference and in the Association’s Journal, Public Health Reviews. UCC (P4) will co-lead WP3, Mapping of the Competency Profiles of the Israeli Schools and Programmes of Public Health. UCC will lend its experience with integrating PH across all education levels (Bachelor, Master, PhD, CPD) and its successes in ensuring its graduates meet the competencies expected of employers. With HUJI (P3) UCC will develop a survey of core competencies taught at Israeli programmes of PH in order to identify how curricula may be developed at each education level, harmonizing between programmes and with workforce/employers needs for entry/competent/expert levels identified in WP2. After completion of WP3 in Y1, UCC will support co-Leads of WP4 in Y2&Y3. JU (P6) will co-lead WP4, Workforce Adaption and Employability in the Israeli PH System. JU along with subcontracted IT support, will work with UH to develop the PHI EPHRF online tool to serve as a dynamic interface for education and training, and practice and workforce collaboration, thus supporting the Practical placement goals of the Israeli HEIs. UM (P10) will co-lead WP5, Building Leadership Capacity in the Israeli PH System. UM will work with BGU (P9) to develop the framework of the PHI Leadership Academy through a review of good practices, development of leadership training modules, and development of train the trainer offerings to serve as key experts for peer series. UM and BGU will carry out peer sessions in each Israeli Partner location. RCUC (P8) will co-lead on Stakeholder Engagement including supporting development of the PHI Stakeholder Engagement Campaign modeled on This is Public Health (TIPH)/I am Public Health (IAMPH) actions. They will bring their academic cross-professional experience to the activities.

# F.2 Cooperation arrangements, management and communication

Please define the organisation of the implementation of the project and the division of tasks between the partners. Please explain the allocation of resources for each activity. Explain also how the tasks are distributed amongst the partners and how project "ownership" is ensured (limit 3.000 characters).

Each of the core WPs is co-led by one European Partner and one Israeli Partner. All partners co-lead at least one WP giving them ownership of part of the project. ASPHER, is taking on the heaviest role as the management organisation and co-lead on two other WPs, and has the largest European allocation of 112.410 EUR. Resources were allocated so that Israeli Partners receive larger sums with each partner allocated ~100.000-120.000 EUR. European HEI Partners were allocated smaller sums of ~60.000-72.000 EUR. The breakdown of tasks were determined in meetings with consortium Partners and were based on the relative strengths of each Partner. WP1: Management is led by ASPHER (P1), which has the experience and capacity to organise projects across partners. All participating HEIs are ASPHER members. WP2: Preparation of Field Qualification Analysis is co-led by AAC (P2) and ASPHER (P1). AAC is staffed with a cross-section of faculty who have studied and work at HEIs across Israel and the Ministry of Health and thus has the network to assess Field Qualifications throughout Israel. ASPHER will lend its experience running similar assessments in Europe. WP3: Development of Education, and workforce harmonization is co-led by HUJI (P3) and UCC (P4). HUJI is Israel’s leading university and can bring 55-years of PH capacity building to bear when developing recommendations for competencies across academic programmes and levels. UCC, which issues degrees in PH at all academic levels (bachelor, master and PhD) will lend its experience in determining appropriate competencies at each educational level and how its students progress through their education and careers. WP4: Implementation of workforce employability is co-led by UH (P5) and JU (P6) supported by UCC (P4). UH which was judged by CHE to have a strong alumni network will lead on developing the PHI EPHRF online tool for practical placements and career development and will organise a career fair. JU has been involved with similar efforts in Poland and will oversee IT subcontracting in Poland. WP5: Development to build leadership capacity will be co-lead by BGU (P9) and UM (P10). BGU will implement a PH Leadership Academy building on BGU School of Management’s Programme on Social Leadership. UM, a critical HEI involved with LEPHIE in Europe and with a strong PBL based curriculum will help to train the trainers who will sustain the new Academy. WP6: Development of stakeholder engagement will be co-led by IAPHP (P7) and SRCUC (P8) supported by HUJI (P3). IAPHP is already engaged with a network of stakeholders across Israel. SRCUC will lend their experience of outreach to other stakeholders that make up the wider PH workforce. WP7: Dissemination will be co-led by ASPHER (P1) and IAPHP (P7). Both organisations have networks and platforms (conferences and publishing) to facilitate dissemination of results. WP8: Quality plan and evaluation will be led by AAC (P2) with ASPHER (P1) arranging external evaluation.

Please explain the overall project and partnership management making specific reference to the management plan and how decisions will be taken. Please describe how permanent and effective communication and reporting will be ensured as well as the measures put in place for conflict resolution (limit 2.000 characters).

The management of the project will be undertaken by ASPHER. In addition to its capacities in Brussels, ASPHER will subcontract an Israeli External Evaluator (EE) to oversee quality control of activities. ASPHER will ensure that the project activities are prepared, implemented and evaluated on time according to the predefined schedule agreed upon by all consortium members described in the Project Work Plan. It will also ensure that allocation of resources is organized, controlled and transparent, guided by the collectively negotiated budget and milestones. Regularly scheduled management meetings will be held in each of the 5 EU-based partner locations (BE/IE/NL/PL/SE) to provide continuous oversight of activities and support WP leaders during the time of preparation/implementation of their WPs. WP leaders will be responsible for progress on the project’s content. Continuous communication will be organized: Regular updates from ASPHER and leaders of the ongoing WPs will be provided to all project participants and all project participants will share items they consider to be important with the overall project team. Internal reports on the implementation of different work packages will be produced every 6 months. Overall project progress reports will be prepared once a year and involve contributions from all partners. The project website will have an intranet where the team can share drafts, presentations and other documents for internal communication. Meeting agendas and minutes will be available there as well. Partners will be encouraged to raise issues of conflict at any point in the process if and when they arise. When possible these will be handled through usual means of communication and during regularly scheduled management meetings. If necessary, ad hoc telconference meetings may be called to resolve conflics in a timely manner. All-partner meetings will be organized 5 times during the 3 year work plan for in-depth face-to-face exchange and discussion. The EE will evaluate the project progress and outputs once a year and a representative will join the all-partner meetings to ensure a comprehensive evaluation and detailed feedback.

# F.3 Organisations and activities

This part must be completed separately by each organisation participating in the project (applicant and partners with its affiliated entities (if any)).

☒

| Partner number ☒ | 939959004 |  |  |  | P1 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | The Association of Schools of Public Health in the European Region (ASPHER) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| ASPHER is the key independent European organisation dedicated to strengthening the role of public health by improving education and training of public health professionals for both practice and research. Founded in 1966, ASPHER is a membership organisation of institutions, spread across EU and wider across WHO European Region, which are collectively concerned with the professional education/training and professionalism of those entering and working within the public health workforce. It promotes activities which foster exchange of information and best practices amongst its members in an effort to ultimately achieve high standards of public health education/training across Europe. ASPHER has currently over 110 institutional members located throughout the European Region of WHO. It is represented in 43 countries in Europe, with more than 5000 academics and experts employed in its member institutions and reaches more than 150 PH training and education instiututes through network structures belonging to the Association. ASPHER is the founder of the Agency for Public Health Education Accreditation (APHEA). ASPHER is an active member of the European Public Health Alliance (EPHA), the European Public Health Association (EUPHA), the EU Health Policy Forum and the World Federation of Public Health Associations (WFPHA). It also led the work of WHO Europe in the area of EPHO 7 (workforce development) under the framework of the European Action Plan for Strengthening Public Health Capacities and Services. The Association's two main yearly events providing platform for meetings in which greater part of its membership takes part are: (i) Deans' and Directors' Retreat (May/June); (ii) European Public Health Conference (October/November). ASPHER’s website is available at http://www.aspher.org. An online, open access journal of the Association – Public Health Reviews – can be accessed via https://publichealthreviews.biomedcentral.com |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP1: Lead Project Coordination. As the managing organisation, ASPHER will: - set up the project governance system. - develop and ensure effective use of the Intranet on the project website. - ensure proper organization of the project consortium meetings. - organize timely integration and delivery of the project reports. WP2: Co-Lead Field Qualifications Analysis in the Israeli PH System. In this preparatory WP, ASPHER will : - assist AAC (P2) to run a survey/self-assessment across PH system in Israel using the CFPHW tool, complemented with a series of interviews with key stakeholders. - assist AAC (P2) to develop the Report from the Survey – Field Qualifications in the Israeli PH System. WP7: Co-Lead Dissemination and Exploitation. For dissemination purposes, ASPHER will: - set up and regularly update the project website including communications via social media. - organize 3 projects presentation sessions at the ASPHER Retreats 2021-23. - organize project pre-conference at the EPH Conference 2023 to serve as final project presentation. - publish the project supplement in Public Health Reviews. WP8: Quality Plan & Evalutaion - provide support by arranging for an external evaluation (via subcontracting). |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  |  |  |  |
| How will the impact of these results be measured in your HEI? |  |  |  |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  |  |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Robert Otok Director |  | Robert Otok joined ASPHER in 2008. Responsible at the beginning for the setting up and organisation of the Association’s office in Brussels, he now coordinates the work of the ASPHER executive board, managing the largest network of schools of public health in the world. He has an extensive experience in developing, implementing and coordinating projects supporting the public health workforce development and professionalisation in Europe; both at individual countries as well as the European level (the latter including advisory and consultancy positions in ECDC and WHO Europe relevant programmes). He actively supports/participates in selected training and research activities of ASPHER members; since 2011 he has also served as member of the editorial board of Public Health Reviews, the open access journal promoting public health knowledge and best practices, published on behalf of ASPHER. Finally, he is responsible for day-to-day operation of the Association and represents ASPHER in international contexts. Robert was awarded Fellowship of the Faculty of Public Health (London) in June 2018. Related publications: Birt CA, Foldspang A, Otok R. Meeting the population health challenge: what should you know, and what should you be able to do? Eur J Public Health. 2018 Oct 1;28(5):789-790. Otok R, Czabanowska K, Foldspang A. Public health educational comprehensiveness: The strategic rationale in establishing networks among schools of public health. Scand J Public Health. 2017 Nov;45(7):720-722. Bjegovic-Mikanovic V, Otok R. Preparation of European Public Health Professionals in the Twenty-first Century. Front Public Health. 2017 Feb 15;5:18. Müller-Nordhorn J, Bjegovic-Mikanovic V, Otok R, Czabanowska K, Foldspang A. Fifty years of serving public health: the Association of Schools of Public Health in the European Region moving forward to the next half-century. Int J Public Health. 2016 Jul;61(6):631-632. Otok R, Foldspang A. Main competences and skills to perform Essential Public Health Operations, offered by Schools of Public Health in four European countries: a short pilot report. Int Journal of Public Health, 2016. Goodman JD, Muckelbauer R, Müller-Nordhorn J, Cavallo F, Kalediene R, Kuiper T, Otok R. European accreditation and the future public health workforce. Eur Journal of Public Health, 2015. Czabanowska K, Rethmeier KA, Lueddeke G, Smith T, Malho A, Otok R, Stankunas M. Public health in the 21st century: working differently means leading and learning differently. Eur Journal of Public Health, 2014. Bjegovic-Mikanovic V, Jovic-Vranes A, Czabanowska K, Otok R. Education for public health in Europe and its global outreach. Global Health Action, 2014. Czabanowska K, Smith T, Konings KD, Sumskas L, Otok R, Bjegovic-Mikanovic V, Brand H. In search for a public health leadership competency framework to support leadership curriculum – a consensus study. Eur Journal of Public Health, 2014. Vukovic D, Bjegovic-Mikanovic V, Otok R, Czabanowska K, Nikolic Z, Laaser U. Which level of competence and performance is expected? A survey among European employers of public health professionals. Int Journal of Public Health, 2014. Czabanowska K, Smith T, Stankunas M, Avery M, Otok R. Transforming public health specialists to public health leaders. The Lancet, 2013. Bjegovic-Mikanovic V, Vukovic D, Otok R, Czabanowska K, Laaser U. Education and training of public health professionals in the European Region: variation and convergance. Int Journal of Public Health, 2013. Bjegovic-Mikanovic V, Czabanowska K, Flahault A, Otok R, Shortell S, Wisbaum W, Laaser U. Policy summary: Addressing needs in the public health workforce in Europe. Health Evidence Network – European Observatory Series, 2013. Otok R, Levin I, Sitko S, Flahault A. European Accreditation of Public Health Education. Public Health Reviews, 2011. |  |  |  |
| Lore Leighton Secretariat |  | Lore Leighton has been working with ASPHER as the Managing Editor of Association’s journal Public Health Reviews (PHR) since 2016. Prior to that she Managed the Journal from 2009-2014 when it was held by The French School of Public Health (EHESP). Lore began taking on Secretariat responsibilities at ASPHER in 2018 on a consulting basis and is formally employed by ASPHER as of January 2019. She studied biochemistry at Northern Michigan University and was employed as a Research Specialist at Rockefeller University, New York and University of California at Berkeley before moving to Europe in 2007. In addition to her responsibilities at ASPHER and PHR, she freelances as a science writer, editor and illustrator. |  |  |  |
| John Middleton President |  | John Middleton is Honorary Professor of Public Health at Wolverhampton University. He is President of the Faculty of Public Health, the standard setting body for public health professionals in the UK. He was Director of Public Health for Sandwell in the West Midlands of England for 26 years; when he retired in 2014 he was the longest serving DPH ever in the UK. He presented at a number of ASPHER conferences in the mid-2000s, but came back to the issues of European public health training and development during his time as Vice President for the UK Faculty of Public Health 2010-2015. He has presented at ASPHER Dean’s Retreats since 2014. He was elected as an executive member of the ASPHER Board in May 2016. He was awarded Fellowship of the Royal College of Physicians (London) in September 2015. He lives in Coventry in the West Midlands and has four grown up children and four grandchildren. In another life he is a blues harmonica player with albums on spotify and apple music. www.drharp.co.uk |  |  |  |
| Prof. Ted Tulchinsky MD MPH Consultant |  | Graduated MD University of Toronto 1961, Yale MPH 1968. In public health over 50 years starting in Canada as a family physician and later as Deputy Minister of Health in Manitoba (1971-76). Immigrated to Israel in 1976; joined the Ministry of Health as head of public health and then Coordinator of Health in the West Bank and Gaza (1980-1994). Worked on water quality and mandatory chlorination; immunization policy; Rift Valley Fever; occupational health; nutrition and mandating micronutrient fortification of flour; continuing education of health workforce. Taught Organization of Public Health Services at the Braun School of Public Health International MPH program from 1982-2016 with students from around the world. From 2010-2018, Head of a school of health professions including BA program in public health at Ashkelon Academic College. Published 110 articles in peer reviewed journals and many book chapters on a wide range of public health topics including infectious diseases (polio, measles, tetanus etc), nutrition policy and food fortification, maternal and child health, mesothelioma, geriatric care, thalassemia, community health workers, public health ethics and development of public health education. From the 1990s consultant to the World Bank and the Open Society Institute mentoring schools of public health across former Soviet Union (Russia, Ukraine), Central Europe (Macedonia, Moldova, Albania and Georgia), and Central Asia (Kazakhstan, Uzbekistan and Mongolia). Lead author of international textbooks The New Public Health now in third edition (2014) used in Israel, Europe and North America; also published in other languages (Uzbek, Bulgarian, Romanian, Macedonian, Mongolian, Albanian, Georgian, and Turkish) and Case Studies in Public Health (2018). Deputy Editor (2010-2018) Emeritus Editor (2018-current) of Public Health Reviews, ASPHER’s society Journal. 2004 to 2008 member of Executive Board of the ASPHER; chaired Ethics and Undergraduate Education Working Groups. 2008 awarded ASPHER’s Andrija Stampar Medal for excellence in the field of Public Health. Works with the Israel Ministry of Health on nutrition issues. |  |  |  |

| Partner number ☒ | 933007208 |  |  |  | P2 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | Ashkelon Academic College (AAC) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| Ashkelon Academic College (AAC) was established in 1967 as an extension of Bar-Ilan University – a large central well-established university near Tel-Aviv. The mission of this extension was to provide opportunities for higher education to the southern population of approximately 90 thousands residents. In 2007, the AAC received recognition from the Israeli Council of Higher Education (CHE/MALAG), as an Israeli institution of higher education, which allowed awarding baccalaureate degrees independently from Bar-Ilan University. These include academic tracks for BA as well as BSc in the college, including Social Sciences, Humanities, Economics, Criminology, Computer Sciences, Tourism and the new School of Health Sciences. AAC creates greater equality in opportunities for higher education for less advantaged population in the southern area of Israel as compared to central Israel. AAC also provides accessibility to high education to minorities, such as Arabs, including Bedouins, and Orthodox Jews. The AAC reduces the trend of in-country migration of population to the central cities of Israel, and creates positive migration to peripheral cities in Israel of students and teachers. AAC has approximately 300 senior academic staff involved in research projects and cooperation with other universities in Israel as well as international cooperation projects. AAC promotes and maintains excellence in teaching undergraduate students and according to CHE/MALAG is rated as a leading academic College in teaching quality. ash-college.ac.il |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?; 8. Number of students; About 5000. Number of Bachelor degrees offered; 17. Number of Master degrees offered; 3 (Applied Economics, Criminology, Social Work). Number of PhD degrees offered; None. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles); No. |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP8: Lead of Quality Plan and Evaluation: AAC will: - organise internal quality control and evaluation. WP2: Co-Lead of Field Qualifications Analysis in the Israeli PH System. In this preparatory WP, AAC will: - run a survey/self-assessment across PH system in Israel using the CFPHW tool, complemented with a series of interviews with key stakeholders. - develop the Report from the Survey – Field Qualifications in the Israeli PH System. WP1: Project Coordination – Participating WP3: Participating in deliverables contributing insights and lessons from preparatory work in WP2 WP4: Participating in deliverables contributing insights and lessons from preparatory work in WP2 to assist with development of the content of the PHI-EPHRF online tool. WP5: Participating in deliverables hosting an onsite Leadership and PBL training (peer) session. WP6: Participating in deliverables taking part in IAMPH Campaign WP7: Dissemination - Participating in deliverables |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| AAC works closely with the regional hospital in Ashkelon (Barzilai) and other health-related agencies in the community. Target populations include residents in the periphery and the Bedouins. Almost half of the AAC new students are Bedouins who live in the southern parts of Israel. AAC provides a course in research methods for Barzilai medical staff to support them with developing research projects. Our students take part in research projects during Practicums, mentored by a senior physician from Barzilai and AAC lecturers. Barzilai supported development of our program giving a course in HSM. Physicians including Barzilai CEO are taking part in PH program courses. Barzilai will be an Associate Partner with AAC in the Project. We are planning tracks of specializations in the third year: research coordination, environmental health and health management, to provide the required academic skills for post-graduate positions as research coordinators and further education. Environmental track will allow graduates to join municipalities and the Ministry of Health as health inspectors. The management track will allow graduates to join health agencies in administrative positions. A future collaboration is planned at the Hebrew University for a joint BA in PH and a Diploma in Dental Hygiene. Lastly, is transition track for graduates to special academic track in Nursing, after completion of the BA in PH. AAC added field trips to our curriculum, such as environmental health sites, food industry and medical services to Bedouins in the desert, and medical services for undocumented migrants. AAC has launched a preparatory course in 2019 for Bedouin students in preparation for enrolment in health, education and other programmes (see description, section D.3). AAC has conducted an institutional project for a "Smoke Free Campus" with student participation. We plan to expand this to work with Barzilai, Ashkelon city and NGOs to develop a "Smoke Free Ashkelon". AAC has conducted a symposium on "Preventing Micronutrient Deficiency Conditions by Food Fortification" with the Israel MoH Nutrition Department, academic and professional associations, media and students. We will reach out to other health programs; Sick Funds, national data bases, communities at special risk, minority groups, local authorities as Associate Partners to seek projects that can evolve into positions for our graduates. |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  | - Reach out to minority groups through special preparatory courses for enrolment in academic programs of PH. - New PBL oriented skills courses, integrated in the AAC public health education program, tailored for the new national and international public health challenges we are facing. - Joint Research, knowledge-share and practical health promotion projects with actors from surrounding hospitals and other Associate Partners. - Occupation oriented academic tracks will be established in the third year of the program. - International and national well-defined transition track will be established from BA to advanced and other related academic paths. - Improved employability of graduates through wider practicum fields offered by hospitals and other Associate Partners. - Extension of basic PH exposure /education in other academic programs to additional AAC Departments and Associate Partners) |  |  |
| How will the impact of these results be measured in your HEI? |  |  | - Monitor the rate of students from minority groups studying in public health education program at AAC. At least 30% of the class each year will be students from minority groups in the surrounding population. - Problem Based Learning oriented courses will be implemented in at least 20% of the public health education program at AAC. - Produce about 10 joint researches with hospitals and other Associate Partners. - Produce at least once a year a health promotion project implemented in the surrounding community, through collaboration of AAC with Associate Partners. - Produce at least once a year a joint learning workshop, conference or seminar, with surrounding hospitals/health facilities and other Associate Partners. - Monitor the rate of application to each of the specialized academic tracks in the third year of the program. - Monitor the rate of graduates continuing to different advanced and parallel academic tracks. - At least 50% of students will perform their practicum at hospitals and other Associate Partners. - Continuous survey of employability to alumni of the public health program at AAC. - Basic public health education implemented in at least half of the other academic departments in AAC. - Minimum of 2 lecturers exchange visits to prepare future students collaboration. |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  | When the project will end, we have a core of skilled academic staff in the AAC department of public health that can continue the process. Collaborations with the Barzilai hospital and other Associate Partners will be sustained after the project is ended by adoption of a continuing process of implementation: The key people at Barzilai hospital will already be incorporated during the continuing development of the public health program; some of them will join the college staff as adjunct lecturers (while keeping their positions in the hospital) after the project budget will be finished. AAC will provide financial support facilities to sustain partnership with hospitals and other Associate Partners and will seek further domestic and international research funding to continue and expand research and cooperation in public health related topics. The AAC department of public health joined recently as a member of ASPHER which will help sustain the results of the project through partnership with European academic and applied health organizations. Therefore, the process will continue, and the cooperation with the Associate Partners will enrich the AAC curriculum and contribute to the employability of graduates as well as their national and international recognition. |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Prof Zohar Mor MD MPH MHA |  | Prof. Zohar Mor is a graduate from Ben Gurion University, where he received his MD degree, and received his MPH and MHA from Tel Aviv University. He is a senior physician specialized in Public Health, and has fulfilled several positions in the Israeli Ministry of Health since 2003, including the head of the National department of tuberculosis and AIDS, the medical officer of Ramla county and currently the head of research in the Tel Aviv Department of Health. He is a senior lecturer from Tel Aviv School of Public Health and currently the head of the BA program at the Ashkelon Academic College. He teaches courses in epidemiology of infectious diseases, mother and child health, seminars in public health, computerized resources in health, Israeli health system, human sexuality and a course in TB and HIV. He is also the president of the European branch of the Union against Tuberculosis and the chair of the National League against Tuberculosis in Israel. His fields of research include infectious diseases, with a special focus in tuberculosis, HIV and sexually transmitted infections in disfranchised populations. He has published more than 70 scientific papers and chapters in books and associate editor in the BMC Public Health. |  |  |  |
| Dr Osnat Bashkin PhD |  | Senior Lecturer in the Department of Public Health, School of Health Sciences, since its founding in 2014 at AAC, Israel. Head of the teaching committee of the department of Public Health. BA in Behavioral Sciences from Ben-Gurion University (BGU) in 1999, and M.Sc. in Human Factors in Health from Ben-Gurion University in 2004. Ph.D. in 2009 in the field of human factors and patient safety in healthcare systems, at BGU, investigating human factors and organizational perspective in the safety of radiology units. From 2009 to 2012, worked as a researcher in the unit of clinical performance research at the Tel-Aviv Sourasky Medical Center, in Tel Aviv, investigated clinical and interpersonal skills of Interns, and evaluated clinical internship programs. Since 2011, worked with Professor Ted Tulchinsky to establish the first Israeli BA program in public health, at AAC. Served as academic coordinator and deputy head of the program. Teaches courses in research methods, psychology, quality assessment in healthcare, scientific writing, quality of healthcare services, and patient safety in healthcare, in addition to coordinating and guiding students in final year research projects (practikum). Initiator and head of AAC Smoke Free Campus since 2017. Recent Publications: Bashkin O. (2018). Patient Safety and the Significance of Human Factors Engineering Modality: A Review. COJ Nurse Healthcare. 3.(1) COJNH.000554.2018. DOI: 10.31031/COJNH.2018.03.000554 Bashkin O, Horne R, Peytremann Bridevaux I. (2018). The influence of health status on the association between diabetes and depression among adults in Europe: Findings from the SHARE international survey. Diabetes Spectrum. Vol 31(1), 75-82. Bashkin O. (2018). Depression among older adults with diabetes in Israel: Pattern of symptoms and risk factors. IMAJ. Vol 20(10), 222-226. Bashkin O, Tulchinsky T.H. (2017). Establishing undergraduate public health education: process, challenges and achievements in a case study in Israel. Public Health Reviews. Vol 38 (1),11. |  |  |  |

| Partner number ☒ | PIC 999975038 |  |  |  | P3 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | Hebrew University of Jerusalem – Braun School of Public Health (HUJI) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| Opened in 1925, The Hebrew University of Jerusalem (HUJI) is Israel’s premier university and leading research institution, ranked among the 100 leading universities in the world and first among Israeli universities. It offers a wide array of study opportunities in 7 faculties and 14 schools. HUJI researchers are awarded one-third of all competitive research grants in Israel, and among the top winners of the ERC's competitive grants. HUJI has some 900 faculty members, 2,000 administrative staff, and 23,000 Israeli and international students. The university is actively engaged in international research and teaching cooperation, with 320 joint project agreements with other universities in 44 countries and over 200 student exchange programs with 95 academic institutions in 24 countries, and numerous faculty-based exchange programs. The Braun School of Public Health and Community Medicine, an integral part of HUJI's Faculty of Medicine and the Hadassah University Hospital, is Israel's pioneer School of Public Health. The School, accredited by APHEA (2015), has a 55-year tradition of public health capacity-building locally and globally. The School strives to improve the physical, mental and social welfare of the global community, with a commitment towards excellence in multidisciplinary and interdisciplinary public health research, training and practice. The School has produced >1,000 Israeli graduates since 1961, and ~850 International MPH graduates from over 100 countries since 1971. The School offers graduate programs in Public Health (MPH), Health Administration (MHA), Clinical Epidemiology, Veterinary Public Health (MVPH) and doctoral-level training. Its unique International MPH program trains professionals mainly from lower-income countries, whose post-MPH careers span government, NGOs, academia and clinical practice. The international alumni program is considered an APHEA "best practice" for its communication network, mentoring and lifelong learning activities particularly in sub-Saharan Africa. The School hosts continuing-education workshops globally and in Jerusalem for international professionals (e.g., China, Moldova, Macedonia, Russia) on a wide range of public health topics. Training modules in epidemiology and bio-statistics for Israeli hospital clinicians and other professional groups are conducted regularly. As an ASPHER member, the School collaborates with universities and public health institutions within the European Region. |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?; 320. Number of students; 23,000. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles); No. |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP3: Co-Lead Mapping of the Competency Profiles of the Israeli Schools and Programmes of Public Health. Based on the preparatory work from WP2, HUJI will: - Map the competency profiles of the Israeli schools and programmes of public health using the ECCLPHP. - To develop the report – COMPETENCY PROFILES OF THE ISRAELI PUBLIC HEALTH SCHOOLS AND PROGRAMMES (with recommendations) (P4 & P3). WP1: Project Coordination – Participating WP2: Participating in deliverables WP4: Participating in deliverables contributing insights and lessons from preparatory work in WP3 to assist with development of the content of the PHI-EPHRF online tool. WP5: Participating in deliverables hosting an onsite Leadership and PBL training (peer) session. WP6: Support co-Leads and participate in deliverables taking part in IAMPH Campaign WP7: Dissemination - Participating WP8: Quality Plan & Evaluation - Participating |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| In addition to its standing as a global top 100 university at the forefront of international research, the Hebrew University is deeply involved with the local communities in Jerusalem, Israel and beyond. Serving the community and strengthening social systems that cross political, religious and socio-economic boundaries, is a value imparted to students irrespective of their formal studies. Students in health professions, particularly, as global citizens, should be exposed to medicine, health care systems and health outcomes in cultures and settings different than the ones they are familiar with, in order to make them more aware, culturally sensitive and resourceful and adaptable in their own settings, and should be aware of disparities on regional or geographical levels. "An effective public health workforce is central to the improvement of health and health system performance in all countries" (Beaglehole R, 2003), and it is the goal and responsibility of schools of public health to educate and train that workforce. This responsibility is reflected in the educational mission of the Braun SPH: educate and train public health and community medicine specialists at a high academic and professional level, so as to improve the physical, mental and social welfare of the population of Israel and elsewhere. Fostering harmonization across levels of Public Health training, and strengthening integration and exchange between SsPH within Israel, and between Israel and Europe, will help ensure that public health practitioners at all levels of training will be professionally and academically equipped to meet the local and national Public Health and health systems challenges in the coming decades. Cross-institutional and cross-border education and research, that will be generated through this initiative, will help highlight the centrality of Public Health in community development and the welfare of the nation and the region. We anticipate, that broad collaborations will serve as a stimulus to other disciplines to reach out to "competing" HEIs and strengthen international partnerships. |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  | As a result of harmonization and integration efforts, we anticipate that public health students will be better prepared to transition across the stages of academic training – from BA to Masters to PhD to post-doctoral training. This would result in a higher proportion of BA-Public Health graduates being accepted into master-level courses in the Braun SPH, a greater proportion of MPH, MHA, and MSc graduates under-taking a PhD, and PhD graduates applying for and being accepted into post-doctoral fellowship programs in Europe and elsewhere. [It is important to note that academic appointments in the Braun SPH are predicated upon, inter-alia, having undertaken post-doctoral level training in a highly recognized HEI abroad, so by expanding the number of fully-trained persons, we enhance the longer-term sustainability of a highly-qualified research and teaching staff at the Braun SPH.] We also anticipate an increase in the number of HUJI Public Health students who will undertake part of their studies in HEIs in Europe and elsewhere, and in the number of foreign students who enroll in master-level courses at the Braun SPH. In terms of research, we will use this collaborative platform to explore opportunities for joint research projects with partner HEIs in areas of mutual interest. |  |  |
| How will the impact of these results be measured in your HEI? |  |  | The Braun SPH maintains computerized records of all applicants into master-level programs, facilitating the monitoring of the number of accepted and rejected applicants from different BA programs in Israel and abroad. The Braun SPH maintains ongoing communication with its alumni in Israel and abroad, which will allows us to track the number of Braun alumni who engage in PhD and post-doc training in the Braun SPH, other SPH in Israel or abroad. HUJI actively encourages student-exchange programs with leading universities worldwide. These efforts are supported and carried out throught HUJI's Authority for Global Activities that maintains faculty-specific and program-specific records of HUJI students who study in other HEIs, and foreign students who come to study in HUJI. Finally, we anticipate that these efforts will lead to closer cooperation and interaction between the SPHs and Public Health academic programs within Israel with regard to curriculum development, admissions procedures and criteria, and inter-HEI Public Health training opportunities. |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  | The sustainability and monitoring of the achieved harmonization, integration and exchange results, will become integrated into the ongoing curriculum review processes at the Braun SPH, thereby requiring little in the way of human and other resources. |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Prof. Yehuda Neumark |  | Yehuda Neumark, PhD, MPH is Associate Professor of Epidemiology at the Hebrew University-Hadassah Braun School of Public Health and Community Medicine where he serves as School Director and former director of the school's International MPH Program. In this capacity, he also oversees an active global Alumni Program of more than 800 graduates from 102 countries mostly in low-income and transitional-income regions. As School director, he led the APHEA Evaluation Process of the Braun School which successfully concluded with APHEA Institutional Accreditation and Curricula Validation awarded in 2015. His research focuses primarily on the epidemiology of alcohol and drug use and misuse, and on the application of information and communication technologies for health promotion among young adults. This work is currently funded by grants from local and international funding agencies, and is reflected in over 60 peer-reviewed articles and book chapters. He reviews for numerous journals and funding agencies, and consults to the Israeli Parliament and other governmental-agencies on national alcohol and drug policy and strategy. He was a member of the executive board of the Association of Schools of Public Health in the European Region (ASPHER) in 2013-2016. His teaching responsibilities include courses in epidemiology, research methods, and community-health, and mentoring public health students and medical students at the bachelor, master and doctoral level. He has appeared on the list of Hebrew University's Excellence in Teaching annually since 2003, and was twice awarded the Faculty of Medicine Prize for Outstanding Lecturer. He is a guest-lecturer and consultant in many countries including Russia, Turkey, Macedonia, Kenya, South Africa and Nepal. His greatest self-proclaimed accomplishment and joy are his children and grandchildren. Publications relevant to public health capacity building: Neumark Y, Manor O, Berry EM (2011). Promoting Public Health in Developing and Transition Countries: The International MPH Program and other capacity-building activities at the Braun School of Public Health and Community Medicine, Hebrew University-Hadassah, Jerusalem, Israel. Public Health Reviews, 33:251-63. Neumark Y, Friedlander Y (2002) Training in Survey and Research Methods within a Master of Public Health Program. Public Health Reviews, 30:217-229. Epstein L, Gofin J, Gofin R, Neumark Y (2002) Three decades of service, research and training in community-oriented primary care; The Jerusalem experience. American Journal of Public Health, 92:1717-1720. |  |  |  |
| Dr. Maureen Malowany |  | Dr. Malowany brings experience in public health research training, developing competency-based curricula and evaluation to this project. With a PhD in History of Medicine (Africa) (McGill University) and a post-doctoral Masters in Health Sciences (London School of Hygiene and Tropical Medicine), Dr. Malowany combines research, teaching and administrative experience in public health in Africa and Europe. As Associate Director, Canadian Institutes for Health Research (CIHR-IHRC) Training Program (STIHR) in Transdisciplinary Public Health Research – McGill University and Public Health Department, Montreal, QC, Canada, Dr. Malowany reviewed fellowship applications annually for training in public health research (doctoral and post-doctoral). Dr. Malowany also designed the seminar program to train doctoral students and post-doctoral fellows from Quebec Universities and international institutions in public health research. Dr. Malowany participated in national committees on public health training and education, including the CPHA Competencies development sessions. In addition to teaching in history of medicine, Africa, and infectious diseases (Lecturer, Faculty of Modern History, University of Oxford), Dr. Malowany was also Visiting Lecturer to the LSHTM (2004-2014), lecturing on the history of malaria. Her public health field experience includes primary research in hospitals and institutes in East Africa, and volunteering with a team of Israeli nurses and doctors working in a dedicated HIV/AIDS clinic in Durban, KwaZulu Natal. As the public health member, Dr. Malowany contributed to the evaluation of this team’s training of KZN’s team on rapid-scale adult male circumcision. At the Braun School, Dr. Malowany teaches and advises international MPH students as IMPH Alumni Academic Coordinator and Lecturer. Dr. Malowany has organised international workshops in Jerusalem and in sub-Saharan Africa. With the Director of the Braun School, Dr. Malowany coordinated the accreditation process with APHEA in 2014-15 and consults on the Healthgrouper.org project on Health Workforce Migration from the Western Balkans (2014-present – manuscript in progress). Relevant publications: Gilles Paradis, Anne-Marie Hamelin, Maureen Malowany, Joseph Levy, Michel Rossignol, Pierre Bergeron, and Natalie Kishchuk (2017). The University–Public Health Partnership for Public Health Research Training in Quebec, Canada. American Journal of Public Health: 107(1):100-104. Virginia Berridge, Martin Gorsky & Alex Mold, eds, History and Health: Public Health, Policy and Practice, 1800-2000; London: Open University Press Understanding Public Health Series, Chapter 7: Case Study: Malaria, Maureen Malowany, Suzanne Taylor, July 2011. |  |  |  |

| Partner number ☒ | PIC 999975717 |  |  |  | P4 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | University College Cork (UCC) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| University College Cork (UCC) was established in 1845. Today there are 20,000 undergraduate and postgraduate students studying across the disciplinary spectrum. There is a strong institutional emphasis on teaching and learning, driven by the Centre for the Integration of Research, Teaching & Learning. Over 70% of academic staff possess qualifications in teaching and learning. The Department of Epidemiology & Public Health, was established de novo in 1997 and transitioned to a standalone School of Public Health (SPH) in October 2017. It is the only standalone School of Public Health in Ireland. In 2018 there were 21 academic, 7 administrative and 29 research staff working in the SPH. The SPH is a full member of ASPHER. The SPH offers an internationally unique and highly successful 4 year undergraduate BSc in Public Health, and two campus based Masters Programmes in Public Health and Occupational Health (IOSH accredited) respectively. In 2014/2015 it launched online programmes to deliver a PG Certificate in Health Protection, an MPH and a Masters in Occupational Health respectively. The SPH also has a well-established doctoral training programme in cardiovascular disease and suicide epidemiology, health services research, occupational health and applied public health research. Furthermore, the SPH provides substantial teaching inputs to medical undergraduates on a 5-year direct entry programme and a graduate entry to medicine programme, as well as making significant contributions to postgraduate and undergraduate degree programmes across the university faculties. The School of Public Health in UCC has a strong research profile. In the most recent UCC international peer reviewed, Research Quality Review exercise (2015) the Department of Epidemiology & Public Health (now SPH) was rated at level 5- “Research quality of leading international standard”. Senior staff in the SPH are acknowledged national leaders with international profiles in CVD and diabetes epidemiology, diet, physical activity and health, occupational health research, health services research, and suicide/self-harm epidemiology and prevention. (1995 characters no spaces) |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP3: Co-lead Mapping of the Competency Profiles of the Israeli Schools and Programmes of Public Health. Based on the preparatory work from WP2, UCC will: - Assist HUJI (P3) to map the competency profiles of the Israeli schools and programmes of public health using the ECCLPHP. - To develop the report with HUJI (P3) – COMPETENCY PROFILES OF THE ISRAELI PUBLIC HEALTH SCHOOLS AND PROGRAMMES (with recommendations) WP4: Support Co-Leads and participate in deliverables contributing insights and lessons from preparatory work in WP3 and language support to assist with development of the content of the PHI-EPHRF online tool. WP1: Project Coordination – Participating WP5: Participating in Leadership and PBL training (peer) session. WP7: Dissemination - Participating WP8: Quality Plan & Evaluation - Participating |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  |  |  |  |
| How will the impact of these results be measured in your HEI? |  |  |  |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  |  |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Professor Ivan Perry MD PhD |  | Professor Ivan Perry is a medical graduate from the National University of Ireland (NUI-Galway). He was subsequently awarded an MD from NUI-Galway, an MSc Epidemiology from the London School of Hygiene and Tropical Medicine (LSHTM) and PhD Epidemiology from the University of London. He is a member of the UK and Irish Faculties of Public Health and has completed specialist training in Public Health Medicine in the United Kingdom. He was appointed Professor of Public Health in the newly established Department of Epidemiology & Public Health in 1997 and over the past 20 years he has led the development of this flourishing, multi-disciplinary Department with a 4–year undergraduate BSc in Public Health, Masters Programmes in Public Health (MPH) and Occupational Health (MSc) and PhD programmes. Professor Perry has supervised over 20 MD’s and PhD’s He has recently led in the establishment of Ireland’s first online Masters in Public Health programme. He was previously, Senior Lecturer in Epidemiology/ Assistant Director of the UK Small Area Health Statistics Unit at Imperial College, London. He has over twenty five years’ experience of population health research including the design and analysis of major national studies, including the Cork and Kerry Diabetes and Heart Disease Study, the Cork Coronary Care Community based Case Control Study, the SLAN 2007 National Health and Lifestyle study and the 2010 Mitchelstown Cohort Study. He has over 270 PubMed listed publications with approximately 20,000 citations (Citation h-index of 64) and he has contributed chapters to international textbooks in Epidemiology, Hypertension and Cardiology. Professor Perry is the Foundation Director of Ireland’s National Self Harm Registry which is now recognised and promoted by WHO as providing a global template for surveillance and research on self-harm. In 2010 he was Co- principal investigator on UCC's successful application for major capital funding under the Programme for Research and Training in 3rd Level Institutions (PRTLI-5-€19.1M) for a project on “Translating Biosciences into Health”. He was the institutional lead for the “National Health Services Research Institute” component of this application. He is Principal Investigator on the HRB Centre for Health & Diet research which was established in 2008 and was awarded a renewal of funding in 2014. He was a co-Principal Investigator on the PhD Scholar Programme in Health Services Research funded by the Health Research Board in 2007. He was also a co-Principal investigator on SLAN-07 a national health and lifestyle survey. He was Principal investigator on the Safefood-funded study on Dietary salt intake and related risk factors in the Irish population (2010) and the Cost of overweight and obesity on the island of Ireland project. The major focus of his work over the past two decades has been on the development and the refinement of field survey methods appropriate for use in population health research in Ireland. He has considerable national and international experience as a peer reviewer with international journals and funding agencies, including the British Heart Foundation, the UK Medical Research Council and the Welcome Trust. |  |  |  |
| Dr Fiona MacLeod MBBS, BSc, MSc, MATLHE |  | Dr Fiona MacLeod qualified in medicine at Saint George’s Hospital Medical School, London. In 1995 she was awarded an MSc in Health Services Management from the London School of Hygiene and Tropical Medicine (LSHTM), and in 2014 an MA in Teaching and Learning for Higher Education from University College Cork (UCC). In 2013 she was appointed Teaching Fellow in the College of Medicine & Health, and in 2016 a Teaching Fellow in the Centre for the Integration of Research, Teaching & Learning (UCC). Fiona completed postgraduate training in clinical medicine and general practice in the UK, and has worked in Peru, Angola and the Former Yugoslav Republic of Macedonia. She joined the Department of Epidemiology & Public Health in UCC in 1998 and has accrued extensive teaching and supervision experience at both postgraduate and undergraduate level, including on the MPH and the direct entry and graduate entry medicine programmes. From 2007 to 2017 she led the strategic curricular development of the BSc Public Health, with responsibility for its implementation and evaluation, as well as providing teaching input in topics including determinants of health, health service delivery and public health practice. In 2017 she took up the role of Chair to the Teaching & Curriculum Committee of the newly established School of Public Health in UCC. Her current principal research interests are in the area of Teaching & Learning, with a particular focus on interdisciplinary learning environments, as well as learning outcomes and competencies in undergraduate public health degrees. Five relevant publications/presentations: MacLeod F. Career paths for graduates from an undergraduate public health programme in Ireland. EUPHA Conference 2018, Slovenia. (Presentation) MacLeod F & Beirne P. BSc Public Health in Ireland – the UCC Experience. RCPI Faculty of Public Health Medicine Summer Scientific Meeting, Dublin, 2016. (Poster) Macleod F. Disciplinary knowledge integration in 1st year students on the BSc Public Health & Health Promotion (BSc PHHP) in University College Cork (UCC). Annual Health Promotion Conference, NUIG, Galway, 2016. (Poster) MacLeod F. Evaluation of interdisciplinary learning in an undergraduate public health degree. EuroSoTL Conference, Cork 2015. (Poster) MacLeod F, Cronin M, Collins A. Moving Mountains to Develop Public Health Knowledge and Skills in Uganda and Ireland. IFGH: Global Health Workforce: Pathways to Health. RCSI, Dublin 2012. (Poster/Presentation) MacLeod F. An undergraduate public health learning environment exposed through the Teaching for Understanding (TfU) framework. Research Teaching Linkages: Practice & Policy, Proceedings of the 3rd Annual Conference NAIRTL. Ireland, 2010. Macleod F, Reilly M, Sheehan J, Codd M, Aziah Mat Nor N, Perry IJ. The Effectiveness of an Intensive Short Course in Teaching Epidemiology and Public Health to Medical Undergraduates. UCC Annual Research Day, Cork 2002. (Poster) |  |  |  |
| Dr Janas Harrington BSc, MPH, PhD |  | Dr Harrington is a Senior Lecturer in Public Health Nutrition, School of Public Health, University College Cork. She graduated with a BSc (Nutritional Science) in 1996, an MA (Health Promotion) in 1997, a PhD (Nutrition Epidemiology) in 2012 and a PG Certificate in Teaching and Learning in Higher Education in 2013. Between 2012 and 2015 she held the post of Health Promotion Pathway Co-ordinator on the Master of Public Health, UCC. Between 2015-2016 she was the Director of the online Master of Public Health, UCC. In Dec 2016 she was appointed as the Director for the BSc Public Health Sciences, UCC. She is a research-active public health nutritionist with expertise in dietary pattern analysis. Her specific expertise is in studying the determinants of healthy dietary patterns and the association between diet patterns and chronic disease, including cardiovascular risk and obesity. She has led successful grant applications as a PI and been a co-applicant and collaborator on grants worth a total of approx. €2 million including PI of one of the Irish consortia contributing to the EU JPI DEDIPAC Knowledge Hub (partner #214). She is currently a work package leader for a EU-fonde Policy Evaluation Network evaluating the effectiveness of existing policies for lifestyle interventions. The work will produce for the first time an Irish Food Environment Policy Index benchmarking the Irish food environments against international best practice. Additionally she is leading the evaluation of the implementation of the Irish obesity policy and action plan. She has considerable experience in teaching and curriculum design drawing on her research experience in Public Health Nutrition, Nutrition Epidemiology and Research Methods. Through her teaching and research she has a commitment to the increased visibility and impact of the School of Public Health, UCC, in the national and international fields of Public Health teachers and researchers. |  |  |  |
| Dr Frances Shiely, BA, PhD, MATLHE |  | Dr Frances Shiely qualified with a BA from the Faculty of Education at the University of Limerick in 1998 and obtained her PhD degree in Epidemiology in 2003. She was awarded a Masters in Teaching and Learning in Higher Education from UCC (2017) and recently a Postgraduate Certificate in Clinical Trials from The University of Edinburgh (2018). She was appointed as Lecturer in Epidemiology and Public Heath in UCC in 2005 and is currently a Senior Lecturer, jointly appointed to the School of Public Health and the HRB Clinical Research Facility. Frances is a member of the BSc Public Health Executive Committee which leads on curricular development and the implementation of the degree programme. She is also one of the core teaching faculty for the degree on which she has taught since her appointment in 2005. She has also taught on the MPH, Dental MPH, MSc Clinical Trials, MA Gerontology and the undergraduate medical programme. Her areas of expertise are epidemiology, clinical trials, quantitative data analysis, and public health data reports. She has supervised 4 PhD students to completion and is currently supervisor for 3 more. She has extensive experience supervising MPH and undergraduate projects. Frances has two main research interests: clinical trial methodology and physical activity and diet related research for the prevention of disease. She is co-PI and UCC lead on the HRB Trials Methodology Research Network. Relevant publications: Shiely F, MM McCarthy. The effect of small group tutors on student engagement in the computer laboratory lecture. Journal of the Scholarship of Teaching and Learning, 2018. Accepted. Awaiting page numbers. Davoren MP, D Dahly, F Shiely, IJ Perry. Alcohol consumption among University students: A latent class analysis. Drugs: Education Prevention and Policy, 2018;25(5): 422-430. Hurley C, CM Sinnott, M Clarke, PM Kearney, E Racine, JE Eustace, F Shiely. Perceived barriers and facilitators to Risk Based Monitoring in academic-led clinical trials: a mixed methods study. Trials 2017 18:423 DOI 10.1186/s13063-017-2148-4 |  |  |  |
| Dr Paul Beirne BDS, MDPH, PhD |  | Dr Paul Beirne qualified in Dentistry in 1989 and was awarded a Masters in Dental Public Health in 1999, before completing his doctorate in 2003. He has been a lecturer in the Department of Epidemiology & Public Health, UCC, since 2005. In this role he has been instrumental in the curricular development and implementation of the BSc Public Health, as well as providing extensive teaching input in the areas of epidemiology, critical appraisal and systematic reviews. Paul also teaches on other undergraduate programmes across the university faculties including undergraduate medicine. He supervises both undergraduate and postgraduate student theses. His principal research interest is in the area of systematic reviews of the effects of health care interventions. He is an active member of the Cochrane Collaboration and has conducted a number of Cochrane reviews. In 2004 he was appointed an Honorary Visiting Fellow at the UK Cochrane Centre. |  |  |  |

| Partner number ☒ | PIC 999897826 |  |  |  | P5 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | University of Haifa (UH) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| The school trains Masters, PhD, and Postdoctoral students in the fields of Health Promotion, Epidemiology, Community Health, Health Systems Policy and Administration, Health Systems Management, Occupational and Environmental Health, Nutrition and Biostatistics. The Masters degrees offered are Master of Public Health, Master of Applied Nutrition (MAN) and Master of Health Administration (MHA). The school also offers Master of Public Health with a Concentration in Mental Health Services, and runs an international MPH programme in Health Services Administration and Global Health Leadership. The student body reflects the regional makeup of the different ethnic/population groups. The school services the very diverse population in the northern region of Israel focusing on research and community cooperation that includes minorities and at risk population and lower socioeconomic status communities. There is a need for more internship and placement opportunities as part of the study programmes. Recently, the Haifa District of the Ministry of Health was recognized as an affiliated institution of UH. This affiliation will encourage research collaboration with the Mother and Child Healthcare Centres and other departments within the District Health Office. The school wishes to broaden collaboration with the healthcare sector such as the Health Maintenance Organizations where students will be able to participate in planning, implementing and evaluating interventions not only for the healthy community but also for patients groups. |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?; http://mous.haifa.ac.il/index.php/component/k2/itemlist/filter?moduleId=105&Itemid=130 398 agreements. Number of students; 17,500. Number of Bachelor degrees offered; 45. Number of Master degrees offered; 65. Number of PhD degrees offered; 50. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles); ABC 574610-EPP-1-2016-GE-EPPKA2-CBHE-JP DARE 561547-EPP-1-2015-1-IL-EPPKA2-CBHE-JP (2015-2951). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP4: Co-lead Workforce Adaptation and Employability in the Israeli PH System. Building on WPs 2 and 3, UH will: - Work with JU (P6) to develop and implement the PHI-EPHRF online tool to serve as a dynamic interface for education/training – practice/workforce collaboration; informing/enabling. - Organise an annual PHI Career Fair and Practical Placements Scheme for the Israeli PH system. WP1: Project Coordination – Participating WP2: Participating in deliverables WP3: Participating in deliverables WP5: Participating in deliverables hosting an onsite Leadership and PBL training (peer) session. WP6: Participating in deliverables taking part in IAMPH Campaign WP7: Dissemination - Participating WP8: Quality & Evaluation - Participating |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| HU collaborates with many organizations and intends to continue these activities and incorporate them into research and training as part of their programs. Examples of activities that are already in planning or implementation stages include: - A formal agreement to affiliate the Haifa District of the MoH. This cooperation includes professionals from the MoH teaching at the MPH programs, training MPH students at the various departments of the Haifa District and developing research projects. - Many students and faculty perform their research thesis projects within Mother and Child Healthcare Centers, enabling both research for improving the PH care services and research training for students The HU health promotion program is developing a practicum in health promotion as a course during the second year of the MPH program. HU made agreements with 5 organizations with senior staff in health promotion that can mentor students. Students perform various tasks in the organizations, such as develop evaluation projects for interventions, perform needs assessment of specific communities, etc. Students collaborate with field healthcare workers or community workers. We need to broaden the types of organizations and communities these organizations serve. HU has an international MPH program in which students are expected to do a practicum and a capstone project. All these courses need agreements with a range of organizations in the community. We are in the process of identifying additional organizations that will enable such cooperation. Moreover, HU sees importance in identifying collaborations that include Arab, minority and at risk and lower SES populations. Target population is the Northern part of Israel includes a very large population of Arabs, Ethiopian immigrants and other peripheral populations. These communities can benefit from incorporating students into projects run by the organizations and by supporting students in the development of new health promotion and public health intervention. HU would like to broaden collaborations with other sectors such Pharma and HMOs. HU has collaborations with the two larger HMO’s where students can participate in planning, implementing and evaluating interventions not only for the healthy community but also for patients groups. Problem based learning (PBL) is being incorporated into some courses and we would be interested in furthering our knowledge of how to do this in the best way possible. In addition, other types of learning are being tested and should be incorporated, such as the flipped classroom. |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  | Develop new sites (fields) for students to get experience and to develop their skills in public health and health promotion Develop new fields for research project for faculty and students Improve and develop courses provided for Masters and PhD students incorporating new teaching techniques Improve employability of our graduates in all programs provided at the school Improve collaboration with health organizations and community organizations and broaden our reach to these organizations |  |  |
| How will the impact of these results be measured in your HEI? |  |  | Increase the number of fields that students can train at by 30% Increase the number of organizations that are able to accept students to train within them by 20%. Increase the number of settings in which faculty and students perform research projects by 20% Increase the number of courses that incorporate new learning techniques by 30% Improve the satisfaction of students and faculty from the collaborations with the different organizations working with the school Improve student satisfaction from the skills they learnt during their studies |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  | When the project will end we will have a large number of agreements with various organizations and a large number of research projects running, these will continue to run as they will have proved to be win-win projects. Our faculty will continue to use the skills they acquired for teaching, including new techniques incorporated in courses and on-line courses |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Prof. Shira Zelber-Sagi |  | Prof. Shira Zelber-Sagi. Head of School of Public Health, Faculty of Social Welfare and Health Sciences, University of Haifa, Haifa, Israel Prof. Zelber-Sagi is a clinical dietitian, Epidemiologist and a researcher in nutritional epidemiology. Graduated BSc in nutrition sciences at the Hebrew University. Graduated a PhD in epidemiology and preventive medicine at the Sackler School of Medicine at Tel Aviv University. Currently, is an associate professor at the School of Public Health, Faculty of Social Welfare and Health Sciences, University of Haifa, head of the Nutrition, Health and Behavior program. Starting from October 2019, she is the Head of School of Public Health. She teaches nutritional epidemiology, advanced clinical nutrition, research methods, cardiovascular epidemiology, guidance for thesis writing. In addition, she currently mentors around 10 students doing their master thesis and another 6 PhD students. She works as a clinical dietitian at the liver Unit of the Tel-Aviv hospital. She is a member at the “National Committee for Nutrition, Gastroenterology and Liver Disease” and Head of the “Gastroenterology and Hepatology Nutrition forum” on behalf of The Israeli Nutrition Association. She is also a member at the EASL Policy and Public Health Committee and the United European Gastroenterology (UEG) Policy and Public Health Committee. Her research deals mainly with nutrition, lifestyle, and non-alcoholic fatty liver disease (NAFLD), colorectal polyps and other chronic diseases. |  |  |  |
| Prof. Orna Baron-Epel |  | Orna Baron-Epel, MPH, PhD. Prof. Baron-Epel has a BSc and PhD in Biology from the Tel Aviv University and a MPH from the Hebrew University in Jerusalem. Today she is a full professor and the former Head of the School of Public Health at the University of Haifa, the Faculty of Welfare and Health Sciences. She teaches public health, health promotion and planning, evaluating and implementing health promotion interventions. In addition she mentors around 10 students doing their master thesis and another 6 PhD students. Prof. Baron-Epel developed and run the department of health promotion in Macabbi Healthcare Services during the years 1988-1995 and then was in charge of publications at the Israel Center for Disease Control between 1995-2000. In 2000 she started teaching at the University of Haifa and developed the Health Promotion department at the School of Public Health of which she was one of the founders. Prof. Baron-Epel spent a sabbatical during the year 2007-8 at the University of California, Berkeley and at the San Diego State University during the year 20013-14. Her research interests include social epidemiology, health promotion, health behaviors, injury prevention and inequalities in health between Arabs and Jews. Her latest work includes areas such as discrimination, social support, social capital and their relation to health. She has published over 90 articles in leading public health, health promotion peer reviewed journals, edited a book on health promotion and serves as the editor to the Israeli Journal of Health promotion. |  |  |  |
| Prof. Manfred Green |  | Manfred Green, MD, PhD, MPH is currently the director of the Global Health Leadership and Administration MPH program at the SPH at the University of Haifa and previously served as head of the University of Haifa School of Public Health, where he is a professor in the Department of Epidemiology. He also serves as an adjunct professor at the University of Georgia College of Public Health in the United States. He received his medical degree at the University of Cape Town in South Africa, his MPH and PhD at the University of North Carolina, Chapel Hill, and his BSc in mathematical statistics at the University of Witwatersrand. He previously served as head of the public health branch for the Israel Defense Forces, as well as founding director of the Israel Center for Disease Control. Research interests: Emergencies resulting from infectious diseases, epidemiology of cancer, meta-analysis, evidence-based medicine, community intervention programs, leadership |  |  |  |
| Prof. Kerem Shuval |  | Prof. Anat Gesser-Edelsburg, PhD is an associate professor (tenure), the head of Health Promotion Program, School of Public Health, Faculty of Social Welfare and Health Sciences, and the Founding Director of the Health and Risk Communication Research Center at University of Haifa. During 2020 she will serve as a visiting scholar at the School of Public Health at the University of Illinois at Chicago, subsidized by the Jewish United Fund/Jewish Federation of Metropolitan Chicago and the UIC School of Public Health. Anat is Associate Editor of Disaster Medicine and Public Health Preparedness and BMC Public Health. Anat has won 28 research grants at a total amount of 4,000,000$, among them TellMe and ASSET, two EC funded research grants. Her most recent book Risk Communication and Infectious Diseases in an Age of Digital Media, was published on 2016 by Routledge Studies in Public Health. She has a BA (Summa Cum Laude) and PhD (With Distinction) both from the Faculty of the Arts, Tel-Aviv University. Anat has completed her postdoctoral research being awarded the Vidal Angel Postdoctoral Fellowship (a competitive grant) for Research against Hate and Bigotry at the Minerva Center for Human Rights, The Faculty of Law, The Hebrew University of Jerusalem. Her research focuses on health and risk communication, social marketing, the positive deviance approach, Entertainment-Education, evaluation of intervention programs, health promotion and persuasive communications. |  |  |  |

| Partner number ☒ | PIC 999642716 |  |  |  | P6 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | Jagiellonian University (JU) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| The Jagiellonian University, one of the oldest Universities in Europe (1364), combines tradition with the challenges of the modern world. In compliance with the principles of the Bologna Process, over 42,000 students study in 16 faculties on all three levels of study: Bachelor's, Master's, and Doctoral. It is one of the leading Polish scientific institutions, collaborating with major academic centres from across the world. Jagiellonian University Medical College is the leading Polish medical school taking pride in the excellent teaching staff. It consists of three faculties (Medicine, Pharmacy and Health Sciences) and employs over 2000 professionals, including about 1200 academic teachers and researchers. The Faculty of Health Sciences takes an interdisciplinary approach to the topic of public health, disease prevention, diagnosis, treatment, care and rehabilitation. The Faculty employs about 200 academic teachers and researchers. The Faculty of Health Sciences and particularly the Institute of Public Health has strong research and teaching infrastructure. The interests of the research and teaching staff of the Institute of Public Health (10 professors and 44 young researchers - PhD and Masters) focus on issues related to health care organisation and funding, health economics, administration and management, epidemiology, health promotion, community health, environmental health, nutrition, management and economics of medicines and medical devices, health technology assessment. The Institute offers the following educational programs for Polish-language students: bachelor and master degree program in Public Health; Bachelor in Organization and Economics of Health Care; postgraduate programs in Management of Health Care Units and Health Technology Assessment and Evidence-Based Medicine in Health Care Management, Hospital-based Health Technology Assessment. As part of the Faculty of Health Sciences, the Institute also participates in the training of PhD students. Since 2005 the Institute cooperates with the Health Systems and Policy Monitor, which is an innovative platform that provides a detailed description of health systems. Since 2015 the Institute is a member of EVIPNet, launched by WHO Europe in 2012, which is a global initiative that promotes the systematic use of health research evidence in policymaking. The Institute is involved in different international education programs (e.g. EuroPubHealth Master Program, Erasmus Mundus/Erasmus+, TransSenior [Marie-Curié]), and educational cooperation (e.g. Global Health Program at the University in Copenhagen and Public Health Bachelor Program at the University of Maastricht). From the beginning of its existence, the Institute is a member of ASPHER. The main project tasks on the side of JU will be carried out in the Department of Health Promotion and e-Health. The Department is involved in teaching and research activities combining modern perception of public health with a special focus on health promotion with the use of innovative information technologies. The e-health environment is treated as a space for the development of the effective public health interventions and monitoring of health behaviours and health risks of involved populations. The research topics carried out by the staff of the Department pertinent to SEEPHI project activities include the use of advanced IT support tools supporting decision making in public health and health care management. Furthermore, the use of standard vocabularies in health information systems is evaluated. |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP4: Co-lead Workforce Adaptation and Employability in the Israeli PH System. Building on WPs 2 and 3, JU will: - Work with UH (P5) to develop and implement the PHI EPHRF online tool to serve as a dynamic interface for education/training – practice/workforce collaboration; informing/enabling. - Assist (P5) to organise an annual PHI Career Fair and Practical Placements Scheme for the Israeli PH system. WP1: Project Coordination - Participating WP5: Participating in Leadership and PBL training (peer) session. WP7: Dissemination - Participating WP8: Quality & Evaluation - Participating |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  |  |  |  |
| How will the impact of these results be measured in your HEI? |  |  |  |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  |  |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Mariusz Duplaga PhD, prof UJ |  | Mariusz Duplaga is a medical doctor with speciality certifications in internal and respiratory medicine and completed training in public health, with PhD in medicine, a professor in health sciences, currently, the Head of the Department of Health Promotion and e-Health, Institute of Public Health, Jagiellonian University Medical College in Krakow. Author of teaching modules in health promotion, health education, telemedicine and e-health, Internet in public health, social marketing, assistive technologies, and health programmes. Research interests and activities include public health and health promotion, health and e-health literacy, medical informatics, e-inclusion, assistive technologies, telemedicine and e-health as well as innovative technologies in medicine. Author or co-author of at 120 full paper and 130 conference submissions. Extensive activities as a reviewer of call for proposals and ongoing projects within national research and development programs as well as consecutive EU framework programmes; cooperation with Ambient Assisted Living Association as a representative of National Centre of Research and Development in Poland, then as a reviewer of realised AAL project. Participation in national and international projects in the area of medicine and information technologies including AIANE (1993-1995, BIOMED II); Medical Data Management (1993-1995, USAID); Hospital Data Management (1996-1999, PHARE); Krakow Centre of Telemedicine (1999-2001, SCI-TECH II), BIOAIR (2000-2003, QoL,5FP), PRO-ACCESS (2002-2004, IST, 5FP), HEALTHWARE (2005-2008, Aerospace, 6FP), e-Health ERA (2005-2007, IST, 6FP), VECTOR (2006-2011, IST, 6FP), MATCH (2006-2008, IST, 6FP) and MPOWER (2006-2011, IST, 6FP), STRonGer (2011-2015 FP7-REGPOT) ProHealth 65+ (2015-2017, EU Health Programme). |  |  |  |
| Christoph Sowada PhD, prof UJ |  | Christoph Sowada is an economist and since 2000 academic teacher at the Institute of Public Health JU CM, and professor in health economics and economics of health insurance. He has worked at three universities in two European countries and supervised 40 completed Masters Theses. Since September 2016 Director of the Institute of Public Health. In 2008-2016 Deputy Director responsible for education and teaching programs, one of the authors of new bachelor and master programs in Public Health, coordinator (from begin) of the EuroPubHealth Master Program in Krakow. Author of nearly 100 scientific publications, member of different research teams in national and European programs, e.g. Phare ACE Programme (1997-2000), “An Integrated Analysis of Industrial Policies and Social Security Systems in Countries in Transition” (1998-2000), Leonardo da Vinci - Mobility: “Innovative teaching methods in Public Health” and “Improvement of employability of Public Health Professionals” (2000-2002), World Health Organization: “Health System Performance and Deficit Spending” (2006-2007), European Union: Prohealth 65+ Health Promotion and Prevention of Risk – Action for Seniors (2015-2017) Sowada C., Jurkiewicz-Świętek I. Management through goals setting – how to organize common study programs, in: Bielecka A. in., Erasmus Mundus. Poradnik Administratora wspólnych studiów, Warszawa: Fundacja Rozwoju Systemy Edukacji, 2012, s. 39-52 |  |  |  |
| Artur Romaszewski PhD |  | Artur Romaszewski is a lawyer and a graduate of the Institute of Public Health (formerly the School of Public Health) of the Jagiellonian University Medical College in Krakow. He received a doctorate in medical sciences from the Institute of Public Health of the JU MC. His research interests are focused on patient data protection. He is a co-author of several books regarding the health care information system and many papers on technological solutions on electronic medical records in the EU. He was involved in expert activities on behalf of the Institute of Public Health in the Standardisation Problem Commission for Healthcare Information Systems (at the Polish Committee for Standardization) and the National Association of Health Insurance Funds in work aimed at determining the necessary minimum scope of data collected by providers contracted by health insurance companies. Since 1998 he has been employed in the Institute of Public Health. For many years, he has lectured in PhD studies on data security and copyright law. He was a supervisor of many theses at the bachelor's, master and postgraduate programmes. |  |  |  |

| Partner number ☒ | 902105724 |  |  |  | P7 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | Israeli Association of Public Health Physicians (IAPHP) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| The goals of the Association of Public Health Physicians in Israel are: serve as the official professional and scientific association of public health physicians in Israel; promote and develop the scientific, administrative, clinical, social, educational and ethical aspects of public health, in cooperation with the Israeli Medical Association; advance the professional standing of public health physicians within the Israeli Medical Association and among government agencies, medical colleagues and the public; serve as an official source for comprehensive professional consultation on the development and organization of health services in Israel; influence and affect the development and implementation of public health policy in Israel in accordance with "Health for All" principles, and to promote awareness to prioritization in resource allocation for public health; facilitate partnerships, processes and actions affecting public health; advance the professionalism of Israeli public health physicians; oversee the training of physicians in public health; collaborate, nationally and internationally, with organizations and individuals that share similar goals of public health promotion; advance the conduct of scientific public health research, and to support the dissemination of research findings among public health colleagues, policy makers and the general public. |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP6: Co-lead Stakeholder Engagement. To engage with stakeholders, IAPHP will: - Work with RCUC (P8) to devise the IAMPH campaign for the Israeli PH system. - Pilot the IAMPH campaign IAMPH Campaign Stories and in the context of the IAPHP conferences (2022 & 2023) with IAMPH Happenings. - Set up the PHI Register. WP7: Co-Lead Dissemination and Exploitation. To disseminate project results, IAPHP will: - Organize 2 dissemination workshops at the IAPHP Conferences 2022-23. WP1: Project Coordination – Participating WP2: Participating in deliverables WP3: Participating in deliverables WP4: Participating in deliverables WP5: Participating in deliverables hosting an onsite Leadership and PBL training (peer) session. WP8: Quality & Evaluation - Participating |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| IAPHP, which is Israel’s primary PH association for all PH professionals (not only physicians) will carry out stakeholder engagement activities with wider PHW through IAMPH Stories and Happenings, including nurses, dental hygienists, pharmacists, etc. so they may recognise their role within PH and for population health. Regiatration as PH profeesionals and Development of training opportunities and CPD in PH for these associated professions will be encouraged and IAPHP will develop a PHI Register while advocating for the need to participate in PH training to enhance career opportunities and benefit the health of the population. IAPHP, which is part of the greater Israeli Medical Association (IMA) maintains contact with stakeholders throughout the health system and will advocate to employers on the benefits of employing PH graduates and developing internship and placement opportunities. IAPHP has close contacts with policymakers and will advocate for national and local policies to strengthen the PHW. Through these efforts IAPHP will bring the reach of the project to a wider variety of stakeholders in Israel beyond the participating HEIs. |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  | Student participation in policy papers/conferences on topics such as Smoking, Food fortification, Fluoridation, Water safety, Road safety, Vaccinations, etc. Promotion of political response to public health and PHW issues, promoting the concept of politics as social determinant of health. Valorisation, recognition, and professionalisation of the core and wider PHW and the roles they play in population health. |  |  |
| How will the impact of these results be measured in your HEI? |  |  | Numbers participating and interest in presentations at planned conferences. Readership/accession of published articles and papers. Changes in PH and PHW policy at national and local levels in Israel. |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  | Volunteer professional input into cross disciplinary, multi-organizational working groups to promote public policy for the PHW and in the tradition of Health in All Policies widely accepted in Europe. |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Dr. Hagai Levine MD MPH Chair |  | Hagai Levine, MD, MPH, is an epidemiologist and public health physician. He is a Senior Lecturer and Head, Environmental Health Track, Braun School of Public Health and Community Medicine at the Hebrew University-Hadassah Faculty of Medicine. He teaches on environmental health, epidemiology, health policy, public health, health promotion, anc control of communicable diseases. Dr. Levine served as Head, Epidemiology Section, Army Health Branch (2009-2011) and as Public Health Officer at the Public Health Services of the Ministry of Health, Israel (2007-2008). He was a visiting professor at Department of Public Health, Icahn Faculty of Medicine, Mount Sinai, New York (2014-2015) and he currently holds an adjunct position there. His current research deals with health policy; tobacco control; Environmental Health; Reproductive Epidemiology; Communicable Diseases and Public Health. Dr. Levine serves on several committees and boards, among them: Coordinator, Israel National Verification Committee for Measles and Rubella Elimination; Executive Board, Israel Society of Ecology and Environmental Sciences; Advisor, Israel Cancer Association; Israeli Health Impact Assessment Working Group; He authored or co-authored over 80 papers and book chapters, and published his work in leading medical and health policy journals, such as the New England Journal of Medicine, Vaccine, Human Reproduction Update, American Journal of Epidemiology, Diabetes Care, American Journal of Public Health. |  |  |  |

| Partner number ☒ | 945995314 |  |  |  | P8 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | The Swedish Red Cross University College (SRCUC) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| The Swedish Red Cross University College (SRCUC) has trained nurses since 1867. The SRCUC (formerly the Red Cross School of Nursing) was founded in 1867 by Emmy Rappe and was the first secular nursing education in Sweden. Since the start, the school has given nursing students the competence and skills required for global nursing needs and, contributed to the development of the Swedish healthcare system. The SRCUC, that offers a bachelor program in nursing as well as specialist education in nursing, has a specific focus on public health within its program. The SRCUC was previously located at the campus of the Royal Institute of Technology (KTH), central Stockholm. In 2016, the SRCUC was relocated in a new and modern building to one of the largest medical campus in Sweden (Flemingsberg campus). This move provides the students with a stimulating professional and pedagogical atmosphere. We offer an inclusive learning environment where a Student Council, involved in the promotion and development of education, represents student interests. At present, the SRCUC has more than 60 employees and around 650 students. We are in collaboration with many Erasmus exchange programs within the European Community such as France, Great Britain, Spain and other countries. We are also active with students/teachers exchange programs outside the European Union such as Japan, Tanzania, Ghana, Columbia etc. We have a close research collaboration with the Swedish Red Cross, Karolinska Institutet and Stockholm University as well as other university nationally and internationally. |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP6: Co-lead Stakeholder Engagement. To engage with stakeholders, SRCUC will: - Work with IAPHP (P7) to devise the IAMPH campaign. - Assist with IAPHP (P7) to set up the PHW register in Israel. WP1: Project Coordination - Participating WP5: Participating in Leadership and PBL training (peer) session. WP7: Dissemination - Participating WP8: Quality & Evaluation - Participating |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  |  |  |  |
| How will the impact of these results be measured in your HEI? |  |  |  |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  |  |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Leah Okenwa-Emegwa |  | Dr. Leah Okenwa-Emegwa is a senior lecturer in public health science at the Swedish Red Cross University College. She holds both masters and PhD degrees in public health sciences obtained 2006 and 2011 respectively from Karolinska Institutet, Stockholm. In addition to diverse roles in administration and education within public health, she has acted as committee member for course content review, been involved in the development of a new bachelors program in public health at the University of Gävle, Sweden and as expert reviewer for applications for scholarship within public health education. Dr. Okenwa-Emegwa’s teaching experience includes undergraduate and post graduate levels in different learning environments such as online/distance and on- campus education. She has also completed many courses related teaching and learning in higher education. At the international front, she was member of a committee for internationalization, charged with developing guidelines and action plan for strategic internationalization. She has close contact and collaborations that include course development with Erasmus partners such as the University of Applied Science, Paderborn in Germany. In 2014 she was a Linnaeus-Palme exchange faculty to the department of public health at Tata institute, India. She has been involved in discussions regarding sustainable development in higher institutions and strategies to achieve set goals. Being a licensed clinical optometrist, her earlier work has included community based eye care in developing country context. Other previous activities include advocacy, planning, implementation and coordination of community based health care and HIV/AIDS prevention programs in rural communities of West Africa in collaboration with UNICEF. She has also been involved in planning and development of teaching aids and curriculum for occupational and community eye health. Research activity cuts across injury epidemiology, violence, occupational health. |  |  |  |
| Stéphanie Paillard Borg Associate Professor |  | Stéphanie Paillard-Borg, Ms, PhD, is an epidemiologist and psychologist, senior lecturer in public health as well as Deputy Head in public health discipline at the SRCUC. Her international background within psychology and mental health, journalism and epidemiology motivate her current research curiosity to study the epidemiological transition from different cultural contexts, geographical angles and historical standpoints about countries such as Ghana, Japan, Switzerland, Sweden. The global demographic and epidemiological patterns are changing rapidly as we go through the twenty-first century. It is largely characterized by overall low birth and death rates globally. This well-known fact is associated with population growth at least for the next 50 years. Consequently, the current global epidemiological transition, represented by change in disease patterns, affects expected life expectancies and survival rates, and is related to an overall change in social organizations and structures. Her main scientific interest is to concentrate on these intertwined, global and rapid demographic, social, economic and political developments from a public health perspective. Her research has recently focused on the global feminization of migration and its consequences, and how these changes affect women's lives. Her ongoing project "Analytical Journalistic Approach to Public Health Research" combines aspects of investigative journalism and explanatory reporting. The project is a combined scientific and journalistic aspiration to hear women's "voices" globally about important issues where they play key roles. This approach aims at giving meaning to complex public health problems in order to promote an enhanced understanding. Projects seek different answers to the growing complexity of a globalized world and its information overflow. Here is a list of selected articles since 2016: Xu, W., Zhang, H., Paillard-Borg, S., Zhu, H., Qi, X. & Rizzuto, D. (2016).Prevalence of Overweight and Obesity among Chinese Adults: Role of Adiposity Indicators and Age. Obesity Facts, 9, 17-28. Paillard-Borg, S. & Holmgren, J. (2016). Immigration, Women, and Japan - A Leap Ahead and a Step Behind: A Qualitative Journalistic Approach. SAGE Open, 6(4), 1–7. Song, F., Bao, C., Deng, M., Xu, H., Fan, M., Paillard-Borg, S., Xu, W. & Qi X. (2016).The prevalence and determinants of hypothyroidism in hospitalized patients with type 2 diabetes mellitus. Endocrine, 55(1), 179-185. Zhang, H., Deng, M., Xu, H., Wang, H., Song, F., Bao, C., Paillard-Borg, S., Xu, W. & Qi, X. (2016). Pre- and undiagnosed-hypertension in urban Chinese adults: a population-based cross-sectional study. Journal of human hypertension, 31(4), 1-7. Zhang, H., Xu, H., Song, F., Xu, W., Paillard-Borg, S. & Qi, X. (2017). Relation of socioeconomic status to overweight and obesity: a large population-based study of Chinese adults. Annals of human biology, 44(6), 495-501. Emegwa Okenwa L., Paillard-Borg, S., Tinghög, P., Saboonchi, F. & von Strauss, E. (2017). A global workspace is the emerging reality for future public health workforce reality for future public health workforce. Socialmedicinsk tidskrift, 94(3), 318-326. Emegwa Okenwa, L., Paillard-Borg S., Tinghög, P., Saboonchi, F., & von Strauss, E. (2017). Framtidens folkhälsovetare verkar på en global arena. Socialmedicinsk tidskrift, 94(3), 318-326. Eva von Strauss, E., Paillard-Borg, S., Holmgren, J. & Saaristo. S. (2017). Global nursing in an Ebola viral haemorrhagic fever outbreak: before, during and after deployment. Global health action, 10(1), 1371427. Paillard-Borg, S., & Halberg, D. (2018). The other side of the mirror: an analytic journalistic approach to the subjective well-being of Filipino migrant women in Japan? Sage Open, 8(1), 1-10. Paillard-Borg, S., Holmgren, J., Saaristo. S. & Eva von Strauss, E. Nurses in an Ebola viral haemorrhagic fever outbreak: Facing and preparing for psychosocial challenges. (Submitted). |  |  |  |

| Partner number ☒ | 999846222 |  |  |  | P9 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | Ben-Gurion University of the Negev (BGU) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| BGU was established in 1969 with the mission of fulfilling the vision of Israel's first prime-minister, David Ben-Gurion, of making the desert bloom with agriculture, science, technology & innovation. BGU is a comprehensive university engaged in research across the entire spectrum of human intellectual endeavour. It is comprised of the Faculties of Natural Sciences, Social Sciences and Humanities, Engineering Sciences, Health Sciences, Business and Management, and the Institute of Desert Research. BGU has about 20,000 students, of which 35% are graduate students (master & PhD). BGU has five campuses: (a) three in Beer-Sheva including the Faculty of Health Sciences Campus (next to Soroka Medical Center) (b) one in Sede Boqer, which includes international Desert Research Centers and the Institute for the Study of Israel and Zionism, and (c) the University’s newest campus in Eilat, established in 2003. As an institution with graduate studies in public health, epidemiology, biostatistics, health policy and management, sociology of health, gerontology and health disaster management, BGU has the potential with a comprehensive learning experience that combines theory and practice to absorb students from undergraduate public health studies, as well as from medicine and allied health professions, with a strong focus on community health, minorities health and dealing with health inequities in the periphery. BGU has approximately 850 senior academic staff who initiate, lead and implement research projects with institutions, companies and foundations worldwide, in addition to maintaining a strong commitment to innovative teaching and research excellence. BGU has major interdisciplinary research centers and institutes which explore new ideas and conduct revolutionary research that has a local and global impact. BGU has participated in many international projects including Tempus, Erasmus (mobility and capacity building). During the past academic year BGU has received funding for about 30 Erasmus+ mobility agreements which represent our commitment to internationalization. |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?; 440. Number of students; 20,000. Number of Bachelor degrees offered; 66. Number of Master degrees offered; 69. Number of PhD degrees offered; 46. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles); 585583-EPP-1-2017-1-IL-EPPKA2-CBHE-JP Developing Modernized Curricula on Immigrant's and Refugee's Lives – DEMO.IL 597904-EPP-1-2018-1-IL-EPPKA2-CBHE-JP Welcome in Israel as a Leading and Learning tool for IaH Assistance and Management - WILLIAM. |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP5: Co-lead Building Leadership Capacity in the Israeli PH System. BGU will: - work with UM (P10 ) to develop the PHI Leadership Academy Train-the-trainer Manual with leadership training modalities. - carry out the peer session pilots across Israel organizing Leadership and PBL training sessions for each Israeli Partner (P2, P3, P5, P7, P9). - work with UM (P10) to evaluate and adapt the train-the-trainer manual and peer session scenarios based on feedback received, followed by organizing the 6th and final peer session in P9. WP1: Project Coordination – Participating WP2: Participating in deliverables WP3: Participating in deliverables WP4: Participating in deliverables. WP6: Participating in deliverables taking part in IAMPH Campaign WP7: Dissemination - Participating WP8: Quality & Evaluation - Participating |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| BGU is establishing a PHI Leadership Academy as an addition to the already established BGU School of Management programme in Social Leadership. This is launched as a joint project between BGU and Mandel foundation, focused on research and models related to PH leadership. The Leadership Academy will serve as the core structure to host and launch the train the trainer and Peer activities for training in problem based learning and leadership education, training and evaluation methodologies. This will create a cadre of trainers and faculty with the capacity to maintain trainings in Israel and incorporate the methodologies into courses and curricula at their home HEI. Other related activities BGU will engage in to strengthen ties with employers and the broader community include : Participation in launching a preparatory course in 2019 for Bedouin students in preparation for enrolment in health, education and other programmes (see description, section D.3). Active efforts to engage with local employers and communities in the peripheral Negev desert region to strengthen opportunities for practical student placements, practice-based theses and employment opportunities. Efforts to increase leadership and practical training methods in course curricula to meet employer needs, including development of a leadership oriented degree track for Master students. |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  | - New leadership courses, integrated in the BGU public health education program, tailored for the current public health challenges, on local, national and international levels. - Leadership oriented research, knowledge-share and practical health leadership projects with actors from both local health institutions (hospital and community) and other Associate Partners. - Leadership oriented academic track will be established in our master programs. - Improved employability of MPH and MHA graduates through wider leadership practicum fields offered by other health institutes and Associate Partners. - Extension of leadership public health exposure /education in other health academic programs in BGU Departments and Associate Partners |  |  |
| How will the impact of these results be measured in your HEI? |  |  | Leadership oriented courses will be implemented in at least 20% of the public health education program at BGU. - Produce about 10 joint leadership oriented research projects with health institutes and other Associate Partners. - Produce at least once a year a health leadership project implemented in the surrounding community, through collaboration of BGU with Associate Partners. - Produce at least once a year a joint learning leadership workshop, conference or seminar, with hospitals/health facilities and other Associate Partners. - Monitor the rate of application to each of the specialized academic tracks. - At least 20% of students will perform their practicum/research project that will include leadership components. - Minimum of 2 lecturers exchange visits to prepare future students collaboration. |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  | When the project will end, we have a core of skilled academic staff in the School of Public Health that can continue the process of integrating leadership in our curriculum. Collaborations with other Associate Partners will be sustained after the project is ended by adoption of a continuing process of implementation: The key people at our affiliated health institutions (Soroka, Barzilai and Assuta hospitals as well as health funds) as well as the Faculty of Management will already be incorporated during the continuing development of the public health program; some of them will join the school of public health staff as adjunct lecturers after the project budget will be finished. BGU will provide financial support facilities to sustain partnership with Associate Partners and will seek further domestic and international research funding to continue and expand research and cooperation in public health related topics with a strong focus on leadership and with the support of the Mandel Foundation. The BGU School of Public Health is planed to join soon (this coming May) as a member of ASPHER which will help sustain the results of the project through partnership with European academic and applied health organizations. Therefore, the process will continue, and the cooperation with the Associate Partners will enrich the BGU curriculum and contribute to the employability of graduates as well as their national and international recognition. |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Prof. Nadav Davidovitch |  | Nadav Davidovitch, MD, MPH, PhD is an epidemiologist and public health physician. He is a Full Professor and Director, School of Public Health at the Faculty of Health Sciences and the Guilford-Glaser Faculty of Business and Management at Ben-Gurion University of the Negev in Israel. He teaches on health policy, public health, health promotion, the Israeli healthcare system, public health ethics, and global health. Prof. Davidovitch served as Head, Epidemiology Section, Israel Defence Forces Health Branch (2003- 2005) and as Public Health Officer at the Central District, Public Health Services, Ministry of Health, Israel (2007-2008). He was a Fulbright visiting professor at Department of Sociomedical Sciences, School of Public Health, Columbia University (2005-2006) and a visiting professor at the School of Public Health, University of Illinois – Chicago (2008 and 2016). His current research deals with health policy; health inequities; health and immigration; vaccination policy; environmental health and public health ethics. Prof. Davidovitch serves on several international and national committees, among them: Executive Committee, European Public Health Association; Head of Middle East Chapter, International Society for Environmental Epidemiology; Israel national advisory committee for health promotion; joint committee on environmental health (Israel Ministry of Health and Ministry for the Protection of the Environment); Israeli Committee for the implementation of the Clean Air Act; Israeli Health Impact Assessment Working Group. He authored or co-authored over 120 papers and book chapters, co-edited 5 volumes and books and published his work in leading medical and health policy journals, such as the New England Journal of Medicine, Clinical Infectious Diseases, Emerging Infectious Diseases, Journal of Pediatrics, Vaccine, Social Science and Medicine, and Law & Contemporary Problems. Prof. Davidovitch is in the process of developing an online teaching platform with Drexel University School of Public Health, in order to have a shared classroom dealing with global health. |  |  |  |
| Prof. Dan Greenberg |  | Dan Greenberg is a Full Professor and Chairman of the Department of Health Systems Management at the Faculty of Health Sciences and the Guilford-Glaser Faculty of Business and Management at Ben-Gurion University of the Negev in Israel, where he teaches on comparative healthcare systems, health technology assessment, and economic evaluation of technologies in healthcare. Since 2008, he is also affiliated with the Center for the Evaluation of Value and Risk in Health (CEVR) at The Institute for Clinical Research and Health Policy Studies at Tufts Medical Center, Boston, MA, and is an adjunct faculty at the Tufts University School of Medicine. Prof. Greenberg is a co-founder and the former President of the Israeli Society for Pharmacoeconomics and Outcomes Research (ISPOR-Israel), and is currently coeditor of Value in Health, the official journal of ISPOR. He developed an online course in health systems around the world, and has experience with online teaching. |  |  |  |
| Dr. Keren Dopelt |  | Keren Dopelt is a senior lecturer at Ashkelon Academic College and Research Associate at Ben Gurion University School of Public Health and the Center for Health Policy Research in the Negev. Her main research interests are Sociology of health, Health promotion, Evaluation, Quality measures, Health policy, Health Disparities and Quantitative Research Methodologies. She received her B.A. in Sociology and Anthropology (Magna cum Laude), MA and PhD in Sociology of Health (MA Thesis Title: Health Risk Behavior among Latchkey Children as a Function of Family, PhD Thesis Title: Psycho-Social Predictors of Involvement in Bullying among Israeli School Students) at Bar Ilan University. She did her Post-doctorate at Ben Gurion University of the Negev - Department of Health Systems Management, conducting research on national quality measures for infants and toddlers preventive health services. Dr. Dopelt also worked in the Ministry of Health, as responsible for health promotion in the Central Health District. She has vast experience in implementing and evaluating health promotion programs in the community with a strong focus on reducing health inequalities. She is the co-founder of the Mitzpe Ramon Conference for Health Equity in the Negev. |  |  |  |

| Partner number ☒ | 999975911 |  |  |  | P10 |
| --- | --- | --- | --- | --- | --- |
| Organisation name & acronym | Maastricht University (UM) |  |  |  |  |
| F.3.1 - Aims and activities of the organisation Please provide a short presentation of your organisation (key activities, affiliations, size of the organisation, etc.) relating to the area covered by the project (limit 2000 characters). |  |  |  |  |  |
| Maastricht University (UM) was founded in 1976, which makes it the youngest Dutch university. The UM is situated in the very south of the Netherlands with close borders to Belgium and Germany and in a geographically central position in Western Europe. Maastricht University’s research and educational activities are focused on issues related to the development of society: Life Sciences, Innovation and Governance. Research at the UM is often undertaken by multidisciplinary teams working on relevant social themes, in close collaboration with international institutes, business and industries. The Faculty of Health, Medicine and Life Sciences (FHML) targets high-quality multidisciplinary research and education in European Public Health, Health Sciences, Life Sciences and Medicine. All FHML educational programmes are rooted in externally recognised research programmes. Maastricht University stands out for its innovative approach to learning using the problem-based methodology and international outlook. With 16,800 students and 4,400 staff, UM offers unique international-oriented programmes taught in English. Slightly over 50% of students, 40% of the academic staff and 10% of the support staff is international, and international themes are deeply rooted in research and education. The Department of International Health (IntHealth) is a young department founded in the year 2008 as the former Faculty of Health Sciences (now FHML) realized the need for a European orientation in health research. A key feature of IntHealth is a provision of education and research in line with the European dimension and vision of health. The department is active in provision of a very successful Bachelor of European Public Health programme and Master of Governance and Leadership in European Public Health. FHML is a member of the Association of the Schools of Public health in European Region (ASPHER) and actively participates in the knowledge and good practice sharing at the international level with respect to educational curricula, educational methodologies and quality assurance. |  |  |  |  |  |
| Only for Partner Country institutions, please provide information on: Number of Memoranda of Cooperation/Understanding the HEI has signed with HEIs outside their own country?. Number of students. Number of Bachelor degrees offered. Number of Master degrees offered. Number of PhD degrees offered. Have you participated in CBHE? If yes, list CBHE projects titles and reference numbers. Describe curricular/ courses developed/ modernised, if any (name of the subject area and courses titles). |
| F.3.2 – Role of your organisation in the project Please describe also the role of your organisation in the project (limit 1000 characters). |  |  |  |  |  |
| WP5: Co-lead WP5: Building Leadership Capacity in the Israeli PH System. UM will: - work with BGU (P9) to develop the PHI Leadership Academy Train-the-trainer Manual with leadership training modalities. - support BGU (P9) to carry out the peer session pilots across Israel organizing Leadership and PBL training sessions for each Israeli Partner (P2, P3, P5, P7, P9). - work with BGU (P9) to evaluate and adapt the train-the-trainer manual and peer session scenarios based on feedback received, followed by the 6th and final peer session in P9 organized by BGU. WP1: Project Coordination – Participating WP7: Dissemination - Participating WP8: Quality & Evaluation - Participating |  |  |  |  |  |
| F.3.3 – Curriculum development project (only for Partner Country institutions) Please fill in if you are applying for a curriculum development project |  |  |  |  |  |
| Please confirm that no similar curricula/ courses/modules were developed/modernised in Tempus IV projects in this HEI. |  |  |  | Choose an item. |  |
| For new courses |  |  |  |  |  |
| What new courses will the project implement in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. Estimated starting date of the new programme. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| For updated courses |  |  |  |  |  |
| Which existing courses will be updated in your HEI? |  |  |  |  |  |
| For each course please fill the following nested table: |  |  |  |  |  |
| Title. Level of study. List of subjects and credits (ECTS or comparable credit system) for each of them. Estimated date of accreditation and accreditation body. % of the modernised subjects compared to total subjects included in the course. Number of students to be accepted in the first year/ second year. Number of teaching staff to be trained. Internship /placements ( if applicable ). List of equipment to be purchased for this course? ( if applicable). Please copy and paste nested tables as necessary |
| F.3.4 – Modernisation of governance, management and functioning of HEIs ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| Provide information on ( if applicable) |  |  |  |  |  |
| List the number of existing centres/networks in your HEI |  |  |  |  |  |
| Is the centre to be created a new one or an update? |  |  |  |  |  |
| If new, why is a new centre necessary? If updated, why is an updated centre necessary? |  |  |  |  |  |
| Where will the centre be located in the institution? |  |  |  |  |  |
| Will this infrastructure be made available to the centre after the project ends? |  |  |  |  |  |
| How many people will be employed in the centre? |  |  |  |  |  |
| Will the institution fund these posts after the project ends? |  |  |  |  |  |
| How many administrative staff will be trained? |  |  |  |  |  |
| Which procedures will be updated /introduced in the institution? |  |  |  |  |  |
| F.3.5 – Strengthening of relations between HEIs and the wider economic and social environment ( only for Partner Country institutions) Please fill in if you are applying for this type of project and define clear the activities to be held in your institution (limit 2000 characters) |  |  |  |  |  |
| F.3.6 – Expected results and impact ( only for Partner Country institutions) |  |  |  |  |  |
| What are the expected tangible results from the project in your HEI? |  |  |  |  |  |
| How will the impact of these results be measured in your HEI? |  |  |  |  |  |
| What financial means and human and other resources will be provided to sustain these results after the project ends? |  |  |  |  |  |
| F.3.7 - Operational capacity: Skills and expertise of key staff involved in the project Please add lines as necessary. |  |  |  |  |  |
| Name of staff member |  | Summary of relevant skills and experience, including where relevant a list of recent publications related to the domain of the project. |  |  |  |
| Katarzyna Czabanowska |  | Katarzyna Czabanowska, Associate Professor at the International Health Department, Maastricht University, the Netherlands. She directs Governance and Leadership in European Public Health Master programme and coordinates the Research Methods trajectory at the Bachelor of European Public Health programme at Maastricht. She has developed the skills trajectory for the European Public Health Bachelor and has supervised Bachelor thesis since 2009 at Maastricht University. She is an educational innovator introducing modern technologies and blended learning into the educational programmes. Her research focus is on public health workforce development in Europe, European public health leadership, and competence-based education. Her research is reflected in many publications including articles published in peer reviewed journals, books, book chapters. She holds honorary positions at the Jagiellonian University Medical College, Krakow, Poland, the University of Sheffield, UK and the IU Richard M. Fairbanks School of Public Health, Indiana, US. She is a President elect of the Association of the Schools of Public Health in the European region (ASPHER), President of the European Public Health Association (EUPHA) Working Group on Public Health Leadership and a winner of the Polish Person 2015 in the Netherlands in the category Science and Technique. Related publications: Katarzyna Czabanowska. Public health competencies: prioritization and leadership. European Journal of Public Health, 2016. Katarzyna Czabanowska, André Malho, Peter Schröder-Bäck, Daniela Popa and Genc Burazeri. Do we develop public health leaders? Association between public health competencies and emotional intelligence: a cross-sectional study. BMC Medical Education, 2014. Vesna Bjegovic-Mikanovic, Aleksandra Jovic-Vranes,Katarzyna Czabanowska and Robert Otok. Education for public health in Europe and its global outreach. Global Health Action, 2014. Ingrid A. E. Spanjers, Karen D. Könings, Jimmie Leppink, Daniëlle M. L. Verstegen, Nynke de Jong, Katarzyna Czabanowska and Jeroen J. G. Van Merriënboer. The promised land of blended learning: Quizzes as a moderator. Educational Research Review, 2015. Katarzyna Czabanowska, Kenneth A. Rethmeier, George Lueddeke, Tony Smith, André Malho, Robert Otok, Mindaugas, Stankunas. Public Health in the 21st Century: “Working Differently Means Leading and Learning Differently” (A qualitative study based on interviews with European public health leaders). European Journal of Public Health, 2014. Nynke de Jong, Karen D. Könings and Katarzyna Czabanowska. The Development of Innovative Online Problem-Based Learning: A Leadership Course for Leaders in European Public Health. Journal of University Teaching & Learning Practice, 2014. Czabanowska, Katarzyna; Moust, Jos H.C., Meijer, André W. M., Schröder-Bäck, Peter and Roebertsen, Herma, Problem-based Learning Revisited, introduction of Active and Self-directed Learning to reduce fatigue among students. Journal of University Teaching & Learning Practice, 2012. William Sherlaw, Kasia Czabanowska, Mark Thompson: English for public health teaching within the context of internationalisation in France in Wilkinson, Robert / Walsh, Mary Louise (eds.) Integrating Content and Language in Higher Education From Theory to Practice. Selected papers from the 2013 ICLHE Conference. Peter Lang GmbH Frankfurt am Main, Berlin, Bern, Bruxelles, New York, Oxford, Warszawa, Wien, 2015. Christoph Aluttis, Claudia Bettina Maier, Stephan Van den Broucke, Katarzyna Czabanowska. Developing the public health workforce in eds: Bernd Rechel and Martin McKee. Facets of Public Health Today. Open University Press. McGraw- Hill Education. Berkshire, England 2014. Katarzyna Czabanowska, Karen Konings, Tony Smith. Teachers’ perceptions of working with the online environment and some learning points based on the LEPHIE project. In ed. Vesna Bjegovic Milankovic. Modern Teaching- distance learning. A guide to online and blended learning with case studies from public health. Brussels 2013. |  |  |  |
| Jascha de Nooijer |  | Jascha de Nooijer is Director of Education for Health at the Faculty of Health, Medicine and Life Sciences, Maastricht University, the Netherlands. She is responsible for two bachelor's programmes (Health Sciences and European Public Health) and nine master's programmes (Epidemiology; Governance and Leadership in European Public Health; Global Health; Health Education and Promotion; Health Sciences Research; Healthcare Policy, Innovation and Management; Human Movement Sciences; Mental Health; and Work, Health and Career). She holds a PhD in Health Promotion (2001), but shifted her career toward education after she graduated from the master's programme in Health Profession Education. Since then, she has been involved in various educational roles, e.g. as a member of the Board of Examiners, as a director of the master's programme in Health Education and Promotion, and as the faculty coordinator for the programme for excellent students (Premium), besides tutoring, lecturing and supervising students. She has a passion for innovation in education, for instance, developing an online course, or using a virtual world to simulate real-life situations for the purpose of learning. Her focus in education is on interprofessional collaboration and teamwork in education, as she believes that such competencies prepare students for their future professions. |  |  |  |
| Matthew Commers |  | Matthew (Matt) Commers is Assistant Professor of European Public Health with the Department of International Health at Maastricht University in the Netherlands. He is currently Director of the Bachelor of European Public Health Programme at Maastricht University. Area of content expertise include: public health education; comparative health care systems and health policy; cross-border care and public health, social epidemiology and health inequalities, health promotion; theory of determinants of health and research on the meaning of health to people. Dr. Commers received his Ph.D. from Maastricht University in 2001. He holds a Master’s degree in Health Policy and Administration from the University of California at Berkeley, and a Bachelor’s degree from the University of Michigan at Ann Arbor. He has over twenty years of professional experiences in higher education, healthcare and public health, including five years in consulting and three years in hospital administration. He holds a second appointment as Adjunct Assistant Professor at the University of Minnesota School of Public Health (USA). |  |  |  |

Please copy and paste tables as necessary

# F.4 List of Associated Partners

(Where applicable)

Capacity-building projects can involve associated partners who contribute to the implementation of specific project tasks/activities or support the dissemination and sustainability of the project. Associated Partners cannot be responsible for core activities of the project (e.g. management, coordination, monitoring, leader of a work group etc.). No financial contribution from the project grant will be allocated to these organisations.

☐

| Name of organisation | Type of institution | Website | City | Country | Role in the project | Activities and related Work Packages |
| --- | --- | --- | --- | --- | --- | --- |
| Association of Schools and Programs of Public Health (ASPPH) | NGO | https://www.aspph.org/ | Washington, DC | United States | Review of materials | As ASPHER’s counterpart organization in North America, ASPPH brings additional international expertise on workforce qualifications through their Certified in PH (CPH) programme and created the first TIPH campaign. It will act as a Reviewer on relevant actions and deliverables (WP2, WP4, WP6). |
| Agency for Public Health Education Accreditation (APHEA) | NGO | https://www.aphea.be/ | Brussels | Belgium | Review of Educational Programmes | APHEA offers review and accreditation to PH education and training courses in Europe and Internationally. It will act as a Reviewer on WP3, education harmonization. |
| World Health Organization – Regional Office for Europe (WHO/Europe) | NGO | http://www.euro.who.int/en/home | Copenhagen | Denmark | Internship, Practicum and research, International outreach | WHO-Europe will be a resource for understanding international PH workforce needs, internship and practicum opportunities to Israeli students and provide international stakeholder engagement (WP2, WP4, WP6). |
| Public Health Reviews (PHRS) | Journal | https://publichealthreviews.biomedcentral.com/ | London | United Kingdom | Dissemination | As the official Journal of ASPHER, PHR may be used to disseminate project outcomes (WP7). |
| Barzilai Hospital | Barzilai Hospital | www.bmc.gov.il/eng https://www.linkedin.com/company/barzilai-medical-center | Ashkelon | Israel | Research practicum for 3rd year students | Barzilai Hospital will provide local research practicums and can provide training courses for senior doctors (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Ashkelon city | Municipality | www.ashkelon.muni.il | Ashkelon | Israel | Community Campaigns | Ashkelon City provides real world local experience with community PH campaigns and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Sick Funds | Primary health care clinics | Various | Various | Israel | Practicum /Stakeholder engagement | Israeli Sick Funds can provide local research practicums and placements (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Healthy Cities Israel | NGO network | www.healthycities.co.il | Jerusalem | Israel | Community Campaigns/ Practicum | Healthy Cities Israel provides real world local experience with community PH campaigns and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Israeli TB and Lung Association | NGO |  | Rehovot | Israel | Community Campaigns/ Practicum | The Israeli TB and Lung Association provides real world local experience with community PH campaigns and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Israel Paediatric Association (IPA) | NGO |  |  |  | Community Campaigns/ Practicum and research | The IPA provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Israel Health Promotion Society | NGO |  |  |  | Community Campaigns/ Practicum and research | The Israel Health Promotion Society provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Israel AIDS Task Force | NGO | http://www.aidsisrael.org.il/ | Tel Aviv | Israel | Community Campaigns/ Practicum and research/ Stakeholder engagement | The Israel AIDS Task Force provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Israel Cancer Association | NGO | http://en.cancer.org.il/ | Givatayim | Israel | Community Campaigns/ Practicum and research/ Stakeholder engagement | The Israel Cancer Association provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Midaat – for informed health | NGO | http://midaat.org.il/midaat/midaat_english/ |  | Israel | Community Campaigns/ Practicum and research/ Stakeholder engagement | Midaat provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Israel Society of Ecology and Environmental Sciences, | NGO | http://www.isees.org.il/?lang=en | Tel Aviv | Israel | Community Campaigns/ Practicum and research/ Stakeholder engagement | The Israel Society of Ecology and Environmental Sciences provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| The Heschel Center for Sustainibility | NGO | https://www.heschel.org.il/heschelen-media | Tel Aviv | Israel | Community Campaigns/ Practicum and research/ Stakeholder engagement | The Heschel Center for Sustainibility provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| The Israeli Forum for Sustainable Nutrition | NGO | https://english.ifsn.org.il/ | Rehovot | Israel | Community Campaigns/ Practicum and research/ Stakeholder engagement | The Israeli Forum for Sustainable Nutrition provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Haifa District, Ministry of Health | Governmental |  | Haifa | Israel | Community Campaigns/ Practicum and research/ Stakeholder engagement | The Haifa District, Ministry of Health provides real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Health maintenance Organizations | public | various | Northern region of Israel | Israel | Practicum/ Stakeholder engagement | Health Maintenance Organizations can provide local research practicums and placements (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Local authorities | Municipalities or local authorities | various | various | Israel | Community Campaigns/ Practicum and research/ Stakeholder engagement | Varoius local authorities throughout Israel provide real world local experience with community PH campaigns, research practicums and involvement with local stakeholders (WP4, WP6). As a local PH employer it will participate in Field Qualifactions survey (WP2). |
| Department for Nursing and Health Sciences, Fulda University of Applied Sciences | HEI | https://www.hs-fulda.de/en/studies/departments/nursing-and-health-sciences | Fulda | Germany | Consultation and Review | Although not in a position to join the proposal as a full consortium partner, Fulda University concentrates on Bachelors level PH eduation and may consult the project development from that specific perspective reviewing materials relating to bachelor/entry level competencies. (WP2, WP3, WP4). |

Please insert rows as necessary

# PART G – Impact and Sustainability

# G.1 Expected impact of the project

Please explain which target groups will use the project outputs /products /results. Describe how the target groups will be reached and involved during the life of the project and afterwards and how the project will benefit the target group at local, regional, national and/or regional level. Please structure your description according to the different levels of impact and stakeholders.

☐

| # | Project results | Who will they impact at national, regional level? | How? |
| --- | --- | --- | --- |
| 1 | Field Qualifications Survey instrument [2.1] | Key stakeholders at local and national levels. Local: e.g., HEI administrative staff, training providers, PH employers, local communities. National: e.g., Employer organisations, national PH organizations, Ministries, government bodies | Local and National: The Field Qualifications Survey will be widely distributed to PH employers in Year 1 of the project period for PHW mapping purposes. Local and National: The Survey will be included in dissemination activities during the Project period. The Survey will be made available on the project website during and after the project period. Local and National: Key stakeholders in the Israeli PH system may freely use and adapt the tool for their own self-assessment or analysis needs. Local and National: Israeli Project Partners will continue to promote the survey after the project period and may use it for periodic checks of the PH system to keep programmes up to date. |
| 2 | Report from the survey of Field Qualifications [2.2] | Key stakeholders at local and national levels. Local: e.g., HEI administrative staff, training providers, PH employers, local communities. National: e.g., Employer organisations, national PH organizations, Ministries, government bodies. Local and National: students, trainees, alumni, and other relevant to benefit from wide dissemination of the report for career guidance, and education/training choice – fully realized via PHI PHRF (see point 5 below). | Local and National: The Field Qualifications Report and key findings will be included in dissemination activities during the Project period. The Report will be made available on the project website during and after the project period and distributed to employers and stakeholders who took part in the survey [2.1]. Local and National: HEIs, employers PH organisations, government bodies, and other relevant stakeholders of the Israeli PH system will have access to the Field Qualifications Report and may use the results for their own competencies development needs or PHW/system planning. Local and National: Key Partners such as IAPHP will continue to widely promote the Report and results after the project period. |
| 3 | Survey instrument to map the competency profiles of the Israeli schools and programmes of PH [3.1] | Local: HEIs offering programmes of PH in Israel. National: Israeli Council for Higher Education (CHE) | Local: The Competency Profile Survey will be distributed to all HEIs offering programmes in PH in Israel for mapping purposed in project year one. National: The CHE will be made aware of the project and survey and may choose to adapt the Survey for its own future use. Local and National: The Survey will be included in dissemination activities during the Project period. The Survey will be made available on the project website and to all schools and programmes of PH in Israel and may be used and adapted to their own assessment needs. Local and National: Israeli Project Partners will continue to promote the Survey after the project period and may use it for periodic checks of their competency offers to keep programmes up to date. |
| 4 | Report from the mapping of the competency profiles of the Israeli schools and programmes of PH with recommendations for harmonization at all educational levels and with the PHW field qualification needs [3.2]. | Local: HEIs offering programmes of PH in Israel. National: Israeli Council for Higher Education (CHE) Local and National: students, trainees, alumni, and other relevant to benefit from wide dissemination of the report for career guidance, and education/training choice – fully realized via PHI PHRF (see point 5 below). | Local and National: The competency mapping Report and key findings will be included in dissemination activities during the Project period. The Report will be made available on the project website during and after the project period and distributed to HEIs who took part in the Survey [3.1]. Key Partners will continue to widely promote the Report and results after the project period. National: CHE will be provided access to the Report. |
| 5 | PHI PHRF online tool [4.1] | Local: HEI Teaching staff, Students, Trainees, Administrative staff, Technical staff, Librarians, Alumni, Local Employers National: National Employers, Employer organisations, PH system governance and other relevant stakeholders in the Israeli PH system. | Local and National: The PHI PHRF tool will have its own dedicated online platform built during the project and maintained by HEIs after the project period. Local: Platform consoles will be installed at participating HEI campuses to allow free access to students. Local and National: Target groups will be informed of and encouraged to use and engage in the platform at all levels of the Israeli PH system. Local and National: Social media will be used to promote the platform. PHI PHRF tool will be included in dissemination activities during the Project period. Israeli Partners will continue to promote and use the tool after the project period |
| 6 | PHI Practical Placement Scheme [4.2] | Local: Students, trainees, faculty, PH employers, local communities. Local and National: Public Health Community Campaigns | Local and National: The PHI Practical Placement Scheme will provide students and trainees with practical research experience with PH employers both in local communities and for national and local PH community campaigns. Local and National: The Practical Placement scheme will be implemented twice during the project period and promoted widely to students seeking practicums, and Associate Partners, PH employers and communities seeking to expand their capacities through student placements. Partner HEIs will continue with Placement Schemes after the project period. |
| 7 | PHI Career Fair [4.3] | Local: Students, trainees, alumni, and PHW and wider Health Workforce in Israel. Local and National: Local and National PH employers | Local and National: The Career Fair will be developed during the project period and held in year 3 of the Project with participation of students, trainees, alumni and other PHW jobseekers as well as local, and national employers. Local: The Career Fair will be promoted at all HEIs with PH related programmes. Local and National: Associate Partners, PH Employers identified in WP2 and others will be invited to the Career Fair to recruit future employees. Local and National: A social media campaign will promote the Fair. Local and National: Israeli Partners will organize an annual PHI Career Fairs after the project period. |
| 8 | PHI Leadership Academy Train-the-trainer Manual with leadership training modalities [5.1] | Local: PHI Leadership Academy, HEI Teaching Staff National: HEIs with programmes of PH in Israel | Local and National: The Train-the-trainer Manual will be included in dissemination activities during the Project period. The Manual will be made available on the project website before and after the project period. All HEIs participating in WP3 will be notified when the Manual becomes available. Local: The manual will primarily be for use by the Leadership Academy, which will continue trainings after the project period. However other HEIs and training programmes may choose to make use of it to better understand leadership and practical PBL training modalities. |
| 9 | Reports from the 5+1 Peer Pilot sessions (evaluation & adaptation of the PHI Leadership Academy framework) / Report (5+1) from the PHI Leadership Academy pilot [5.2] | Local: PHI Leadership Academy National: HEIs with programmes of PH in Israel | Local and National: The Final Report from the 5+1 Peer Pilot Sessions will be included in dissemination activities during the Project period and made available on the project website before and after the project period. All HEIs participating in WP3 will be notified when the Report becomes available. Local: The Report will primarily be for use by the Leadership Academy to determine strengths and weaknesses of the pilots and make improvements for trainings after the project period. The Mandel Foundation will provide continuing support for the PHI Training Academy. Other HEIs and training programmes may choose to use the Report to inform and improve on similar programmes. |
| 10 | PHI IAMPH Campaign Plan [6.1] | Local: Project consortium and other stakeholders participating in the project | Local: The plan will primarily be for internal use by the consortium during the project period, however it will be made available on the project website and other groups may choose to use it to inform similar campaign planning both locally and nationally. |
| 11 | PHI IAMPH Stories [6.2] | National: PH Students, Trainees, General public, PHW, wider health workforce, other professions with PH roles (e.g., lawyers, city planners, engineers, police, teachers), peripheral communities and minorities. | National: Target groups include the core PH and wider health workforce, students, trainees, and general public from across Israel including peripheral and minority communities. The campaign will launch on a dedicated website available before and after the project period and promoted through National and Local social media campaigns. National: The IAMPH Campaign will grow awareness of PH roles played by the PHW and others and increase professional PH identity encouraging target groups to be recognized as PH professionals through the PHI Register [6.4] and seek formal PH training to improve their work and advance careers. Local and National: Partners may continue the IAMPH campaign or similar after the project period. |
| 12 | PHI IAMPH happenings at IAPHP conferences [6.3] | National: PH Students, Trainees, PHW, wider health workforce, allied professions and other IAPHP conference attendees. | National: Target groups include the core PH and wider health workforce, PH students and trainees, and other allied professions. Participation will be promoted at the annual IAPHP conference bringing together a national audience of IAPHP’s network. National: The IAMPH Campaign will grow awareness of PH roles played by the PHW and others and increase professional PH identity encouraging target groups to be recognized as PH professionals through the PHI Registrer [6.4] and seek formal PH training to improve their work and advance careers. National: IAPHP may continue with similar events after the project period. |
| 13 | PHI PHW Register [6.4] | National: PHW, wider health workforce, other allied professions, other professions with PH roles (e.g., lawyers, city planners, engineers, police, teachers), workers providing EPHOs in peripheral communities and minorities. | National: The PHI Register will be implemented during and maintained after the project period by IAPHP. All professionals with a PH role will be encouraged to register their professional status which will provide validated recognition of their professional status and strengthen their professional PH identity. National: The PHI Register will be promoted widely through the IAMPH Campaign and other social media. IAPHP will continue to promote the Register after the project period and Partner HEIs will encourage students and alumni to register. |
| 14 | Report from the IAMPH Campaign pilot [6.5] | Local: Project consortium and relevant stakeholders in the project. | Local: The report will primarily be for internal use by the consortium during the project period. However, it will be made available on the project website during and after the project period. |
| 15 | SEEEPHI Public Health Reviews (PHRS) supplement [7.4] | National: HEI Teaching Staff, Librarians, Wider PHR readership | National: Papers of the project results will be published in a special edition of PHRS. PHRS is now ASPHER’s Society Journal, but it was originally published in Israel and retains a readership in county. It will target the wider national and international PHRS readership who may benefit by learning from and implementing similar actions. PHRS is hosted freely online and listed in recognized Pubmed and Web of Science search engines. It will be available during and after the project period. |
| 16 | Project website, newsletter & social media (Facebook, Twitter, Instagram, Youtube, Linkedin) [7.5] | Local and National: Teaching Staff, Students, Trainees, Wider Internet, social media community, PHW | Local and National: Project results and materials will be promoted widely to the PH community through the project website, newsletter and social media campaigns. The project website will be available locally, nationally and internationally and materials will be available during and after the project period. It will benefit any stakeholder wishing to learn from the project or implement other similar actions in Israel or elsewhere. |

Overview of short term impact indicators (during the project EU funding period)

☐

| Short term impact | Target groups/potential beneficiaries | Quantitative indicators (in numbers please) | Qualitative indicators |
| --- | --- | --- | --- |
| Analysis of employer and community expectations of PH field qualifications | PH Employer and community organisations | Total number of employers and community organisations from across the PH system responding to the survey. | Development of the survey instrument; Full survey report. |
| Mapping of competency profiles of HEIs | HEIs | Total number of HEIs from across Israel responding to the survey. | Development of the survey instrument; Full survey report with recommendations for Harmonization. |
| Increased resources for employability, including individual career and PHW planning enabled via PHI PHRF, PHI Career Fair, PHI Practical Placement Scheme. | Students, alumi, PHW, wider health workforce, PH employers, PH organizations, HEIs, other relevant stakeholders | Traffic on PHI PHRF online platform (i.e. users, site visits, etc.). PHI Practical Placement Scheme – total number of placement sites and students taking part in the scheme. Total numbers attending - both job seeker and job providers the PHI Career Fair. | Visibility and overall feedback received over utility of the provided service (online tool, placement scheme, career fair) . |
| Increased resources for leadership training and PBL for Israeli schools and programmes of PH | HEI/Faculty | Number of faculty and trainers trained in the 5+1 pilot peer training sessions. | Overall feedback received and satisfaction of faculty and trainers. |
| Increased awareness of who makes up the PHW through the PHI IAMPH Campaign. Recognition and strengthened PH identity through the PHI Register | General public, PHW/ wider health workforce/ other professionals with a PH role/ peripheral and minority communities | Number of parties actively engaged in the IAMPH campaign and the population and geographical coverage of the campaign. Number of entries in the PHI Register | Overall feedback and visibility of the PHI IAMPH Campaign and PHI Register. |

Overview of long term impact indicators (after the projects EU funding period)

☐

| Long term impact | Target groups/potential beneficiaries | Quantitative indicators (in numbers please) | Qualitative indicators |
| --- | --- | --- | --- |
| Harmonization of PH education and training at all academic levels aligned with the field qualifications required by PH system. | HEIs/PH employers/ broader PH system | Number of HEIs receptive to implementing recommendations - expected in at least the 4 participating Israeli Parner HEIs. | Overall other feedback and discussions in relevant forums (e.g., between HEIs, CHE). |
| Strengthened collaboration with HEIs and PH employer organizations. | HEIs/PH employers/ broader PH system | Number of established collaborative arrangements between HEIs and PH employers. | Greater overall integration of HEIs with the PH system. |
| Well-defined transition track between education levels | Students/HEIs | Number of students continuing to different advanced and parallel academic tracks supported by alumini surveys. | Overall popularity and student and alumni satisfaction of PH studies. |
| Improved employability and clear career paths for PH professionals | Alumni/PHW/PH employers | Number of job posts in the PH system and dynamics in the employment market. | Overall popularity and satisfaction with PH as a profession. |
| PHW Development and Professionalization plans in place in the PH system. | Decisionmakers/ relevant PH system stakeholders | Number of policies proposed and implemented to develop the PHW. | Overall visibility and relevant discussions on PHW planning in the Israeli PH system and governance. |
| Strengthen Leadership Capacity in the Israeli PH system. | HEIs/PH employers/ other PH system stakeholders | Number of new leadership and PBL oriented skills courses, integrated in PH education programmes. | Overall greater performace of the Israeli PH system |
| High public awareness of PH issues and strong recognized PH profession in Israel. | General public/PHW/ wider health workforce | High level of PH literacy. Sufficient number of professionally recognized and identified PH workers. | Overall PH system performance and appreciation for the work and roles of PH professionals. |

# G.2 Dissemination and exploitation strategy

Please explain how the dissemination will be organised during and after the project's lifetime. Define each target group and what communication channels will be used to reach them and when.

☒

| Target Group | Means of Communication to Reach These Target Groups | When | Indicators to measure the effectiveness of the means of communication |
| --- | --- | --- | --- |
| Israeli PH Community | Dissemination Workshops at IAPHP Public Health Conference | Annually 2022-2023 | Number of audience members attending project dissemination sessions at conference. Increase in traffic to project website. |
| ASPHER Community (100+ HEIs in the WHO European Region represented by 40+ countries) | Project presentations at ASPHER Deans’ and Directors’ Retreat | Annual Retreat 2021 - 2023 | Number of audience members attending project related presentation sessions. Increased visibility of project content in the ASPHER website and blog. Increase in traffic to project website. |
| Wider International PH Community | EPH Pre-Conference serving as final conference of the project | 2023 | Number of audience members attending pre-conference. Potential for project sustainability and scale-up. Increase in traffic to project website |
| Wider PH community | Freely available Open-access Public Health Reviews supplement | During and after the project period | Number of readers accessing articles. Altmetric attention score. Number of article citations. |
| PH Community inside and outside Israel | Project website, newsletter and social media | During and after project period | Number of visitors to the website and reactions to social media communications |

# G.3 Sustainability

Explain how exploitation activities will ensure optimal use of the results within the project's lifetime and afterwards. Explain how the impact of the project will be sustained beyond its lifetime.  Please list the outcomes that you consider sustainable and describe the strategy to ensure their long lasting use beyond the project's lifetime. Also explain how the results will be mainstreamed and multiplied at national/regional level. Describe the strategy foreseen to attract co-funding and other forms of non-EU support for the project.

☐

| Sustainable Outcomes | Strategy to ensure their sustainability | Resources necessary to achieve this | Where will these resources be obtained? |
| --- | --- | --- | --- |
| HARMONIZATION of programmes of PH at all academic levels with PHW needs. | Engagement and commitment of Israeli Partner HEIs to maintain harmonization. Wide distribution of the project report across Israel and shared with CHE. Survey Instruments [2.1,3.1] developed during the project may be used to reassess workforce and educational competencies after the project period. | Report and recommendations from the mapping of the competency profiles of the Israeli schools and programmes of PH [3.2]. Survey Instruments [2.1, 3.1]. HEI staff hours to carry out periodic follow up evaluations of competencies after the project period. | The Report and Survey Instruments developed will be freely available on the project website. Israeli HEIs will dedicate staff hours on a periodic basis to reassess/review PHW needs and corresponding educational competencies. |
| Workforce adaptation and inceased EMPLOYABILITY in the Israeli PH System | PHI PHRF online tool [4.1] will be built during the project and sustained by Israeli Partners for continuous use after the project period. This is complemented by the PHI Practical Placement Scheme [4.2] and PHI Career Fair (4.3) rollouts, to be maintained by Israeli HEIs after the project period. | Basic IT skills and staff hours to operate and maintain the PHI PHRF online tool provided by Israeli partners. Commitment of Israeli HEIs and IAPHP to sustain the Scheme and host and the career fair. | Israeli HEIs/IAPHP/MoH/sponsoring employers will provide funding and staff hours. |
| Strong LEADERSHIP capacity in the Israeli PH system | Establishment of PHI Leadership Academy at BGU (P9) as an extention of the existing Mandel Social Leadership Programme. Incorporation of Leadership and PBL methods in PH curricula at Israel HEIs. | PHI Leadership Academy train the trainer manual [5.1]. Trainers trained to sustain training sessions in Leadership education and PBL [5.2]. Dedicated Leadership Academy in country. Staff hours and funding for HEI Faculty to attend the PHI Leadership Academy. Staff hours for HEI Faculty to review and revise course curricula. | Manual [5.1] developed during the project period will be available on the project website during and after the project period. Trainers and faculty trained during the project period can sustain trainings after the project period. Ongoing commitment from Israeli HEIs to dedicate straff hours and funding for faculty to attend the PHI Leadership Academey trainings and review and revise curricula. Sources of funding: Mandel Foundation or others/participating HEIs/MoH/BGU. |
| Increased recognition of the diversity of the PHW through OUTREACH | Continuation of the piloted PHI IAMPH Campaign [6.1,6.2,6.3] to build awareness of PH roles. Establishment of the PHI Register [6.4] through IAPHP to offer official recognition to all members of the workforce performing PH roles. | Commitment from Isreali partners to continue IAMPH/TIPH type campaigns to continue to build an reinforce awareness of PH roles and who performs them. Commitment from IAPHP to maintain and promote the PHI Register. | IAMPH stories [6.2] and campaign planning [6.1] established during the project period may be used and built on for continued IAMPH/TIPH campaigning. HEIs and IAPHP must provide or seek funds required. IAPHP must be commited to maintaining and all partners must be involved in promoting the PHI Register. |

# PART H - Other EU grants

Please list the projects for which the organisations involved in this application have received financial support from EU programmes.

☒

| Programme or initiative | Reference number | Beneficiary Organisation | Title of the Project |
| --- | --- | --- | --- |
| European Commission, DG SANCO, Action Prgramme | CHAFEA/2014/Health/03 | Tenderer: Maastricht University | Tender “Mapping Patients’ Rights in all member States of the European Union” |
| ERASMUS, LifeLong Learning Programme | 510176-LLP-1-2010-1-NL-ERASMUS-ECDCE | Coordinator: Maastricht University | Leaders for European Public Health (LEPHIE) |
| Horizon 2020 Programme DG Research | Horizon2020-PHC-23-2014/634201 | Coordinator: IMPERIAL London Partner: Maastricht University | MOCHA, Models of Child Health Appraised |
| ERASMUS+ Jean Monnet Programme | 565538-EPP-1-2015-1-NL-EPPJMO-NETWORK | Coordinator: Maastricht University, Technical lead: University of Malta | Jean Monnet Network of European Integration, Small States and Health (SMShealth.eu) |
| European Commission, DG SANTE, Action programme | EAHC/2009/Health/05 | Tenderer: Maastricht University | Tender “Developing Public Health Capacity in the EU: A review of the capacity of EU Member States to develop and implement public health policies and interventions” |
| ERASMUS + | 2017-1-AT01-KA107-034900 | Ashkelon Academic College - AAC | Staff Mobility |
| Horizon 2020 | H2020 OPERAM study | Univeristy College Cork | H2020 OPERAM study |
| Erasmus Mundus Joint Master Degrees | 574436-EPP-1-2016-1-FR-EPPKA1-JMD-MOB | EHESP School of Public Health, Rennes, France (Partner – Jagiellonian University Medical College) | EuroPubHealth Plus |
| Erasmus+ KA2 Strategic Partnerships | 2018-1-PL01-KA203-050990 | Jagiellonian University Medical College | International Medical English Testing System |
| Erasmus+ KA2 Strategic Partnerships | 2018-1-NLOI-KA203-038925 | Maastricht University, The Netherlands (Partner – Jagiellonian University Medical College) | Online Adaptive International Progress Testing |
| Erasmus+ KA2 Strategic Partnerships | 2018-1-SK01-KA203-046318 | Pavol Jozef Safarik University in Kosice, Slovakia (Partner – Jagiellonian University Medical College) | Building Curriculum Infrastructure in Medical Education |
| Erasmus+ KA2 Capacity building | 2018-3825-011-011 | University of Pavia, Italy (Partner – Jagiellonian University Medical College) | Improvement of children care teaching as a template for modernising postgraduate medical education in Central Asia |
| Erasmus+ KA2 Strategic Partnerships | 2019-1-PL01- KA203-065700 | LUMINAR Foundation, Poland (Partner – Jagiellonian University Medical College) | CLIL in Medical Education: Reaching for Tools to Teach Effectively in English in a Multicultural and Multilingual Learning Space |
| Erasmus+ KA2 Strategic Partnerships | 2019-1-SE01-KA203-060571 | Regon Blekinge, Sweden (Partner – Jagiellonian University Medical College) | E-LifeLong Learning in Prevention of Suicide in Europe |
| ERASMUS+ KA2 Knowledge Alliances | 612454-EPP-1-2019-1-DE-EPPKA2-KA | University of Augsburg, Germany (Partner – Jagiellonian University Medical College) | Developing, implementing, and disseminating an adaptive clinical reasoning curriculum for healthcare students and educators |
| H2020-PHC-2014 | GA 635316 | PARC SANITARI SANT JOAN DE DEU, Spain (Partner – Jagiellonian University Medical College) | Ageing Trajectories of Health: Longitudinal Opportunities and Synergies |
| H2020-MSCA-RISE-2016 | GA 734684 | PERCUROS BV, The Netherlands (Partner – Jagiellonian University Medical College) | Characterisation Of A Green Microenvironment And To Study Its Impact Upon Health and Well- Being in The Elderly As A Way Forward For Health Tourism |
| H2020-MSCA-RISE-2016 | GA 734790 | STAB VIDA INVESTIGACAO E SERVICOS EM CIENCIAS BIOLOGICAS LDA, Portugal (Partner – Jagiellonian University Medical College) | Blood test for clinical therapy guidance of non-small cell lung cancer patients |
| H2020-MSCA-RISE-2017 | GA 777682 | PERCUROS BV, The Netherlands (Partner – Jagiellonian University Medical College) | Personalised postoperative immunotherapy to improving cancer outcome and improving quality of life |
| H2020-MSCA-ITN-2018 | GA 812656 | KATHOLIEKE UNIVERSITEIT LEUVEN, Belgium (Partner – Jagiellonian University Medical College) | Training Network for Healthcare Innovators for Transitional Care in Senior Citizens |
| H2020-SFS-2018-1 | GA 818318 | FUNDACIO EURECAT, Spain (Partner – Jagiellonian University Medical College) | Impowering consumers to PREVENT diet-related diseases through OMICS sciences |
| HP-JA-01-2017 | GA 801600 | ISTITUTO SUPERIORE DI SANITA, Italy (Partner – Jagiellonian University Medical College) | Joint Action on Health Inequalities |
| H2020 - Mental Health in the Workplace | SC1-BHC-22-2019 | Univeristy College Cork | MINDUP - Mental Health Promotion and Intervention in Occupational Settings |

Please list other EU grant proposals submitted by your organisation, or by any partner organisation in this project proposal. For each grant application, please mention the EU Programme concerned and the amount requested.

☐

| Programme concerned | Beneficiary Organisation | Amount requested |
| --- | --- | --- |
| ERASMUS + Capacity Building | Gordon academic college of education/AAC | 1,000,000 EUR |
| ERASMUS + Capacity Building | Universita' degli studi di Firenze UNIFI/AAC | 1,000,000 EUR |

# PART I - Check List

Please make sure that you fully completed each part of this application form, as follows:

☒

☒ 	PART D - RELEVANCE OF THE PROJECT

☒	PART E - QUALITY OF THE PROJECT DESIGN AND IMPLEMENTATION

☒	E.4 Logical Framework Matrix

☒	E.5 Workplan

☒	E.6 Work packages

☒	PART F - Quality of the Project Team and Cooperation Arrangements

☒	PART G - Impact and Sustainability

☒	PART H - Other EU grants

☒	PART I - CHECK LIST

Please see Programme Guide, Part B for your action, Table A – Project Implementation (amounts in Euro per day) Programme Countries and Table B - Project Implementation (amounts in Euro per day) Partner Countries.